## Slide 1: Planning & Execution Unified Product Lifecycle (UPLC) Overview
UPLC 3.0.0, December 2023

## Slide 2: UPLC 3.0.0 Release Notes for Planning, Development and Platform Execution
UPLC 3.0.0: Product Planning Updates
New Planning Sign-Off criteria added to PK, PC & EC to establish clear hierarchy between standard requirements and milestone level sign-offs to drive bottoms-up accountability
Finance, LFU, Manufacturing and Supply Chain Product Planning requirements updated for IDM2.0 compliance
SAAF expectations changed from recommended to required to insure Intel is IDM2.0 ready and in compliance with managing External Foundry ECI (External Confidential Information) access and removal
New requirements added to PK, PC & EC to drive greater SMG direct input into Product Planning process
Package Assembly Technology interlock criteria added to PK, PC & EC to drive better alignment with Product Planning
EC checklist and UPLC Schedule BKM updated to align with current revision of the Schedule Methodology regarding schedule date types and expected buffer size and to drive better alignment with Gladius Scope & TT2 initiatives
Strategic BOM requirements updated with expectations to align to finance project hierarchy
Minor verbiage updates made to PK, PC and EC Risk Management requirements to improve consistency
Clarification in PRD template and PC & EC requirements that PTP assumptions need to be documented
To ensure key product data is being managed & maintained throughout PLC, Bounding Box process changes captured in Finance & BBOX BKMs
HAS BKM update only to highlight the need for Negative Space cases that require error handling and validation
New Intel Automotive BU Addendum added for PK, PC & EC along with a CCG BU Addendum for PC
UPLC 3.0.0: IP Governance Updates
  IE/IAC requirements scrubbed with changes classified into four categories: L1 (governable requirement changes – 2 reqs), L2 (addendum changes only – 12 reqs), L3 (footnote & explanation changes only – 13 reqs), or L4 (requirement removed as redundant/not needed – 9 reqs)
  IE embedded checklist scrub: Embedded checklist was part of IE document; approved to be incorporated as requirements in UPLC 3.0.0
  95% scan insertion requirements added to earlier IP execution milestones to support the SOC’s efforts to measure coverage and converge on coverage goals
  FV requirements scrubbed as part of an overall UPLC effort to make requirements at TI more SMART
*A complete Change Log since PLC 1.0 can be found here: http://goto.intel.com/PLCRevisionControl

## Slide 3: UPLC 3.0.0 Release Notes for Planning, Development and Platform Execution (cont.)
UPLC 3.0.0: SOC Development Updates
  DEG Staff-sponsored A0 & PROD TI sign-off requirements established to drive GM-level approval for all governed programs
  Scan requirements were overhauled to enable industry competitive Scan and post-Si ramp. SOC SD, SOC MFG, and IP scan requirements added with existing SOC SD/MFG scan requirements scrubbed for clarity or removed as redundant/no longer required.
  IDM 2.0 compliance and overall hygiene (all swimlanes) verified
  Significant simplification and optimization achieved by combining PSS & MDIV swimlanes into the PSS swimlane, clarifying receivables vs. deliverables, and driving tighter interlocks
  SAAF requirement added to A0 TI checklist
  SD swimlane requirements were updated to address an ARL SKT Si escape around unintended power islands and to improve their clarity and measurability
  Fuse swimlane requirements were updated to reflect Fuse latest BKMs and to provide more effective grading and verification
  Silicon Enabling MFG requirements were updated to reflect latest MFG BKMs
  Pre-Si Sys Val 1.0 (TI Gating) Debug Tools and A0 PO Readiness Electrical Validation requirements updated to reflect latest Sys Val BKMs
  PLC CP EC was split into PLC CP EC and PLC CP TR so Platform level EC checklists would map into a separate Governance Checkpoint vs. Design level TR checklists
  PSS TR was split into PSS TR PC & PSS TR EC with PSS TR PC mapped to PLC CP PC and PSS TR EC mapped to PLC CP TR
  PDK & corresponding Bounding Box milestone for 0.3 added and milestone 0.0.1 renamed to 0.01
  The FW-SW swimlane was split into Ingredient level checklists at FW-SW 0.5, 0.8, 1.0 & 1.1 and Platform level checklists at FW-SW 0.0-1.1 with only FW-SW 0.5-1.1 assigned to new milestones called FW-SW Platform
UPLC 3.0.0: Integrated Platform Execution
  PLC Checkpoint designations added to Silicon Ingredient milestone interlock requirements to reduce confusion and to ensure Integrated Platform 1.0 does not gate A0 TI
  Reformatted Platform HW Eng BKM (Platform HW Engineering WG Worksheet) for consistency with Integrated Platform checklist
  Updated PGVP BKM to include definition of PGVP Plan 0.9, 1.0, and 1.1
  Updated Collateral (PAE) BKM for DCAI - shift left on DCAI requirements for ePDG, EDS, and RP design archive from Integrated Platform 1.1 to 1.0
  Added clarifications to the Supply Chain Integrated Platform BKM
*A complete Change Log since PLC 1.0 can be found here: http://goto.intel.com/PLCRevisionControl

## Slide 4: Table of Contents
Product Lifecycle (PLC) Overview & Updates
PLC Timelines for Base and Derivative Die
Appendix
  Overview: PLC Category Themes Pre-Si & Post-Si
  Deep Dive: Long Term Retention for UPLC
  Deep Dive: Pre-Silicon Systems (PSS) PLC
  Deep Dive: Test Chip Development PLC
  PLC Overlays: Security (SDL) PLC

## Slide 5: Pre- & Post-Si PLC for Full Milestones: SOC Development
Planning Phase
0.5 Phase
0.3 Phase
1.0 Phase
A0 TI Phase
Post-Si Phase
Execution Commit (EC)
P&E PLC Integrated Gantt (Chrome): http://goto.intel.com/PLCGantt
*Handoff only for SOC VAL enabling (drop occurs during SOC RTL 0.0 Quality Checks – see Pre-Si Gantt)
SOC RTL
SD TR | SD 0.0 |  | SD 0.5 |  | SD 0.8 | SD 1.0 | 
SD
(Structural Design)
Product/Die Overview HAS
RTL Freeze
Platform A0 PO / PO Exit
PROD Si PO / PO Exit
A0 ES2
PROD TI
Silicon Enabling
& Execution MFG
0.0 | RTL 0.5 | RTL 0.8 | 1.0
UPLC 3.0.0
A0 TI
PROD Si QS
PROD Si PRQ
SOC RTL TR
Tape-in
PRQ
A0 PO Read. | PPOE | Pre-PROD Step | Validation |  | PROD Step Validation
 |  |  | PO Readiness |  | 
A0 Si Read. | PPOE | A0 Execution MFG | PROD Step CE | PROD Step Execution
PSS
(Pre-Si Systems)
SOC VAL
0.0 | 0.3 |  | VAL 0.5 | VAL 0.8 | VAL 1.0
SOC VAL TR
A0 ES1
Pre-Si Sys Val TR | 0.0 |  | Sys Val 0.5 | Sys Val 0.8 | 1.0
 |  | 0.3 |  |  | 
SOC RTL 0.3*
Platform PO Exit
SiE MFG TR | SiE MFG 0.0 | SiE MFG 0.5 | SiE 0.8 | SiE 1.0
Pre-Si &
Post-Si Sys Val
0.3 | 0.5 | IP FW/DRV 0.8 | IP FW/DRV 1.0 | IP FW/DRV 1.1
IP FW/DRV
0.8 Phase
Fuse
Fuse TR
Fuse 0.5 | Fuse 0.8 | Fuse 1.0
A0 Readiness
A0 Validation
PROD Step Readiness
PROD Step Validation
PSS 0.0 | PSS 0.3 | PSS 0.5 | PSS 0.8 | PSS 1.0 | PSS 1.1
PSS TR
Hard Freeze
Non-Governed Milestones
Governed Milestones
IP Design – SIP
IP Design – HIP
All Other HAS
HAS 0.2 | HAS 0.5 | HAS 0.8 | SOC HAS 1.0 | SOC HAS 1.1
IC | IE | EV1 | EV2 | UV1 | UV2 | eFV/FV
IC | IE | EV1 | UV /EV2 | UV | FV
Product
Planning
Product Concept
(PC)
Product Kickoff (PK)
HAS 0.5 | HAS 0.8 | HAS 1.0 | SOC HAS 1.1

## Slide 6: Platform PLC for Full Milestones: Platform Execution
108_84
UPLC 3.0.0
Planning Phase
0.5 Phase
1.0 Phase
Post-Si Phase
Integrated Platform Alpha
SOC A0 PO / PO Exit
SOC A0 TI
Integrated Platform QS
PRQ
Integrated Platform Pre-Alpha
PAS
PAS 0.5 | PAS 0.8 | PAS 1.0
Platform A0 PO Exit
Int. Platform
Pre-Alpha
Int. Platform
Beta
Int. Platform
QS
Int. Platform
PRQ/PV
Integrated Platform Beta
Integrated Platform PRQ/PV
Platform
Power-On
Exit
Int.
Platform
Alpha
Execution Commit (EC)
Release Quality
ARCHITECTURE PATHFINDING | TECHNOLOGY READINESS
*For more information on Platform Execution Swimlanes: https://goto.intel.com/PlatformExecution
**For more information on the FW/SW Swimlane: https://goto.intel.com/PlatformSW
Integrated Platform PLC*
Design Complete
(A0 TI)
A0 PO Readiness
(A0 PO Start)
Mid-Design
(Design 0.8)
Non-Governed Milestones
Self-Governed Milestones
Governed Milestones
Integrated Platform 0.5 | Integrated Platform 1.0 | Integrated Platform 1.1
FW/SW 0.0 | FW/SW 0.1 | FW/SW 0.3 | FW/SW 0.5 | FW/SW 0.8 | FW/SW 1.0 | FW/SW 1.1
FW/SW**
SIM 0.5
Si Product (Die)
0.0 | 0.5 | 0.8 | 1.0 | TI | 1.1
Technology Readiness
Product
Planning
Product Concept
(PC)
Product Kickoff (PK)
Beta
Alpha
Pre-Alpha
PV
SIM 0.8
SIM 1.0
PLC CP PROD TI
VS0
VS1
VSV
Platform HW Eng*
Platform HW Eng 0.5 | Platform HW Eng 1.0 | Platform HW Eng 1.1
Integrated Platform QRC (goto/ReleaseQuality)
Execution Governance + Integrated Platform Execution Governance
Int Plat PRQ/PV
Bounding Box Grading Targets
Platform Planning Only
Ingredient + Platform Development

## Slide 7: PLC Milestone Levels by Project Complexity
 | MINIMUM Milestones | MODERATE Milestones |  |  | FULL Milestones
Milestone Start | SOC RTL 1.0 SOC VAL may begin at 0.8 | SOC RTL 0.8 SOC VAL may begin at 0.5 |  | SOC RTL 0.5 SOC VAL may begin at 0.3 | SOC RTL 0.0 SOC VAL begins at 0.0
1st Gov. Review | Planning: PK Execution: PLC CP 1.0 | Planning: PK Execution: PLC CP 0.8 |  | Planning: PK Execution: PLC CP 0.5 | Planning: PK Exe: PLC CP 0.3
Critical Dependencies | SOC RTL Handoff X.X  SD & SOC VAL X.X Start SOC VAL 0.8 / PSS 0.8 / SOC RTL 1.0  RTL Freeze |  | RTL Freeze / SOC VAL 1.0 / SD 1.0  Hard Freeze Hard Freeze / PSS 1.0 / MDIV 1.0  A0 TI |  | 
IP Readiness | IP RTL at 1.0 quality at SOC RTL 1.0 start 100% of IP development can be Just In Time relative to SOC / SD | All IP RTL at 0.8 quality at SOC RTL 0.8 Start No co-development (IP exists on process node) |  | JIT IP RTL (20%) at 0.5 quality at SOC 0.5 Start Early IP RTL (80%) at 0.8 quality at SOC RTL 0.5 Start | JIT IP RTL at 0.0 quality; Boot IPs at 0.3 quality; Early IPs at 0.5 quality at SOC Start
Database Fork Health | Hard Freeze (A0 TI) quality Inherited Health: High | RTL Freeze (SOC RTL 1.0) quality Inherited Health: Medium |  | <= RTL Freeze (SOC RTL 1.0) quality Inherited Health: Can be Low | New Database
Technical Elements | 1-2 IP changes limited to non-architectural, non-PHI changes (e.g., eMMC 4.4 to 4.5) No re-floorplanning No package changes No change to Boot Flow Small IP experiencing a small SW-visible change (e.g., GMM/legacy IPs) Low number of bugs being pushed from Base | 1-2 IP changes that can change an interface (e.g., HSIC to SSIC, USB 2.0 to 3.0, new GFx core, increasing CPU cores) Re-floorplanning that does not impact package size (e.g., same number of pins / no DFt impact) Boot Flow changes constrained to minor, non-architectural updates Medium number of bugs being pushed from Base |  | Multiple IP changes (3-4+) limited to non-architectural, non-PHI changes -OR- 1-2 IP changes being co-developed starting at 0.5 -OR- Compaction Re-floorplanning can have limited package size impact (limited bump map or pitch changes) Boot Flow may change (e.g., Storage or PM controller modified) High number of bugs being pushed from Base | Lead Arch Products Only Includes New Process IPs & SOC
Common Definition | Universal derivative requirements: No chassis changes, consistent process node with base |  |  |  | 
5_85 15_84
UPLC 3.0.0

## Slide 8: PLC Governance Levels by Swimlane
Governed Swimlanes/Milestones
Full Governance: These requirements and their corresponding milestones are required and must be fully governed at applicable Governance Checkpoints
Requirements reside in main body of UPLC Catalog and are marked as ‘Must Have’ or ‘Governed’ as their Governance Priority
Online Governance Checklist System expected to be used to identify PLC gaps
Active PLC Governance Review Board (GRB) members and Product Domain Experts are expected to participate in the Governance Review
Pre-Reviews by the Swimlane’s GRB Lead are expected to be conducted with their Project Functional Area counterpart
SOC/IP Design Swimlanes: Design (A0/PROD TI), SOC RTL, SD, SOC VAL, PSS, IP FW/DRV including 1.1 and Platform PROD TI Gate, Silicon Enabling MFG, Silicon Execution MFG (PROD TI ECO Cutoff Only), Pre-Si Sys Val, Post-Si Sys Val (PROD TI ECO Cutoff Only), Pre-Si Fuse, Post-Si Fuse (Fuse A0), IP Design
Product Planning Swimlane: Product Kickoff (PK), Product Concept (PC), Execution Commit (EC)
Platform Execution Phase Swimlanes: Integrated Platform PLC (Governance owned by PMOX), FW/SW (Planning & Development Phase; Governance owned by Release Quality)
Self-Governed Swimlanes/Milestones
Limited Governance: These requirements and their corresponding milestones are optional for governance
Requirements reside in the Addendum of the UPLC Catalog and are marked ‘Self-Governed’ as their Governance Priority
Online Governance Checklist System may be used to deploy & grade these requirements upon customer request
Active GRB members not required for Governance; Pre-Reviews by GRB not required
Product domain experts not required in the Reviews except if Waiver or Gate requested
SOC Swimlanes: SD 0.0
Platform Execution Phase Swimlanes: Platform HW Eng
Business Unit Planning Addendums: CCG (PC Only), DCAI, NEX, Automotive (Auto)
Non-Governed Swimlanes/Milestones
No Governance: These requirements and their corresponding milestones are provided for informational purposes only
Requirements reside in the Addendum of the UPLC Catalog and are marked ‘Non-Governed’ as their Governance Priority
The Online Governance Checklist System can not be used to deploy & grade these requirements
Active GRB members not required for Governance.
Pre-Reviews by GRB not required
Product domain experts not required in the Reviews
SOC/IP Swimlanes: SOC HAS, CDFS, Silicon Execution MFG (non-PROD TI), Post-Si Sys Val (non-PROD TI), Post-Si Fuse (PROD Stepping)
Platform Execution Phase Swimlanes: PAS
UPLC 3.0.0

## Slide 9: PLC Requirements Governance Prioritization
UPLC 3.0.0
UPLC 2.5.0+ Governance Priority | UPLC 2.4.0 Governance Priority | Governance Priority Definition | Kind of Criteria | Impact = Low/Medium | Impact = High/Showstopper
Must Have | Must Have | Governed requirements Highest impact requirements that are most likely to gate a program if not complete | Base Criteria | Waiver or Modulation (team signoff) | Exception (management approval)
Governed | Potential Gate Non-Gating (Main Body) | Governed requirements Impactful requirements that may gate a program if not complete (situation dependent) | Base Criteria | Waiver or Modulation (team signoff) | Exception (management approval)
Self-Governed | Non-Gating (Addendum) | Self-Governed requirements found in the UPLC’s addendums Optional for BU/Functional Team to deploy (however, if deployed they become required to grade) BU/Functional Team level impacting requirements representing optimized execution within a program (includes stretch goals, unique segment needs) Enables data collection and/or hardening a new process that will eventually move to Must Have or Governed Governance Priority (includes pilot milestones and criteria) | Optional but Recommended Criteria Pilot of New Milestones and Criteria | Waiver or Modulation (team signoff) | Exception (management approval)
Non-Governed | Reference Guide | Requirements are not governed and rarely deployed & graded Can include reference information/material Not available as part of default tool | Custom/Program Specific Criteria Legacy Criteria | No Exceptions No Waivers No Modulations | 

## Slide 10: IP Governance Review Checkpoints
99_84 106_84 113_84 123_84
UPLC 3.0.0
IP Governance Checklists and other collateral can be found at: http://goto.intel.com/IPGovernance

## Slide 11: Planning Governance Review Checkpoints
TR Assess
99_84 106_84 113_84 123_84
Tape-in
IP Planning
UPLC 3.0.0
Execution Commit (EC)
IP Execution Commit (IE)
IP Concept (IC)
IP Ready
Product Concept (PC)
Planning Governance Checklists and other collateral including the Product Roadmap Addition Without Stepping Checklist can be found at: http://goto.intel.com/PlanningGovernance
SD TR | SD 0.0 |  | SD 0.5 |  | SD 0.8 | SD 1.0 | 
0.0
Product HAS/Die Overview HAS
SOC RTL Handoff
SOC VAL
SD
Hard Freeze
SD Cleanup
RTL 0.0 | SOC RTL 0.5 | SOC RTL 0.8 | RTL 1.0
SOC RTL
0.5
1.0
0.8
0.0 | VAL 0.3 |  | SOC VAL 0.5 | SOC VAL 0.8 | SOC VAL 1.0
RTL Freeze
SOC RTL 0.3
SiE MFG TR | SiE MFG 0.0 | SiE MFG 0.5 | SiE MFG 0.8 | SiE MFG 1.0
SOC RTL TR
SOC VAL TR
Silicon Enabling MFG
GLS
IP FW/DRV 0.3 | IP FW/DRV 0.5 | IP FW/DRV 0.8 | IP FW/DRV 1.0 | IP FW/DRV 1.1
IP FW/DRV
Fuse
Fuse TR
Fuse 0.5 | Fuse 0.8 | Fuse 1.0
Pre-Si Sys Val TR | 0.0 |  | Pre-Si Sys Val 0.5 | Pre-Si Sys Val 0.8 | Sys Val 1.0
 |  | Pre-Si Sys Val 0.3 |  |  | 
Pre-Si Sys Val
PSS
PSS 0.0 | PSS 0.3 | PSS 0.5 | PSS 0.8 | PSS 1.0
Basic boot to OS with Slim FW*
Basic boot with Prod-Lite FW**
PSS TR
D2I
IP Design – SIP
IP Design – HIP
All Other HAS
Product Planning
Product Kickoff (PK)
PLC CP # | Primary Anchor Milestone | IP Gov Milestones* *For select programs only | Other Key Milestones** **EC-Gating TR Requirements Only
PLC CP PK | Product Kickoff (PK) |  | 
PLC CP PC | Product Concept (PC) | IP Concept (IC) | PSS TR PC
PLC CP TR PLC CP EC | PLC CP EC: Execution Commit (EC) | IP Execution Commit (IE) | PLC CP TR: SOC RTL TR, SD TR, SOC VAL TR, PSS TR EC, SiE MFG TR, Pre-Si Sys Val TR
IC | IE | EV1 | UV/EV2 | UV | FV
IC | IE | EV1 | EV2 | UV1 | UV2 | eFV/FV
Product Definition validated externally. LZ requirements frozen and under change control. Established initial POR w/full engineering response. Product value, financial sanity check completed.
Setting product requirements and initial prioritized technology opportunities.
Initial product direction and frame including program goals & segmentation strategy. Long-lead features & technologies identified to enable Pathfinding. Investment budget & initial development plan provided.
HAS 0.2 | HAS 0.5 | HAS 0.8 | HAS 1.0 | HAS 1.1
HAS 0.5 | HAS 0.8 | HAS 1.0 | HAS 1.1
PSS TR PC
PSS TR EC
UPLC’s Planning Governance Program uses standardized Checklists to drive disciplined Planning Milestone closure and to establish transparency around Planning Waiver requests & approvals
Product Kickoff (PK)
PK
Product Concept (PC)
PC
Execution Commit (EC)
EC/TR

## Slide 12: Pre-Si Governance Review Checkpoints
TR Assess
99_84 106_84 113_84 123_84
Tape-in
IP Planning
UPLC 3.0.0
Execution Commit (EC)
IP Execution Commit (IE)
IP Concept (IC)
IP Ready
Product Concept (PC)
Checkpoint to Milestone Map Report can be found here (bottom row): http://goto.intel.com/PLCReports
PLC CP # | Primary Anchor Milestone | Other Anchor Milestones | IP Gov Milestones* *For select programs only | Other Key Milestones
PLC CP 0.3 | SOC VAL 0.3 | None | EV2 (HIP)/UV (SIP) | SOC RTL 0.0/0.3, SOC VAL 0.0, PSS 0.0, IP FW/DRV 0.3; Optional: SD 0.0
PLC CP 0.5 | SOC RTL 0.5 | None | UV1 (HIP)/UV (SIP) | PSS 0.3, Pre-Si Sys Val 0.0/0.3, SiE MFG 0.0, Fuse TR, IP FW/DRV 0.5
PLC CP 0.8 | SOC RTL 0.8 | SD 0.5, SOC VAL 0.5 | UV2 (HIP)/FV (SIP) | PSS 0.5, Pre-Si Sys Val 0.5, SiE MFG 0.5, Fuse 0.5, IP FW/DRV 0.8
PLC CP 1.0 | SOC RTL 1.0 (inc. Freeze) | SD 0.8, SOC VAL 0.8 |  | PSS 0.8, Pre-Si Sys Val 0.8, SiE MFG 0.8, Fuse 0.8, IP FW/DRV 1.0
PLC CP A0 TI | A0 TI (@ A0 TI – 2wks) | None | eFV/FV (HIP) | SD 1.0, SOC VAL 1.0, PSS 1.0, Sys Val/MFG 1.0, Fuse 1.0, Hard Freeze
Governance Swimlanes
Key: Lead Arch Products Only
SD TR | SD 0.0 |  | SD 0.5 |  | SD 0.8 | SD 1.0 | 
0.0
SOC RTL Handoff
SOC VAL
SD
Hard Freeze
SD Cleanup
RTL 0.0 | SOC RTL 0.5 | SOC RTL 0.8 | RTL 1.0
SOC RTL
0.5
1.0
0.8
0.0 | VAL 0.3 |  | SOC VAL 0.5 | SOC VAL 0.8 | SOC VAL 1.0
RTL Freeze
SOC RTL 0.3
SiE MFG TR | SiE MFG 0.0 | SiE MFG 0.5 | SiE MFG 0.8 | SiE MFG 1.0
SOC RTL TR
SOC VAL TR
Silicon Enabling MFG
GLS
IP FW/DRV 0.3 | IP FW/DRV 0.5 | IP FW/DRV 0.8 | IP FW/DRV 1.0 | IP FW/DRV 1.1
IP FW/DRV
Fuse
Fuse TR
Fuse 0.5 | Fuse 0.8 | Fuse 1.0
Pre-Si Sys Val TR | 0.0 |  | Pre-Si Sys Val 0.5 | Pre-Si Sys Val 0.8 | Sys Val 1.0
 |  | Pre-Si Sys Val 0.3 |  |  | 
Pre-Si Sys Val
PSS
PSS 0.0 | PSS 0.3 | PSS 0.5 | PSS 0.8 | PSS 1.0
Basic boot to OS with Slim FW*
Basic boot with Prod-Lite FW**
PSS TR
D2I
IP Design – SIP
IP Design – HIP
Product Planning
Product Kickoff (PK)
IC | IE | EV1 | UV/EV2 | UV | FV
IC | IE | EV1 | EV2 | UV1 | UV2 | eFV/FV
PSS TR PC
PSS TR EC
0.5
1.0
0.8
0.3
A0 Tape-In
A0 TI
A0 Tape-In
Full Chip Design Enablement
RTL Freeze
Full Chip Design Enablement
Basic Boot Complete
TI-gating SD milestone leading to final synthesis
TI-gating Validation milestone leading to final synthesis
Primary integration milestone enabling SD, SOC VAL & PSS
RTL Code Complete
Basic boot complete ensuring subsequent completion of boot
RTL Freeze

## Slide 13: Post-Si Governance Review Checkpoints
A0 Fab TPT | Volume Samples |  | B0 Fab TPT |  | 
98_85 88_84
Please Note: See Post-Si 2 Stepping Model for a more details
UPLC 3.0.0
Silicon
Post-Si
Sys Val
PSS/
IP FW/DRV
PSS / IP FW/DRV 1.1
FW Code Complete
A0 TI
PROD TI
Fuse
A0 Readiness
PROD Stepping Readiness
PROD Stepping Validation
Volume
Samples
Silicon Enabling/ Execution
A0 Validation
A0 Si Readiness |  | A0 Execution MFG |  | PROD Step CE | PROD Stepping Execution
A0 PO Readiness |  | Pre-PROD Stepping | Validation | POE | PROD Stepping Validation
 |  |  | PROD Step PO Readiness |  | 
A0 POR SKU Validation (started RTL 0.8 exit)
B0 POR SKU Validation
Platform PROD TI Gate
A0
TI
PROD TI
PROD TI ECO Cutoff
A0
Power-On Start
A0 Platform
Power-On Exit
(PPOE)
Platform PO Exit
Post-Si PLC CP # | Anchor Milestone(s) | Other Key Milestones
PLC CP A0 PO | A0 Si Readiness, A0 PO Readiness (occurs @ A0 PO Start – 2wks) | PSS 1.1, IP FW/DRV 1.1 (i.e., FW Code Complete), Fuse A0 Readiness
PLC CP PROD TI | PROD TI ECO Cutoff MFG, PROD TI ECO Cutoff Sys Val (occurs @ PROD TI – 2wks) | Platform PROD TI Gate, Fuse A0 Validation, B0/C0/D0 TI
PRQ
Governance Swimlanes
A0 PO Readiness
A0 PO Readiness (PSS 1.1)
A0 PO
A0 Power-On Start
FW Code Complete & PSS PO Readiness
PROD TI
PROD TI ECO Cutoff
PROD TI Ready, SW/FW Prod TI-Gate
Platform Production TI Gate
Notes: Assumptions
Product complexity range and Pre-Si quality required to enable 2 steppings
Average 14 weeks of Fab TPT time (base on approximation of 14nm standard TPT & 10nm Priority TPT)
  Wide variation of FAB TPT across projects will drive individual project schedule TPT’s.
Above example targets CCG Platform Roll Out Model (ROM5). Alignment across DPG WIP.
  Assumes single ES sampling milestone.
A0 fully functional and validated in pre-Si (< 100 projected or deferred post-Si RTL bugs)
Validation TPT assumes full cycle necessary A0 -> B0
Detailed SW/FW execution requirements & timing WIP (“CSCO” is Customer Sighting Cutoff”)
Silicon HW & SW major external milestones defined by Unified QRC: (https://goto.intel.com/releasequality)

## Slide 14: Table of Contents
Product Lifecycle (PLC) Overview & Updates
PLC Timelines for Base and Derivative Die
Appendix
  Overview: PLC Category Themes Pre-Si & Post-Si
  Deep Dive: Long Term Retention for UPLC
  Deep Dive: Pre-Silicon Systems (PSS) PLC
  Deep Dive: Test Chip Development PLC
  PLC Overlays: Security (SDL) PLC

## Slide 15: Pre-Si PLC for Minimum Milestones (SOC RTL 1.0 Start)
60_84
SD 1.0 | 
SOC RTL Handoff
SOC VAL
SD
Hard Freeze
Tape-in
SOC RTL
1.0
RTL Freeze
PSS
Product HAS/Die Overview HAS
1.0
SOC VAL 0.8** | SOC VAL 1.0
SOC RTL 1.0
PSS D2I
PSS 1.0
Database Fork
*In order to ensure that the project’s first complete design phase is fully enabled, these TR/0.0 milestones are intended to represent the critical planning & early implementation work that should not be skipped (e.g., hierarchy, floorplan, etc.). Expectation is to refresh Base Project’s TR & 0.0 phases (see their Themes for details) with the full list of requirements being project-defined.
**The start of SOC VAL 0.8 will feed off the base product
1.1
SiE MFG 1.0
TR/0.0*
TR/0.0*
TR/0.0*
TR/0.0*
Silicon Enabling MFG
Execution Commit (EC)
A0 TI Phase
UPLC 3.0.0
IP FW/DRV 1.0
IP FW/DRV
Pre-Sys Val 1.0
Pre-Si Sys Val
Non-Governed Milestones
Governed Milestones

## Slide 16: Pre-Si PLC for Moderate Milestones (SOC RTL 0.8 Start)
1.0 Phase
A0 TI Phase
62_84
SD 0.8 | SD 1.0 | 
SOC RTL Handoff
SOC VAL
SD
Hard Freeze
Tape-in
SOC RTL
1.0
0.8
RTL Freeze
Product HAS/Die Overview HAS
SOC HAS 1.0
PSS
SOC RTL 0.8
SOC VAL 0.5 | SOC VAL 0.8 | SOC VAL 1.0
SOC RTL 1.0
TR/0.0*
PSS 0.8 | PSS 1.0
PSS D2I
Pre-Sys Val 0.8 | Pre-Sys Val 1.0
IP Execution Commit (IE)
Execution Commit (EC)
GLS
TR/0.0*
TR/0.0*
TR/0.0*
*In order to ensure that the project’s first complete design phase is fully enabled, these TR/0.0 milestones are intended to represent the critical planning & early implementation work that should not be skipped (e.g., hierarchy, floorplan, etc.). Expectation is to refresh Base Project’s TR & 0.0 phases (see their Themes for details) with the full list of requirements being project-defined.
TR/0.0*
Pre-Si Sys Val
UPLC 3.0.0
IP FW/DRV 0.8 | IP FW/DRV 1.0 | 
IP FW/DRV
SiE MFG 0.8 | SiE MFG 1.0
Silicon Enabling MFG
SOC HAS 1.1
Non-Governed Milestones
Governed Milestones

## Slide 17: Pre-Si PLC for Moderate Milestones (SOC RTL 0.5 Start)
0.8 Phase
1.0 Phase
A0 TI Phase
73_84
SD 0.5 | SD 0.8 | SD 1.0 | SD cleanup
SOC RTL Handoff*
SOC VAL*
SD*
Hard Freeze
Tape-in
SOC RTL*
1.0
0.8
RTL Freeze
Product/Die Overview HAS*
1.0
PSS
TR/0.0** | 0.5
SOC RTL 0.5
SOC RTL 0.8
SOC VAL 0.5 | SOC VAL 0.8 | SOC VAL 1.0
Execution Commit (EC)
SOC RTL 1.0
PSS D2I
PSS 0.5 | PSS 0.8 | PSS 1.0
*Milestone extends before product definition
**In order to ensure that the project’s first complete design phase is fully enabled, these TR/0.0 milestones are intended to represent the critical planning & early implementation work that should not be skipped (e.g., hierarchy, floorplan, etc.). Expectation is to refresh Base Project’s TR & 0.0 phases (see their Themes for details) with the full list of requirements being project-defined.
SiE MFG 0.5 | SiE MFG 0.8 | SiE MFG 1.0
GLS
TR/0.0**
TR/0.0**
TR/0.0**
TR/0.0**
Silicon Enabling MFG
UPLC 3.0.0
Pre-Sys Val 0.5 | Pre-Sys Val 0.8 | Pre-Sys Val 1.0
IP FW/DRV 0.5 | IP FW/DRV 0.8 | IP FW/DRV 1.0 | 
IP FW/DRV
Pre-Si Sys Val
HAS 1.1
Non-Governed Milestones
Governed Milestones

## Slide 18: Pre-Si PLC for Full Milestones
TR Assess
99_84 106_84 113_84 123_84
Tape-in
Note: For all 0.3 milestones, 0.5 activities are happening in parallel; chassis is required to be stable
*Slim FW consists of CSE SV FW, early PMC and PUnit FW, and FSP-Lite (FW (BIOS) Support Package)
**Production Lite consists of “lite” version of CSE production FW to support PSS along with production versions of other boot related FWs
IP Planning
UPLC 3.0.0
Execution Commit (EC)
IP Execution Commit (IE)
IP Concept (IC)
IP Ready
Product Concept (PC)
Planning Phase
0.5 Phase
A0 TI Phase
0.3 Phase
0.8 Phase
1.0 Phase
SD TR | SD 0.0 |  | SD 0.5 |  | SD 0.8 | SD 1.0 | 
0.0
Product HAS/Die Overview HAS
SOC RTL Handoff
SOC VAL
SD
Hard Freeze
SD Cleanup
RTL 0.0 | SOC RTL 0.5 | SOC RTL 0.8 | RTL 1.0
SOC RTL
0.5
1.0
0.8
0.0 | VAL 0.3 |  | SOC VAL 0.5 | SOC VAL 0.8 | SOC VAL 1.0
RTL Freeze
SOC RTL 0.3
SiE MFG TR | SiE MFG 0.0 | SiE MFG 0.5 | SiE MFG 0.8 | SiE MFG 1.0
SOC RTL TR
SOC VAL TR
Silicon Enabling MFG
GLS
IP FW/DRV 0.3 | IP FW/DRV 0.5 | IP FW/DRV 0.8 | IP FW/DRV 1.0 | IP FW/DRV 1.1
IP FW/DRV
Fuse
Fuse TR
Fuse 0.5 | Fuse 0.8 | Fuse 1.0
Pre-Si Sys Val TR | 0.0 |  | Pre-Si Sys Val 0.5 | Pre-Si Sys Val 0.8 | Sys Val 1.0
 |  | Pre-Si Sys Val 0.3 |  |  | 
Pre-Si Sys Val
PSS
PSS 0.0 | PSS 0.3 | PSS 0.5 | PSS 0.8 | PSS 1.0
Basic boot to OS with Slim FW*
Basic boot with Prod-Lite FW**
D2I
IP Design – SIP
IP Design – HIP
IC | IE | EV1 | UV/EV2 | UV | FV
IC | IE | EV1 | EV2 | UV1 | UV2 | eFV/FV
HAS 0.5 | HAS 0.8 | HAS 1.0 | HAS 1.1
HAS 0.2 | HAS 0.5 | HAS 0.8 | HAS 1.0 | HAS 1.1
All Other HAS
Product Planning
Product Kickoff (PK)
PSS TR PC
PSS TR EC
PSS TR
Non-Governed Milestones
Governed Milestones

## Slide 19: Post-Si PLC: 2-Stepping Model
A0 Fab TPT | Volume Samples |  | B0 Fab TPT |  | 
98_85 88_84
Please Note: This is an example PLC timeline to demonstrate phases; timelines will vary due to various factors (FAB TPT, complexity, customer timing requirements, # of steppings, etc.)
Notes:
More assumptions in Slide Notes…
Key Dates:
A0 Power On (A0 PO)
Volume Samples (+4wks)
PPOE = +4wks - +7wks based on design complexity
Pre-Alpha/ES1 = + 9wks(DPG) – +11wks(CCG)
ES2 parts available for validation
B0 EC0 cut-off = 14wks
Platform PROD TI Gate = +16wks
Alpha/ES2 = +18wks
B0 TI = 18wks + A0PO
ES2 = 19-21wks
UPLC 3.0.0
Silicon
Post-Si
Sys Val
PSS /
IP FW/DRV
PSS 1.1 / IP FW/DRV 1.1
A0 TI
B0 TI
Fuse
A0 Readiness
PROD Stepping Readiness
PROD Stepping Validation
Volume
Samples
Silicon Enabling/ Execution
A0 Validation
A0 Si Readiness |  | A0 Execution MFG |  | PROD Step CE | PROD Stepping Execution
A0 PO Readiness |  | Pre-PROD Stepping | Validation | POE | PROD Stepping Validation
 |  |  | PROD Step PO Readiness |  | 
A0 POR SKU Validation (started RTL 0.8 exit)
PROD POR SKU Validation
Platform PROD TI Gate
A0
TI
B0 TI
A0
ES2
B0 PO
B0 QS
B0 PRQ
B0
POE
B0 ECO Cutoff
A0
ES1
A0
Power-On Start
A0 Platform
Power-On Exit
(PPOE)
Platform PO Exit
Post-Si Phase
Beta
PV
Pre-Alpha
Alpha
FW Code Complete
Additional details regarding Platform A0 PO Exit can be found at: http://goto.intel.com/PPOE
Notes: Assumptions
Product complexity range and Pre-Si quality required to enable 2 steppings
Average 14 weeks of Fab TPT time (base on approximation of 14nm standard TPT & 10nm Priority TPT)
  Wide variation of FAB TPT across projects will drive individual project schedule TPT’s.
Above example targets CCG Platform Roll Out Model (ROM5). Alignment across DPG WIP.
  Assumes single ES sampling milestone.
A0 fully functional and validated in pre-Si (< 100 projected or deferred post-Si RTL bugs)
Validation TPT assumes full cycle necessary A0 -> B0
Detailed SW/FW execution requirements & timing WIP (“CSCO” is Customer Sighting Cutoff”)
Silicon HW & SW major external milestones defined by Unified QRC: (https://goto.intel.com/releasequality)

## Slide 20: Post-Si PLC: 2.5-Stepping Model
A0 Fab TPT | Volume Sample |  | B0 Fab TPT |  | B1 Fab TPT | 
98_85 9_84
Key Dates:
A0 Power On (A0 PO)
Volume Samples (+4wks)
PPOE = +4wks - +7wks based on design complexity
Pre-Alpha/ES1 = + 9wks(DCG) – +11wks(CCG)
B0 EC0 cut-off = 14wks
Platform PROD TI Gate
ES2 parts available for validation
Alpha/ES2 = +18wks
B0 TI = 18wks + A0PO
ES2 = 19-21wks
Assumptions:
High Product complexity and/or insufficient pre-si activities could drive 2.5 stepping model.
  Complexity could be driven by new process, high architectural change, unproven IP’s, complex analog circuits w/out test chip, …
Average 14 weeks of Fab TPT time (base on approximation of 14nm standard TPT & 10nm Priority TPT)
  Wide variation of FAB TPT across projects will drive individual project schedule TPT’s.
Above example targets CCG Platform Roll Out Model (ROM5).
All pre-si PLC expectations same as 2-stepping model:
    A0 fully functional and validated in pre-Si, shift-left activities.
    B0/B1 planned for bug fixes only; no new features.
Detailed SW/FW execution requirements & timing WIP (“CSCO” is Customer Sighting Cutoff”)
Silicon HW & SW major external milestones defined by Unified QRC: http://goto.intel.com/releasequality
Silicon
PSS / IP FW/DRV
Fuse
A0 Readiness
B0 Validation
PROD POR SKU Validation
A0 TI
B0 TI
B1 TI
Silicon Enabling/ Execution
B0
PO
A0 TI
B1
PRQ
B0 TI
B1 QS
A0
ES2
B0
ES2
B1 PO
B1
TI
B0 ECO
Cutoff
A0
ES1
A0 Si Readiness |  | A0 Execution MFG | PROD CE | PROD Stepping Execution | PROD CE | PROD Stepping Execution
A0 PO Readiness |  | Pre-PROD Stepping | Validation | PROD POE | PROD | Stepp Validation | PROD POE | PROD Step Validation
 |  |  | B0 PO Readiness |  |  | PROD PO Ready |  | 
A0 Validation
A0 POR SKU Validation (started RTL 0.8 exit)
B0 POR SKU Validation
B0 Readiness
PSS/IP FW/DRV 1.1
FW Code Complete
Platform PROD TI Gate
A0
Power-On Start
A0 Platform
Power-On Exit
(PPOE)
Platform
PO Exit
Post-Si
Sys Val
PROD Step Readiness
PROD Step Validation
Post-Si Phase
UPLC 3.0.0
Alpha
Beta
PV
Pre-Alpha
Please Note: This is an example PLC timeline to demonstrate phases; timelines will vary due to various factors (FAB TPT, complexity, customer timing requirements, # of steppings, etc.)
Additional details regarding Platform A0 PO Exit can be found at: http://goto.intel.com/PPOE

## Slide 21: Post-Si PLC: 3-Stepping Model
Assumptions:
High Product complexity and/or insufficient pre-si activities could drive 3 stepping model.
  Complexity could be driven by: new process, high architectural change, unproven IP’s, complex analog circuits w/out test chip, …
Average 14 weeks of Fab TPT time (base on approximation of 14nm standard TPT & 10nm Priority TPT)
  Wide variation of FAB TPT across projects will drive individual project schedule TPT’s.
Above example targets CCG Platform Roll Out Model (ROM5).
All pre-si PLC expectations same as 2-stepping model:
  A0 fully functional and validated in pre-Si, shift-left activities.
  B0/C0 planned for bug fixes only; no new features.
Detailed SW/FW execution requirements & timing WIP (“CSCO” is Customer Sighting Cutoff”)
Silicon HW & SW major external milestones defined by Unified QRC: http://goto.intel.com/releasequality
98_85 9_84
UPLC 3.0.0
B0
PO
Silicon
PSS / IP FW/DRV
A0 TI
C0
PRQ
A0 Fab TPT |  |  | B0 Fab TPT |  | C0 Fab TPT | 
A0 PO Readiness | A0 POE | Pre- | PROD Stepping Validation | B0 POE | Pre-PROD | Stepping Validation | POE | PROD Stepping Validation
 |  |  | B0 PO Readiness |  |  | PROD Step PO Readiness |  | 
B0 TI
C0 QS
A0
ES1
B0
ES2
C0 PO
C0 TI
A0 Si Readiness | A0 CE | A0 Execution MFG | B0 CE | B0 Execution MFG | PROD Step CE | PROD Stepping Execution
PSS/IP FW/DRV 1.1
Platform PROD TI Gate
B0 POR SKU Validation
A0 Readiness
A0 Validation
B0 Readiness
B0 Validation
A0 POR SKU Validation (started RTL 0.8 exit)
PROD POR SKU Validation
PROD Stepping Validation
Fuse
A0 TI
B0 TI
C0 TI
Volume
Samples
FW Code Complete
C0 ECO
Cutoff
Silicon Enabling/ Execution
A0 Power-On Start
A0 Platform
Power-On Exit
(PPOE)
Platform
PO Exit
Post-Si
Sys Val
PROD Step Readiness
Post-Si Phase
Alpha
Beta
PV
Pre-Alpha
Please Note: This is an example PLC timeline to demonstrate phases; timelines will vary due to various factors (FAB TPT, complexity, customer timing requirements, # of steppings, etc.)
Additional details regarding Platform A0 PO Exit can be found at: http://goto.intel.com/PPOE

## Slide 22: Table of Contents
Product Lifecycle (PLC) Overview & Updates
PLC Timelines for Base and Derivative Die
Appendix
  Overview: PLC Category Themes Pre-Si & Post-Si
  Deep Dive: Long-Term Retention for UPLC
  Deep Dive: Pre-Silicon Systems (PSS) PLC
  Deep Dive: Test Chip Development PLC
  PLC Overlays: Security (SDL) PLC

## Slide 23: Pre-Si PLC: Overview of Category Themes
18_84 27_84
UPLC 3.0.0
 | 0.0 | 0.5 | 0.8 |  | 1.0
SOC RTL | Code and connect hierarchy and floor-plan Integrate all negotiated IPs | Ensure 100% of Globals are feature complete (including fabrics) per HAS | Clean all RTL flows Drive to 100% feature complete RTL |  | Predictable A0 TI execution onfinal RTL
SD | Conduct initial floor plan and die size estimations Provide initial constraint definition and flow verification | Run first full cycle of all partition and fullchip flows on RTL Have layout-based timing quality at SD 0.5 | Converge full SD partition and Full-Chip with fully featured RTL Ensure all tools & flows are functional, run, & results are reviewed |  | Design supports tape-in criteria
SOC VAL | Enable validation tools and infrastructure such that validation execution can start and TFM issues are identified and addressed. | Establish a basic level of health of SOC 0.5 RTL for IP integration and global flows, including exercise of new features | Complete all path clearing and drive sufficient volume validation to de-risk RTL freeze and production quality A0 silicon. |  | Complete all tape-in gating validation
PSS/FW | Create pre-Si SW development Plan Define IP/FW dependencies for each UC/OS Track | Enable pre-Si systems (HFPGA, SLE, n-1) with basic secured boot for SW/FW development and deployment | Finish all HW/SW co-validation (have 100% of IPs ready) Note: this is a freeze gating milestone |  | SW quality checkpoint: Go/No-Go Gate for A0 TI
Silicon Enabling | MFG test plans, execution started to enable 0.5 content Test/Reliability targets refined Support for IP level content checkout and breadth verification FV Val strategy ratified | Basic HVM reset released and passing ITPP repay Initial content creation to verify RTL func and enable depth content creation Initial verif of IP based content in FC Pre Si tests environment enabled | Full HVM reset release All content modes passing in sim/emu to provide final feedback to design Content, hardware and silicon planning to enable first silicon High priority Post Si content delivered |  | Full silicon test content finalized; Test Program shell complete
MDIV | Confirm RTL staging plans meet MDIV needs with IP and SOC design teams. EFFM RTL compile checks are setup correctly and gating SOC RTL releases. | 50% of MDIV content ready and available. All legacy content ported from previous program. Lag die: First X-die model built; ensure it passes reset through first fetch and boots BIOS with 50% emulation collateral integrated and enabled. | 100% of MDIV content ready and available; 100% of emulation collateral integrated and enabled Minimum pass rate of 80% for legacy content and 80% for new features that are enabled All RTL Freeze-gating items are passing |  | Pass rate greater than or equal to 95% and all TI-gating tests passing.

## Slide 24: Post-Si PLC: Overview of Category Themes
18_84 27_84 31_84
UPLC 3.0.0
 | A0 Si Readiness | A0 PO Exit | A0 Execution | PROD TI ECO Cutoff | PROD Stepping Content Enabled | PROD Stepping Execution |  | PRQ
Silicon Execution | 100% of planned content integrated into 1st Si TP Silicon validation complete on all targeted tests Si HW checkout complete Closure of pre-Si test program activities, 100% targeted content available for silicon Power On | Initial mfg test demonstrated on silicon. Enable initial samples to kick off system enabling. Identify and prioritize key areas for debug | PPSM Silicon Execution Successful Full Temp Testing capability enabled | Pre-Si Validation of bug fixes, analysis of characterization data, identification of any key changes to next stepping | Ensure stability of test program to B0 change | All test content deployed to enable final characterization to close GB’s Formal Qual Samples milestone. Close GB's. Enable Factory Startup and Closure of Qual Cert Product ship for revenue granted; final product goals met or waiver with closure plan in place |  | Product ship for revenue granted; final product goals met
 | A0 PO Readiness | A0 PO Exit | Pre-PROD Stepping Val | PROD Step PO Ready | PROD Stepping PO Exit | PROD Step Validation |  | PRQ
Post-Si Validation | SVE/Validation team PO plan done PPV Content Delivered EV Content Ready All Post-Si collaterals are validated and ready for PO with required mitigation Silicon must be fully featured Pre-Si validation completed | All POR HW landing zone features touched for one or few POR skews and aligned configuration Silicon ready for early customer sample Form-factor build go/no-go decision | Complete validation that will impact PC TI and enables PRQable TI Alpha SW released and validated PnP Readiness @ PO Platform golden configuration enabled | Content, tools, SW/FW, systems all ready for B0 Power On | Validate all ECO and bug fixes; ensure quality same or better than ES silicon Silicon ready for early customer sample All PnP indicators/ benchmarks are enabled and within 80% of target | Functional validation complete and focus on platform stability SW / FW release with Beta quality |  | Achieve confidence in volume Si ramp & customer launch

## Slide 25: Table of Contents
Product Lifecycle (PLC) Overview & Updates
PLC Timelines for Base and Derivative Die
Appendix
  Overview: PLC Category Themes Pre-Si & Post-Si
  Deep Dive: Long Term Retention for UPLC
  Deep Dive: Pre-Silicon Systems (PSS) PLC
  Deep Dive: Test Chip Development PLC
  PLC Overlays: Security (SDL) PLC

## Slide 26: Long-Term Retention Requirements for UPLC
*For more information on LTR including LTR Checklist management: http://goto.intel.com/LTRChecklists
Software
Testing & debugging
Documents
Domains
Collaterals / Capabilities
Hardware
Architecture
Design (FE/SD)
Pre-Si Validation
Si Mfg. / Validation
IP SW/FW & Plat. Val.
Milestone
UPLC
LTR Hub
Governance for LTR Requirements
PLC
Rel Quality
LTR
Fab
(Out of Scope)
Program | Swimlane | Governance Checkpoint | LTR Checkpoint | Request | LTR Requirements for PLC Governance
PLC | Design | CP PROD TI | LTR 2: SOC Architecture HAS, SOC Design | Checkpoint to ensure that there is a plan to complete LTR SOC Design checklists by PRQ and HAS documents are accessible | [MUST HAVE] LTR plan reviewed and approved with LTR Governance Lead, including owner and timeline; All HAS documents are accessible in ACMS
RQ | Hardware | PRQ | LTR 3: HW RQ | Checkpoint to ensure LTR Checklists are completed for SOC RTL, SD, Si Mfg and Post Si Sys Val | LTR Checklist complete*
RQ | Platform | PV | LTR 4: Integrated Platform RQ | Checkpoint to ensure LTR Checklists are completed for Integrated Platform | LTR Checklist complete*
Product Concept (PC)
Execution Commit (EC)
Production Release (PRQ/PV)
Product Discontinuance (LTS)
End of Support
PROD TI
A0 TI
A0 PO
LTR 2
LTR 3
LTR4
LTR Verified
LTR Retired
UPLC 3.0.0

## Slide 27: Table of Contents
Product Lifecycle (PLC) Overview & Updates
PLC Timelines for Base and Derivative Die
Appendix
  Overview: PLC Category Themes Pre-Si & Post-Si
  Deep Dive: Long Term Retention for UPLC
  Deep Dive: Pre-Silicon Systems (PSS) PLC
  Deep Dive: Test Chip Development PLC
  PLC Overlays: Security (SDL) PLC

## Slide 28: PSS PLC Swimlane governance – Abbreviated High-Level View
A0
Tape-in
Execution
Commit (EC)
Product
Concept (PC)
FEASIBILITY (1.5Q)
PSS 0.0
CONCEPT (1.5Q)
PSS TR
Dependencies | Receivables | IPs (HW) | Specs, IP changes, features impacting system flows/Features coverage identified, past learnings/escapees | Specs, IP features design and validation staging plan and coverage, commits to PSS | IP collaterals delivery and validation​ | IP collaterals delivery and validation​ | IP collaterals delivery and validation​ | IP collaterals delivery and validation​ | IP Validation related to PSS1.1 features passing ahead of the milestone
 |  | SoC/Die (HW) | Specs, SoC changes, features impacting system flows/Features coverage identified, past learnings/escapees | Specs, SoC features design and validation staging plan and coverage, commits to PSS | SoC Val 0.3 Val Completed and publish results | SoC 0.5 Val completed and published results. Spec Updates to 0.8 | Code Complete and released. Soc Val 0.8 completed, and results published | RTL featured completed and released. SoC Val for all TI gating completed. PO configuration provided and validated | All SoC Val related to PSS1.1 completed. Final PO configuration provided and validated
 |  | FW/SW | Specs, FW/SW changes, features impacting system flows/Features coverage identified, past learnings/escapees | Specs, FW/SW features design and validation staging plan and coverage, commits to PSS | All FW/DRV/SW Developed and integrated Per PSS 0.3 milestone requirements | All FW/DRV/SW Developed and integrated Per PSS 0.5 milestone requirements and code complete | All TI critical FW/SW Feature complete - validation done All FW/SW and Drivers integrated and released to internal/external customers | All FW/DRV/SW Feature complete | 100% of PSS 1.1 BKC/IFWI tests passing. All FW/Drivers integrated into the BKC/IFWI, all fw/drv/sw PO stack integrated and validated in BKC.
 |  | Model | Initial PSS Environment and tools strategy and learnings | Model commitment to PSS and delivery plans in place​ | Essential collaterals and new platform RTL in place. Model alive ​ | RTL 0.5 based models and collaterals delivered with PSS 0.5 features ​ | RTL 0.8 based models and collaterals delivered ​ with PSS 0.8 features ​ | RTL 1.0 based models and collaterals delivered ​ with PSS 1.0 features ​ | TI based models and PO collaterals delivered
 | Planning |  | Risk and new features Analysis for PSS impact.​ Initial PSS Strategy and Coverage matrix​ | Dependencies and Staging Plan.​ ​Technology intercepts​ High level commits | PSS Plan & commits update as required ​ | PSS Plan & commits update as required ​ | PSS Plan & commits update as required ​ | PSS Plan & commits update as required ​ | PSS Plan & commits update as required
Deliverables | Target |  | PSS D2I Readiness and feedback​ | EC+6 weeks ​ Provide pre silicon System Strategy and committed plan​ | RTL 0.5 Feedback​ Provide healthy pre silicon systems ready for CI​ | RTL 0.8 Feedback​ Provide feedback and indication to design health​ | RTL Freeze​ Provide feedback to governance review and decision​ | A0 Tape-In​ Provide feedback to governance review and decision​ | Check point @A0 TI Complete @ A0 Power-On
 | Results |  | Initial val plan in place. Targeted models and flows identified ​ | PSS validation strategy and coverage matrix in place. Validation plan in place ​ | Models alive & ready for continuous integration.​ | Legacy integration & basic system functionality. IP level functionality for new IPs ​ | Critical flows and new functionality. Feedback to RTL Freeze validation and all targeted domains enable ​ | Gating TI focus – All Gating TI flows passing, or bugs dispositioned​ | PO Readiness Flows passing based on PO Platform
PSS1.0
PSS0.8
PSS0.5
PSS0.3
RTL1.0
RTL0.8
RTL0.5
PSS1.1
A0
Power-On
UPLC 3.0.0

## Slide 29: Table of Contents
Product Lifecycle (PLC) Overview & Updates
PLC Timelines for Base and Derivative Die
Appendix
  Overview: PLC Category Themes Pre-Si & Post-Si
  Deep Dive: Long Term Retention for UPLC
  Deep Dive: Pre-Silicon Systems (PSS) PLC
  Deep Dive: Test Chip Development PLC
  PLC Overlays: Security (SDL) PLC

## Slide 30: Test Chip PLC for Full Milestones
99_84 106_84 113_84 123_84
*Note: Test Chip milestone requirements are the same as SOC
UPLC 3.0.0
Tape-in
Test Chip IP RTL*
POLO
PROD
Test Chip
TC IP3
Test Chip HAS*
0.5 | 0.8 | 1.0
0.5 | 0.8 | 1.0
Test Chip RTL*
Test Chip SD*
0.0 | 0.5 |  | 0.8 | 1.0 | 
TC Fab/Package/Test | TC Validation
Hard Freeze
0.0
SOC RTL – Integration and Handoff
Hard Freeze
0.0 QC | SOC RTL 0.5 QC | SOC RTL 0.8 QC | RTL 1.0 QC
SOC RTL – Quality Checks
0.5
1.0
0.8
RTL Freeze
SOC RTL TR
SD TR | SD 0.0 |  | SD 0.5 |  | SD 0.8 | SD 1.0 | 
SOC SD
TC IP2
TC IP1
TC TI
0.5 | 0.8 | 1.0
PSS
Test Chip Planning
Finalize Test Chip Planning (TI-5Qtrs)
SOC RTL 0.3
Test Chip PSS Planning (TI-5Qtrs)
TR Assess
IP Planning
Execution Commit (EC)
IE
IC
IP Ready
Product Concept (PC)
D2I
PSS 0.0 | PSS 0.3 | PSS 0.5 | PSS 0.8 | PSS 1.0
PSS TR
Product Planning
Product Kickoff (PK)
Non-Governed Milestones
Governed Milestones

## Slide 31: Table of Contents
Product Lifecycle (PLC) Overview & Updates
PLC Timelines for Base and Derivative Die
Appendix
  Overview: PLC Category Themes Pre-Si & Post-Si
  Deep Dive: Long Term Retention for UPLC
  Deep Dive: Pre-Silicon Systems (PSS) PLC
  Deep Dive: Test Chip Development PLC
  PLC Overlays: Security (SDL) PLC

## Slide 32: Security Development Lifecycle (SDL) Overview
HW-S0
HW -S1
HW-S2
HW-S3
HW-S4
SW-Pre – Prod
SW-Prod
SW-Post-Prod
Note: Complete Security Development Lifecycle can be found at http://goto.intel.com/SDLe
Product Concept (PC)
Execution Commit (EC)
Production Release (PRQ)
Product Discontinuance (LTS)
End of Support
PROD TI
A0 TI
A0 PO
HW-S5
UPLC 3.0.0
PLC & Release Quality Requirements:
  SDL is integrated in both Planning & Execution UPLC & Release Quality and gates enforced via those execution and governance processes
  Before a new ingredient/component is added from CCB, registration in SDLe is required
  All SDL requirements must be followed else security exception must be approved

## Slide 33: Security (SDL) Integrated PLC
108_84
Note: Complete Security Development Lifecycle can be found at http://goto.intel.com/SDLe
0.0 Phase
0.5 Phase
0.3 Phase
1.0 Phase
A0 TI Phase
Post-Si Phase
0.8 Phase
IP HAS
SOC RTL
SD TR | SD 0.0 |  | SD 0.5 |  | SD 0.8 | SD 1.0 | 
SD
RTL Freeze
Platform A0 PO / PO Exit
PROD Si PO / PO Exit
A0 ES2
PROD TI
Silicon Enabling
& Execution MFG
0.0 | RTL 0.5 | RTL 0.8 | 1.0
A0 TI
PROD Si QS
PROD Si PRQ
RTL TR
Tape-in
PRQ
PSS
SOC VAL
0.0 | 0.3 |  | VAL 0.5 | VAL 0.8 | VAL 1.0
SOC VAL TR
A0 ES1
SOC RTL 0.3
Pre-Si &
Post-Si Sys Val
 | 0p3 | 0p5 | 0p8 | 1p0
IP FW/DRV
Execution Commit (EC)
Pre-Si Sys Val TR | 0.0 |  | Sys Val 0.5 | Sys Val 0.8 | 1.0
 |  | 0.3 |  |  | 
SiE MFG TR | SiE MFG 0.0 | SiE MFG 0.5 | SiE 0.8 | SiE 1.0
A0 PO Read. | PPOE | Pre-PROD Step | Validation |  | PROD Step Validation
 |  |  | PO Readiness |  | 
A0 Si Read. | PPOE | A0 Execution | PROD Step CE | PROD Step Execution
Platform PO Exit
UPLC 3.0.0
IP Design - HIP
IP Design - SIP
PAS
IP Arch Complete | IP Arch Final
PSS 0.0 | PSS 0.3 | PSS 0.5 | PSS 0.8 | PSS 1.0 | PSS 1.1
PSS TR
PAS 0.5 | PAS 0.8 | PAS 1.0
Product/Die Overview HAS
All Other HAS
HAS 0.2 | HAS 0.5 | HAS 0.8 | SOC HAS 1.0 | SOC HAS 1.1
Product
Planning
Product Concept
(PC)
Product Kickoff (PK)
FW/SW 0.0 | FW/SW 0.1 | FW/SW 0.3 | FW/SW 0.5 | FW/SW 0.8 | FW/SW 1.0 | FW/SW 1.1
FW/SW**
Beta
Alpha
Pre-Alpha
PV
IC | IE | EV1 | EV2 | UV1 | UV2 | eFV/FV
IC | IE | EV1 | UV /EV2 | UV | FV
HAS 0.5 | HAS 0.8 | HAS 1.0 | SOC HAS 1.1
VSV
VS0
VS1
Non-Governed Milestones
Governed Milestones