## Slide 1
Publications Chairs
Jungwoo Joh, Texas Instruments
Geert Eneman, imec
June 25, 2024

## Slide 2: Outline
Publication timeline
Mira for IEDM 2024
Reminder for paper selection meeting

## Slide 3: Timeline (2024)
April: Setup IEDM 2024 Mira conference submission page and add all SCCs as track chairs
April 22nd (or earlier): letter confirmation of all SCM (ASAP for visa issue)
May 21st: Website open for abstract submission
End of June: Mira training for SCCs – Review
July 11th: Abstract submission closes (Thursday)
July 14th: All reviewers added in Mira by SCC & Gail to send SCM instruction email
Final list of all SCMs to PCs  checks
Follow-up with Invited & FS
July 24th: final decision on paper allocations (Wednesday)
July 29th: Send out abstracts to all, SCMs etc. (Monday)
August 19th: Late News Deadline
August 20th : SCM finalized reviews (Tuesday)
August 25th/26th: Planning Meeting / Put together the program / Technical program meeting
~3 weeks for paper review

## Slide 4: Mira Account Setup
Each SCC need to upload SCM list to Mira for 2024
  CEM to send email to all committee members notifying them to login and authenticate account. This is necessary due to 2 factor authentication requirements and not being able to use email address as login
  SCM to respond via email to CEM confirming they have created account. CEM to “upgrade” member to Reviewer (same process applies to SCCs, CEM to upgrade them to SCC in Mira)

## Slide 5: Paper Selection Meeting (Aug 26)
Current plan, Aug 26 meeting:
Legacy Excel spreadsheet will NOT be used
Assure Accept/Reject decisions will be input directly in Mira live during meeting – (a backup Excel spreadsheet for record)
Time management is very important
  Quality review
  Session creations
  Time management
  Finish all works before 4pm of Aug. 26
  SC members should not make any plan to leave before 6pm