## BWF decision Critica path
Q1'21 | Q2'21 | Q3'21 | Q4'21
· 26.5p L/S structure reticle TO · Paper process file release for BWF PF | · 26.5p CMOS/IC test structure TO · 1.5b/c: Engineered nucleation distribution for RD & SD composition for RWB @33.5p · BiSM: Engineered SD composition for RWB @33.5p | · BWF spider TO · 26.5p array L1D no show stopper · 1.5b/c: 30% window budget compaction demonstrated · Preliminary si process file for BWF PF | · BWF Spider Block functional, Array MTS/DTS validated, · TC03 CMOS si meet MTS/DTS.
Q1'21 | Q2'21 | Q3'21 | Q4'21
1. 26.5p L/S structure reticle taped out (Max) | 1. 1st cut FP etch demo at BWF pitch, within 3 sigma of MTS. (Max, Frank) | 1. litho, PQ, seal/fill, clean, etch L1D no show stopper (Frank) 2. BWF spider TO (Sandeep, Khaled, Max) | 1. BWF Spider Block function (Max, Sanjay) 2. Array MTS/DTS validated, BWF spider golden silicon for array process file (Sanjay)
1. TCAD demo for functional dts to support 4kx4k and 2kx4k design (Baofu) | 1. silicon validation of MTS vs. DTS to support 26.5p SLC design (Erv, Kia) 2. 26.5p CMOS/IC test structure TO (Erv, Kia) | 1. ATF LV golden silicon fabout (Erv, Kia) | 1. HV X'tors validated (Erv, Kia) 2. golden silicon ready for compact model (Erv, Kia)
1. Experimental (Paper) Process file and design rule for core design pathfinding (DerChang) |  | 2. Speculative collateral for circuit performance (speed and energy) assessment (DerChang)
Circuit PF cont (Sandeep) | 1. Tile control circuit functional (SPICE, Sandeep) 2. paper estimate of die size meeting LRP goal (Eddie) | 1. EoQ Rev -2 Start (Sandeep) | 1. EoQ Rev -1 Start (Sandeep)
| 1. Understanding PM disturb and engineering nucleation distribution (Sanjay) 2. Understanding SD memory effect and engineering window (Fuga, Ananth) | 1. 30% window budget compaction thru sigma, drift, and cycling shift reduction (Sanjay) 2. 33.5p SD unipolar memory demonstrated (Max, Frank)
| 1 Understanding BiSM switching mechanism and engineering memory window (Fuga, Ananth) | 1. BiSM switching mechanism scalable (Fuga) 2. 33.5p SD Bipolar memory demonstrated (Max, Frank)
1. Die siz, energy on par with SXP (Mase)