## WW28-2020
# | Projects | Stage | Owner | Goal (Aim high) | Existing PF success criteria | Critical Path (Interim Milestone, as measured by)
P1242 (array pitch placeholder:26.5nm, aka 26.5p) | [5 empty] | Q3/2020 | Q4/2020 | 1H/2021 | 2H/2021
1 | New PM | 2 | Dan, Lu, Hemant | Eliminate C-cell, enable 1.5b/c | 33.5p results meet PrePOR criteria
2 | New SD | 2 | Fuga, Dany, Dan | Enable BiSM, 1.5b/c, no seasoning | 33.5p results meet PrePOR criteria
3 | New Electrode | 3 | Fuga, Dany, Kumar, Hemant, Anath | 60% I reset reduction | 33.5p results self consistent in DTS
4 | Ru Array Metal | 3 | Prashant, Max, Cathy | 30% conductivity improvement | silicon demo at L1E (WL only)
5 | Seal | 3 | Todd | 13nm Space enabling | Silicon demo at L1D
6 | Fill | 2 | litho TBD (spin on), CVD=Todd | 13nm Space enabling | passing L1D and 33.5p TD demo
7 | PQ vs. DSA | 2 | Kyuchul, Vivek, Todd (alt spacer) | <17nm space CDU, cost | Passing L1D, scalability @ cost demo
8 | Toppling Margin | 2 | Wets TBD | 13nm Space enabling | Passing L1D (no damage to sidewall)
9 | CUA and Design Rule | 3 | Prashant, Balaji, Khaled, Eddie | 26.5p enabling
10 | Interconnect scheme | 4 | Khaled and Eddie | 26.5p enabling
11 | Planar HV Scaling | 4 | Luo, Baofu | 26.5nm enabling
12 | Read/Write Energy | 3 | Sandeep, Balaji | 70% P1241 Read/write energy
13 | Modular Design | 2 | Eddie, Sandeep | Scaling model implemented @ BWF
14 | 2Kx4Kx4 tile | 3 | Sandeep, Luo, Khaled | Meeting 32GB LRP goal
Defintions
|  | 1 | Concept: Ideas with first principle / trust-worthy empirical
Strategic long range plan or simple napkin cartoon illustrations, passing first principle
|  | 2 | Early Research: Incumbent identified, competition surveyed, papers studied, landing zone emerging
Brainstorming connecting the ideas to landing and id the value and critical gaps
|  | 3 | Path Validation: to validate, quantify, justify for the value proposition and identify execution paths
Integrated scope validated by segment and value proposition justified.
|  | 4 | Module Definition: Critical logistics and infrastructures identified for intercept
technically integrated scope validate with acceptable cost assessment
|  | 5 | Exiting Path-finding: Spec definitions and risk assessment. One step prior to NTI/NPI
Silicon based scalability assessed, cross t dot i, final scrub before roadmap commitment
| Project score list |  | New module count | Complexity of module | Interaction vs. modularity

## WW29-2020
# | Projects | Stage | Owner | Goal (Aim high) | Existing PF success criteria | New module/count | Complexity of module | Interaction vs. modularity | Critical Path (Interim Milestone, as measured by)
P1242 (array pitch placeholder:26.5nm, aka 26.5p) | [8 empty] | Q3/2020 | Q4/2020 | 1H/2021 | 2H/2021
Must Graduate
1 | 1st/2nd Cut and Toppling | 2 | Wets TBD | 13nm Space enabling | Passing L1D (no damage to sidewall) | Hardmask, PVD, 1st Cut, 2nd Cut | High | Stack, liner/seal
2 | Liner/Seal | 3 | Todd | 13nm Space enabling | Silicon demo at L1D | ALD | Med | PM CMP, 2nd cut and Disturb
3 | CUA and Design Rule | 3 | Prashant, Balaji, Khaled, Eddie | 26.5p enabling | No show stopper assessed w/ silicon | d2d, d2w, c2g, p2p, end cap, contact | Low | FE integrity
4 | Interconnect scheme | 4 | Khaled and Eddie | 26.5p enabling | Med Risk of metallization on paper | M2/M3 scaling or adding M5 | Low | Displacement energy, TDDB
5 | Planar HV Scaling | 4 | Luo, Baofu | 26.5nm enabling | No show stopper assessed w/ silicon | HVT scaling and consolidation | Low | FE integrity and CMOS Rel
6 | Read/Write Energy | 3 | Sandeep, Balaji | 70% P1241 Read/write energy |  | tbd | ? | ?
7 | Critical Layer overlap | 2 | Frank | 26.5p enabling | < 4nm | tbd | tbd
Contingency
1 | New Electrode | 3 | Fuga, Dany, Kumar, Hemant, Anath | 60% I reset reduction | 33.5p results self consistent in DTS | PVD, 1st Cut and 2nd Cut | Low: Known material and AR | reset current vs. endurance
2 | New PM | 2 | Dan, Lu, Hemant | Eliminate C-cell, enable 1.5b/c | 33.5p results meet PrePOR criteria | PVD, 1st Cut and 2nd Cut | High: Long cycle of learning
3 | New SD | 2 | Fuga, Dany, Dan | Enable BiSM, 1.5b/c, no seasoning | 33.5p results meet PrePOR criteria | PVD, 1st Cut and 2nd Cut | BiSM-med, 1.5b/c-High, very Hi-seasoning
4 | Fill | 2 | litho TBD (spin on), CVD=Todd | 13nm Space enabling | passing L1D and 33.5p TD demo | new spin on | High: New proprietary chemical | CMP, seal, 2nd Cut and Disturb
5 | Array metal condutivity | 3 | Prashant, Max, Cathy | 30% conductivity improvement | silicon demo at L1E (WL only) | PVD, 1st Cut and 2nd Cut | Low: known from IMEC and CR
6 | PQ vs. DSA | 2 | Kyuchul, Vivek, Todd (alt spacer) | <17nm space CDU, cost | Passing L1D, scalability @ cost demo | Litho | High: brand new litho
7 | Modular Design | 2 | Eddie, Sandeep | Scaling model implemented @ BWF | 5% (?) footprint reduction | W/L constraint | Med:
8 | 2Kx4Kx4 tile | 3 | Sandeep, Luo, Khaled | Meeting 32GB LRP goal |  | new Array topo/circuit and CMOS | Very High
Defintions
|  | 1 | Concept: Ideas with first principle / trust-worthy empirical
Strategic long range plan or simple napkin cartoon illustrations, passing first principle
|  | 2 | Early Research: Incumbent identified, competition surveyed, papers studied, landing zone emerging
Brainstorming connecting the ideas to landing and id the value and critical gaps
|  | 3 | Path Validation: to validate, quantify, justify for the value proposition and identify execution paths
Integrated scope validated by segment and value proposition justified.
|  | 4 | Module Definition: Critical logistics and infrastructures identified for intercept
technically integrated scope validate with acceptable cost assessment
|  | 5 | Exiting Path-finding: Spec definitions and risk assessment. One step prior to NTI/NPI
Silicon based scalability assessed, cross t dot i, final scrub before roadmap commitment
| Project score list |  | New module count | Complexity of module | Interaction vs. modularity

## SLC vs. 1.5bpc vs. BiSM
# | P1242 Candidates | SLC | 1.5b/c | BiSM
| Pitch [nm] | 26.5 | 33.5 | 28
1 | 1st/2nd Cut and Toppling | 13nm Space enabling | New SD, Similar AR to P1241 | New SD, AR similar to P1241
2 | Liner/Seal | 13nm Space enabling
3 | Fill | 13nm Space enabling
4 | CUA and Design Rule | 26.5p enabling |  | 28p enabling
5 | Interconnect scheme | 26.5p enabling |  | 28p enabling
6 | Planar HV Scaling | 26.5nm enabling |  | 28p enabling
7 | Read/Write Energy | 70% P1241 Read/write energy |  | 70% P1241 read/write energy
8 | New SD |  | RWB, Sigma @ 80mV | RWB
Not Applicable