## Q1
Program/Scope |  |  |  |  | 5: Concept | 4: Early Research | 3: Path-Finding | 2: Module Definition | 1: Exiting Path-finding
| Projects | Stage | Owners (Customer) | Vision, Value or Issues | Ideas with first principle / trust-worthy empirical | Incumbent identified, competition surveyed, papers studied, landing zone emerging | to validate ideas, identify execution paths and justify the value proposition | Critical logistics and infrastructures identified for intercept | Spec definitions and risk assessment. One step prior to NTI/NPI
P1242 (Gen+1) |  |  | (Max, Mase)
1 | PQ vs. DSA | 2 | Kyuchul, Vivek | Cost |  |  |  | Preliminary silicon and Risk Assessment for project plan development
2 | PM and memory effects | 3 | Kumar, Lu | RWB, Set Speed, Disturb |  |  | Statergy development (TD, RWB, Speed)
3 | Seal/Fill (and TD) | 4 | Todd (Film) | Step Coverage & Thermal Disturb |  |  | to be started
4 | Decoder (CUA) | 3 | Sandeep, Saad, Divesh | die size and BW (tile size) |  |  | S37: design change list
5 | Recess Channel Transistor (CUA contingency) | 4 | Luo, Prashant
6 | BiSM Roadmap Intercept (TD contingency) | 2 | Fuga, Mase, Max
7 | 3DIC Roadmap Intercept (CUA contingency) | 4 | Sandeep, Shafqat, Prashant
8 | 1.5b/c Roadmap Intercept (Cost contingency) | 4 | Sanjay, Mase
BiSM |  |  | (DerChang)
1 | New BiSM material and co-sputter | 3 | Dan, Fuga | Prep for BiSM materail PF at F11x
2 | RWB algorithm | 2 | Qawi, Dany | Latency and energy |  |  | In-die Pre-Read for Normal Write RWB gap vs. si policy simplification | system pre-read; Bantu t-spec and flow development
3 | RWB, Scaling, Reliability confidence | 2 | Fuga, Dany | Scalability |  |  | model bulding with 5nm 2nd cut reduction assessment
4 | 3T Mux | 2 | Balaji, Eddie | Energy at >10% density impact |  |  | Assess die size and routing impact on a weak grounding leg for each row/col; Assess component cost vs. ALF32.
5 | BiSM device model (includeing Mass transport) | 2 | Ananth, Fuga | Enabling |  |  |  | mass transport model development
6 | BiSM DFT of Se glass | 3 | Ananth, Fuga | Enabling
Architecture |  |  | (Max, Mase)
1 | Float deselect scheme | 4 | Mase, Balaji | Energy, decoder footprint | eliminate deselect toggle energy
2 | 3D Tier architecture | 5 | Werner | Density | 3D decoding
Transistor and Interconnect (Periphery) |  |  | (Shafqat, DerChang)
1 | Long term 3DIC Strategy | 4 | Sandeep, Khaled, Prashant | component scaling path | kickoff WW45 | 3DXP component modularity analysis for disaggregation
2 | Monolithic 3D (ADM, PolySi, LTSi) | 4 | Luo, Prashant | HV scaling |  | benchmark per P1240.0 e-spec and r-spec
3 | Trenched FINFET for decoder | 4 | Werner, Luo, Prashant | HV scaling |  | Structure building and Performance assessment
4 | Stacked 3D | 5 | Prashant, Shafqat | component scaling path | technology survey
5 | Wide EG channel (GaN, TMDC) | 5 | Prashant, Jack | HV scaling | technology survey
6 | P1222.6 ADM device TCAD model | 2 | Ananth, Luo | Enabling |  |  |  | Porting ADM model
Selector |  |  | (DerChang)
1 | ADM Diode | 5 | Charles | 3DXP energy and BW density | Empirical data review, building first principle model and process flow
2 | Oxide Selector | 3 | Noriyuki, Abhishek S., Devin, Fuga | New SD and BiSM (to reduce cycling evolution) |  |  | Establishing L0/L1E flow by validating As doped SiO2 matching iedm paper
3 | Doped ZnO | 4 | Ilya, Ashishi | New SD (no snapback) |  | SRC funding with UTA.
4 | No seasoning stack | 5 | ???
PM |  |  | (DerChang)
1 | High speed PCM (doped 212) | 3 | Ilya | DRAM replacement |  |  | CR tool dep@temp upgrading
2 | Low Drift PM for C-cell bias elimination | 5 | Dan | C-cell bias elimination
Diode select cross Point Array |  |  | (DerChang)
1 | Low Program current PM (iPCM) | 4 | Charles K., Kaan O., Ilya | PM replacement |  | Paper research and external collab
2 | ThinFilm Diode (ANM Schottky) | 4 | Charles, Prashant | SD replacement |  | CR learning and early stage of exp.
3 | Array Architecture | 4 | Prashant, Charles
Test Vehicles |  |  | (Fuga)
1 | MID (CMOST included) | 1 | Abhishek, Hank | Enabling -- L1E for thin film memory and switches
2 | L2 Vehicle for model building | 3 | Fuga, Mase | Enabling -- L2 for memory cell pathfinding |  |  | single cell and mini array for silicon based validation and model development
P1241 (G+1) |  |  | (Darren, Sanjay, Seshu)
1 | PM & Integrity for RWB/Speed | 2 | Kumar, Fey, Lu | RWB, Set Speed |  |  |  | Id serval candisates passing L0. Working toward L1E screening.
2 | New SD for memory effects | 3 | Dan, Fey, Lu | RWB |  |  | SAG with In doping ID'd.
3 | P1241 Mechanical model | 3 | Renata, Dan | Enabling
4 | 1.5 b/c array/test enablement | 4 | Hemant, Saad, Fuga | Density |  | scope assessment, Algo analysis, attributes for landing
5 | High Thruput Seasoning | 5 | Raghu, Chris | Sort cost | in-die mini probe pad for wafer level seasoning
6 | Tile Knock out elimination | 3 | Max to designate (array & yield)
1 | MBA | 5 | Mase | BW density
2 | 3D Deck architecture with Deck Select | 5 | Max | Density in 3D decoding | 3D decoding with deck architecture