## WW27-2020
Scope | Projects | Stage | Owner | Goal | Critical Path/ Interim Milestone, as measured by)
P1242 |  |  |  |  | Q3/2020 | Q4/2020 | 1H/2021 | 2H/2021
1 | New PM (set speed vs. window, tempco, drift) | 2 | Dan, Lu
2 | New SD (leakage, drift, tempco, memory effects) | 2 | Fuga, Dany
3 | Cell Stack Architecture (I-V) | 3 | Fuga, Dany, Kumar, Hemant | Energy, Disturb
4 | Ru Array Metal | 4 | Prashant, Max, Cathy
5 | Seal | 2 | Todd
6 | Fill | 2 | Todd
7 | PQ vs. DSA | 2 | Kyuchul, Vivek
8 | CUA and Design Rule | 3 | Prashant, Balaji, Khaled, Eddie
9 | Interconnect Scheme | 4 | Khaled and Eddie
10 | Planar HV Scaling | 4 | Luo, Baofu
11 | Read/Write Energy | 3 | Sandeep, Balaji | HV scaling, Interconnect, smaller tile footprint
12 | Modular Design | 2 | Eddie, Sandeep
13 | 2Kx4Kx4 tile | 3 | Sandeep, Luo, Khaled
14
15
16
17
BiSM
1 | Algorithm | 5 | Dany | Latency and energy
2 | RWB, Scaling, Reliability confidence | 5 | Fuga, Dany | Scalability
3 | New BiSM material and co-sputter | 3 | Fuga, Dan | Prep for BiSM material PF at F11x
4 | MLC | 2 | Fuga, Dany | Parallelism, Energy
1.5b/c
1 | Algorithm | 3 | Hemant, Sanjay
2 | RWB, Scaling, Reliability confidence | 4 | Hemant, Sanjay
3 | New SD material | 3 | Fuga
Architecture (Technology and Design)
1 | CUA: CMOS DR vs. Array Pitch | 3 | Sandeep, Khaled, Eddie
2 | Float deselect scheme | 2 | Mase, Balaji | Energy, decoder footprint
3 | 3DIC | 2 | Sandeep, Prashant, DerChang
4 | Pillar Select 3D architecture | 1 | Khaled, Prashant, Max | Density
5 | Deck Select 3D architecture | 1 | Khaled, Prashant, Max | Density
6 | MBA (MultiBitAccess of a tile) | 1 | Mase, DerChang | BW
Transistor and Interconnect
1 | Low resistivity array metal | 3 | Prashant, Max | Energy
2 | Long term 3DIC Strategy | 2 | Sandeep, Khaled, Prashant, Eddie | Function/Technology disaggregation for scaling velocity
3 | Monolithic 3D (ADM, PolySi, LTSi) | 2 | Luo, Prashant | HV scaling
4 | RCT and variants for decoder | 2 | Luo, Prashant | HV scaling
5 | Wide EG channel (ADM, GaN, TMDC) | 1 | Prashant | HV scaling
Selector
1 | Oxide Selector | 2 | Noriyuki, Abhishek S., Devin @ CR, Fuga | New SD and BiSM (to reduce cycling evolution)
2 | ADM Diode | 1 | Charles @ CR | 3DXP energy and BW density
3 | No seasoning stack | 1 | Max
4 | Diode Select cross point array | 1 | DerChang | 3DXP energy and BW density
PM and Interface
1 | Ga displacement (PM2A3) | 3 | Kumar, Dan
2 | Ge doped GaSb | 3 | Kumar, Dan
3 | PM2A3 set speed improvement | 3 | Lu, Dan
4 | Low drift PM for C-cell elimination | 1 | Dan | C-cell bias elimination
5 | iPCM | 1 | Charles, Kaan @ CR, Prashant, Kumar | Energy

## WW31-2020
Scope | Projects | Stage | Owner | Vision, Value or status
P1242 26.5nm Full Stack SLC |  |  |  | 3DXP G+2
1 | Hard Mask | 3
2 | 1st Cut | 3
3 | 2nd Cut | 3
4 | Liner | 3
5 | Seal | 3 |  | Energy, Disturb
6 | 193 overlay | 2
7 | HVT STI L/S | 2
8 | HVT well Implant | 2
9 | HVY Poly Patterning | 1 |  | C-cell bias elimination
10 | HVY Poly Patterning | 1 |  | C-cell bias elimination
11 | Dummy Poly | 1 |  | C-cell bias elimination
12 | HVT Tip | 1 |  | C-cell bias elimination
13 | HVN Halo | 1 |  | C-cell bias elimination
14 | Contact | 1 |  | C-cell bias elimination
15 | Interconnect | 1 |  | C-cell bias elimination
16 | HVT consolidation | 1 |  | C-cell bias elimination
17 | Energy Reduction | 1 |  | C-cell bias elimination
18 | Modular Design | 1 |  | C-cell bias elimination
19 | HVY Poly Patterning | 1 |  | C-cell bias elimination
Full Stack SXP |  |  |  | 3DXP G+2
1 | PM and memory effects | 3 | Dan, Lu, (Fuga and Dany from SD)
2 | CUA | 3 | Prashant, Sandeep, Balaji, Luo, Khaled, Eddie
3 | Read/Write Energy | 3 | Sandeep, Balaji
4 | Set Speed improvement | 3 | Lu, Dan
5 | Electrode, PM Interface Hot spot | 3 | Lu, Ananth, Fuga, Kumar | Energy, Disturb
6 | Seal/Fill | 2 | Todd, (Frank's designate)
7 | PQ vs. DSA | 2 | Kyuchul, Vivek
8 | 1.5b/c Roadmap Intercept | 2 | Sanjay, Hemant
9 | Low Drift PM | 1 | Dan | C-cell bias elimination
BiSM
1 | Algorithm | 5 | Dany | Latency and energy
2 | RWB, Scaling, Reliability confidence | 5 | Fuga, Dany | Scalability
3 | New BiSM material and co-sputter | 3 | Fuga, Dan | Prep for BiSM material PF at F11x
4 | MLC | 2 | Fuga, Dany | Parallelism, Energy
Architecture (Technology and Design)
1 | CUA: CMOS DR vs. Array Pitch | 3 | Sandeep, Khaled, Eddie
2 | Float deselect scheme | 2 | Mase, Balaji | Energy, decoder footprint
3 | 3DIC | 2 | Sandeep, Prashant, DerChang
4 | Pillar Select 3D architecture | 1 | Khaled, Prashant, Max | Density
5 | Deck Select 3D architecture | 1 | Khaled, Prashant, Max | Density
6 | MBA (MultiBitAccess of a tile) | 1 | Mase, DerChang | BW
Transistor and Interconnect
1 | Low resistivity array metal | 3 | Prashant, Max | Energy
2 | Long term 3DIC Strategy | 2 | Sandeep, Khaled, Prashant, Eddie | Function/Technology disaggregation for scaling velocity
3 | Monolithic 3D (ADM, PolySi, LTSi) | 2 | Luo, Prashant | HV scaling
4 | RCT and variants for decoder | 2 | Luo, Prashant | HV scaling
5 | Wide EG channel (ADM, GaN, TMDC) | 1 | Prashant | HV scaling
Selector
1 | Oxide Selector | 2 | Noriyuki, Abhishek S., Devin @ CR, Fuga | New SD and BiSM (to reduce cycling evolution)
2 | ADM Diode | 1 | Charles @ CR | 3DXP energy and BW density
3 | No seasoning stack | 1 | Max
4 | Diode Select cross point array | 1 | DerChang | 3DXP energy and BW density
PM and Interface
1 | Ga displacement (PM2A3) | 3 | Kumar, Dan
2 | Ge doped GaSb | 3 | Kumar, Dan
3 | PM2A3 set speed improvement | 3 | Lu, Dan
4 | Low drift PM for C-cell elimination | 1 | Dan | C-cell bias elimination
5 | iPCM | 1 | Charles, Kaan @ CR, Prashant, Kumar | Energy

## WW35-2020
Scope | Projects | Stage | Owner | Vision, Value or status
P1250 26.5nm Full Stack SLC
1 | Critical Layer Overlay | 5 | Frank
2 | CUA and Design Rule | 4 | Luo, Balaji, Khaled, Eddie |  | Interconnect scheme
3 | Interconnect scheme | 4 | Khaled, Eddie, Sandeep, Erv |  | Planar HV Scaling
4 | Planar HV Scaling | 4 | Luo, Baofu |  | Read/Write Energy
5 | 1st/2nd Cut and Toppling | 3 | Dan, Cathy
6 | Liner/Seal | 3 | Todd |  | CUA and Design Rule
7 | Read/Write Energy | 3 | Sandeep, Erv
8 | 2Kx4Kx4 tile | 3 | Sandeep
P1250 Contingency
1 | Electrode for 50% Iprogram scaling | 3 | Fuga, Kumar, Hemant
2 | Array Metal 30% r reduction | 3 | Prashant, Max, Cathy
3 | Modular Design | 3 | Balaji, Khaled, Alex
4 | New PM | 2 | Dan, Lu
5 | New SD | 2 | Fuga, Dany, Dan
6 | Fill | 2 | Todd
7 | PQ vs. DSA | 2 | Kyuchul, Vivek
Full Stack SXP |  |  |  | 3DXP G+2
1 | PM and memory effects | 3 | Dan, Lu, (Fuga and Dany from SD)
2 | CUA scalability | 3 | Prashant, Sandeep, Balaji, Luo, Khaled, Eddie
3 | Read/Write Energy | 3 | Sandeep, Balaji
4 | Set Speed vs. Write Disturb scaling | 3 | Lu, Dan
5 | Program Current Reduction | 3 | Lu, Ananth, Fuga, Kumar | Energy, Disturb
6 | 1.5b/c | 3 | Sanjay, Hemant, Sandeep
7 | Seal/Fill scaling path | 2 | Todd, (Frank's designate)
8 | Sub 26.5nm litho | 2 | Kyuchul, Vivek
BiSM
1 | Algorithm | 5 | Dany, Prashant D. | Latency and energy
2 | RWB, Scaling, Reliability confidence | 5 | Fuga, Dany | Scalability
3 | Die Size & Energy | 4 | Balaji | Prep for BiSM material PF at F11x
4 | New BiSM material and co-sputter | 3 | Fuga | Parallelism, Energy
5 | MLC | 2 | Fuga, Dany, Prashan D. | Parallelism, Energy
Architecture (Technology and Design)
1 | CUA: CMOS DR vs. Array Pitch | 3 | Sandeep, Khaled, Eddie
2 | Float deselect scheme | 2 | Mase, Balaji | Energy, decoder footprint
3 | 3DIC (monolithic & heterostacking) | 2 | Sandeep, Prashant, DerChang
4 | NAND-Like 3DXP | 1 | Khaled, Werner, Max, Erv
5 | Pillar Select 3D architecture | 1 | Prashant, Max, DerChang | Density
6 | Deck Select 3D architecture | 1 | Prashant, Max, DerChang | Density
7 | MBA (MultiBitAccess of a tile) | 1 | Mase, DerChang | BW
Transistor and Interconnect
1 | Low resistivity array metal | 3 | Prashant, Max | Energy
2 | Long term 3DIC Strategy | 2 | Sandeep, Khaled, Prashant, Eddie | Function/Technology disaggregation for scaling velocity
3 | Monolithic 3D (ADM, PolySi, LTSi) | 2 | Luo, Prashant | HV scaling
4 | X'tor Augmentation | 2 | Luo, Prashant | HV scaling
5 | Wide EG channel (ADM, GaN, TMDC) | 1 | Prashant | HV scaling
Selector
1 | Oxide Selector | 2 | Noriyuki, Abhishek S., Devin @ CR, Fuga | New SD and BiSM (to reduce cycling evolution)
2 | ADM Diode | 1 | Charles @ CR | 3DXP energy and BW density
3 | No seasoning stack | 1 | Fuga, Max
4 | Diode Select cross point array | 1 | DerChang | 3DXP energy and BW density
PM and Interface
1 | Ga displacement (PM2A3) | 3 | Kumar, Dan
2 | Ge doped GaSb | 3 | Kumar, Dan
3 | PM2A3 set speed improvement | 3 | Lu, Dan
4 | Low drift PM for C-cell elimination | 1 | Dan, Dany | C-cell bias elimination
5 | iPCM | 1 | Charles, Kaan @ CR, DerChang, Kumar | Energy

## prep for P1250
Scope | Projects | Stage | Owner (Customer) | Vision, Value or status | # | Projects | Existing PF success criteria | New module/count | Complexity of module | Interaction vs. modularity
Transistor and Interconnect |  |  | (DerChang) |  | P1242 (array pitch placeholder:26.5nm, aka 26.5p)
1 | Low resistivity array metal | 3 | Prashant | Energy | Must Graduate
2 | Long term 3DIC Strategy | 2 | Sandeep, Khaled, Prashant, Eddie | Function/Technology disaggregation for scaling velocity | 1 | Critical Layer Overlay | Roadmap to <4nm validated | None, new scribe structure | Med | Stack, liner/seal/GF/CMP
3 | Monolithic 3D (ADM, PolySi, LTSi) | 2 | Luo, Prashant | HV scaling | 2 | 1st/2nd Cut and Toppling | Passing L1D (no damage to sidewall) | Hardmask, PVD, 1st Cut, 2nd Cut | High | Stack, liner/seal/GF/CMP
4 | Trenched FINFET for decoder | 2 | Luo, Prashant | HV scaling | 3 | Liner/Seal | Silicon demo at L1D | ALD | High | PM CMP, 2nd cut and Disturb
5 | Wide EG channel (ADM, GaN, TMDC) | 1 | Prashant | HV scaling | 4 | CUA and Design Rule | No showstopper assessed w/ silicon | d2d, d2w, c2g, p2p, end cap, contact | Low | FE integrity
Selector |  |  | (DerChang) |  | 5 | Interconnect scheme | Med Risk of metallization on paper | M2/M3 scaling or adding M5 | Low | Displacement energy, TDDB
1 | ADM Diode | 1 | Charles @ CR | 3DXP energy and BW density | 6 | Planar HV Scaling | No showstopper assessed w/ silicon | HVT scaling and consolidation | Low | FE integrity and CMOS Rel
2 | Oxide Selector | 2 | Noriyuki, Abhishek S., Devin, Fuga | New SD and BiSM (to reduce cycling evolution) | 7 | Read/Write Energy |  | tbd | ? | ?
3 | No seasoning stack | 1 | ??? |  | Contingency
4 | Diode Select cross point array | 1 | Charles @ CR | 3DXP energy and BW density | 1 | New Electrode | 33.5p results self consistent in DTS | PVD, 1st Cut and 2nd Cut | Low: Known material and AR | reset current vs. endurance
PM and Interface |  |  | (DerChang) |  | 2 | New PM | 33.5p results meet PrePOR criteria | PVD, 1st Cut and 2nd Cut | High: Long cycle of learning
1 | Ga displacement (PM2A3) | 3 | Kumar, Dan |  | 3 | New SD | 33.5p results meet PrePOR criteria | PVD, 1st Cut and 2nd Cut | BiSM-med, 1.5b/c-High, very Hi-seasoning
2 | Ge doped GaSb | 3 | Kumar, Dan |  | 4 | Fill | passing L1D and 33.5p TD demo | ALD | High: New proprietary chemical | CMP, 2nd Cut and Disturb
3 | PM2A3 Set Speed improvement | 3 | Lu, Dan |  | 5 | Array Metal Conductivity | +30% silicon demo at L1E (WL only) | PVD, 1st Cut and 2nd Cut | Low: known from IMEC and CR
4 | Low Drift PM for C-cell elimination | 1 | Dan | C-cell bias elimination | 6 | PQ vs. DSA | Passing L1D, scalability @ cost demo | Litho | High: brand new litho
5 | Hot spot (Interface engineering) | 3 | Lu, Ananth, Fuga | Energy, Disturb | 7 | Modular Design | 5% (?) footprint reduction | W/L constraint | Med:
6 | iPCM | 1 | Charles, Kaan @ CR, Prashant, Kumar | Energy | 8 | 2Kx4Kx4 tile |  | new Array topo/circuit and CMOS | Very High

## scratch pad
Scope | Projects | Stage | Owner | Vision, Value or status
Architecture (Technology and Design)
1 | CUA: CMOS DR vs. Array Pitch | 3 | Sandeep, Khaled, Eddie
2 | Float deselect scheme | 2 | Mase, Balaji | Energy, decoder footprint
3 | 3DIC (monolithic & heterostacking) | 2 | Sandeep, Prashant, DerChang
4 | NAND-Like 3DXP | 1 | Khaled, Werner, Max, Erv
5 | Pillar Select 3D architecture | 1 | Prashant, Max, DerChang | Density
6 | Deck Select 3D architecture | 1 | Prashant, Max, DerChang | Density
7 | MBA (MultiBitAccess of a tile) | 1 | Mase, DerChang | BW
Transistor and Interconnect
1 | Low resistivity array metal | 3 | Prashant, Max | Energy
2 | Long term 3DIC Strategy | 2 | Sandeep, Khaled, Prashant, Eddie | Function/Technology disaggregation for scaling velocity
3 | Monolithic 3D (ADM, PolySi, LTSi) | 2 | Luo, Prashant | HV scaling
4 | X'tor Augmentation | 2 | Luo, Prashant | HV scaling
5 | Wide EG channel (ADM, GaN, TMDC) | 1 | Prashant | HV scaling
Selector
1 | Oxide Selector | 2 | Noriyuki, Abhishek S., Devin @ CR, Fuga | New SD and BiSM (to reduce cycling evolution)
2 | ADM Diode | 1 | Charles @ CR | 3DXP energy and BW density
3 | No seasoning stack | 1 | Fuga, Max
4 | Diode Select cross point array | 1 | DerChang | 3DXP energy and BW density
PM and Interface
1 | Ga displacement (PM2A3) | 3 | Kumar, Dan
2 | Ge doped GaSb | 3 | Kumar, Dan
3 | PM2A3 set speed improvement | 3 | Lu, Dan
4 | Low drift PM for C-cell elimination | 1 | Dan, Dany | C-cell bias elimination
5 | iPCM | 1 | Charles, Kaan @ CR, DerChang, Kumar | Energy