## ATF CMOS WW49
Metric | Commit | WW47 | WW48 | WW49 | Issue/Item-->Next Step ETA | Trend
% R90.08 Yield on target silicon (Lot Average) | ≥30% Yield | 32.1% | 17.6% |  | W POL Skew Lot yields 26.1%.
% P90.08 inner yield (no Region E die) |  |  | 21.6%
% P90.08 outer yield (Region E die only) |  |  | 4.3%
% R91 Yield on target silicon (Lot Average) |  | 4.5% | 2.6% |  | All 3 lots showing Zero yields on early process order wafers at VIA. L1 TF in progress
# of Wafers Reporting Yield |  | 18 | 120 | 0 | No wafers tested WW49
Best Wafer (% Yield) | >40% | 47.99% | 52.68% |  | Wafer was part of W POL Skew, 40s Buff Split
Segmentation of residual gaps (target yield %) | segmentation to >30% yield | 25% | 25% | 25% | Change (reduction) from previous week is because we have new monitors (in debug) suggesting that there maybe additional modes in addition to the current M1-M1 short resulting in incorrect the output of the complex gate. Better clarity next week. As an update, we have observed set fails having a similar M1-M1 short at the input.
Process/Design Fix for Residual Gaps (% yield) | Solution ID to > 25% yield | 25% | 25% | 25% | WW44
High Risk for DBR | 0 | 2 | 2 | 2 | DV has flagged two items in I/O path
High Risk for 1st silicon | 0 | 4 | 4 | 4 | ASML PLY timeline is long pole for 1st silicon
# of issues: DTS Time 0 | 80% Compliance to DTS | 80% | 80% | 80% | Waiting for Rev91 volume data to make a change in this - WW45
# of issues: DTS Reliability | Piece-wise fixes demonstrated | 80% | 80% | 80% | R91 improved VBD as expected, other mechanisms WIP; Rev91 wafers shipped to Rel and expect data in WW46
# of DTS Issues Segmented to Process | 90% of known issues | 80% | 80% | 80% | Waiting for Rev91 volume data to make a change in this - WW45
# of architectural issues | Piece-wise fixes demonstrated | 2 | 2 | 2 | WCMP residue on R91 still challenged
Showstoppers for ATF DBR | 0 | 0 | 0 | 0
High risk for ATF 1st Silicon | 0 | 2 | 2 | 2 | R91 solution space and MLR layer checkin
L4 on ALF CMOS P2/P3 Operations | 100% | 94% | 96%
L4 on ALF P1 Operations | 95% | 87% | 87%
Total Health% (% OOC, CLCR, TMM) | 95% | 90.93% | 92.29% | 90.95% | CLCR
EDI | 55 | 78.25 | 71.68 | 59.95 | PPLY elevated for 5oclock streaks
EDI | 55 | 259 | 112.3 | 103.9 | R91/2 driven by edge NVD voids (STI voids at edge) driving normalization
EDI | 55 | 125.3 | 196.4 | 168.4
MRCL of Technology Enabling Tools | 8 - meet schedule | 3 | 3 | 3 | TFE581, GTV592_3, RTI581 Qual Complete; ACE581/582 IQ behind schedule - In L2TF