## Slide 1: TMC for AI-PC
DerChang Kau and Team TMC, Aug. 16, '24
Terraced Memory Cube for small form factor IPM
Chiplet Cubing Innovation: Heterogenous 3D Integration
Low Power Wide-IO DDR: Mainstream DRAM Technology
800GB/s Mockup
Packaging Risk Assessment (Risk Management Pending)
“Drive-To” Schedule

## Slide 2: Why Terraced Memory Cube (TMC) to replace HBM 3D Packaging innovation remixed with mainstream DRAM technologies
TMC = Terraced Chiplet Cubing (TCC) + Low Power Wide-IO DDR DRAM (LPW)
TCC disaggregates vertical connectivity from active silicon in 3D stacking  smaller DRAM die size
LPDDR interface deploys simplest connectivity with minimum overhead  no base die required with energy optimized data transfer
Wide-IO improves parallelism of mainstream DRAM product (DDR or LPDDR)  4X LPDDR DQ width with Samsung’s lead product @ 2027;

## Slide 3: Terraced Memory Cube with TCC
TMC – terraced stacking of memory chips interconnected vertically using low cost TSV chips to widen data width in a Terraced Chiplet Cubing (TCC) construction.
A TMC example for 3D stack of Low-Power wide-IO, LPW, DRAM chips
16 tiers of 32Gb LPW
64GB TMC 2K DQ

## Slide 4: Intel-Samsung Meeting (Feb'24, Aug’24)

## Slide 5: Mockups of Memory Cube and Cost Breakdown
Input Information |  |  | 1b-process w/ 2GB-die |  |  |  |  |  |  | 
 |  |  | TMC – 4Hi 8GB |  | TMC – 8Hi 16GB |  | TMC – 12Hi 24GB |  | TMC – 16Hi 32GB | 
Memory | Memory component |  | LPWIO-1b-2GB/die |  |  |  |  |  |  | 
 | Size |  | 7 x 7 mm2 |  |  |  |  |  |  | 
 | Gross die/wafer |  | 1301 |  |  |  |  |  |  | 
 | Yield |  | 85.7% |  |  |  |  |  |  | 
 | Incoming wafer $$ |  | $ 3586 |  |  |  |  |  |  | 
 | $$ / die |  | $3.2 |  |  |  |  |  |  | 
TSV die | Scheme |  | 0P1M + TSV |  |  |  |  |  |  | 
 | Size |  | 2.05 x 5.2 mm2 |  | 2.4 x 5.2 mm2 |  | 3.83 x 5.2 mm2 2.04 x 5.2 mm2 |  | 5.26 x 5.2 mm2 2.4 x 5.2 mm2 | 
 | Gross die/wafer |  | 5867 |  | 5023 |  | 3161 5867 |  | 2313 5023 | 
 | Incoming wafer $$ |  | $ 450 |  |  |  |  |  |  | 
 | $$ / die |  | $ 0.077 |  | $ 0.090 |  | $ 0.143 (need 6ea) $ 0.077 (need 5ea) |  | $ 0.195 (need 8ea) $ 0.090 (need 7ea) | 
Assembly | Stack Height |  | 0 + 4 Hi |  | 0 + 8 Hi |  | 0 + 12 Hi |  | 0 + 16 Hi | 
 | Size |  | 9.9 x 7 mm2 |  | 11.7 x 7 mm2 |  | 12.8 x 7 mm2 |  | 14.9 x 7 mm2 | 
 | Gross die/wafer |  | 871 |  | 725 |  | 663 |  | 569 | 
 | Process cost/wafer |  | $ 2776.5 |  | $ 4393.3 |  | $ 6057.0 |  | $ 7367.9 | 
 | Process cost/unit |  | $ 3.27 |  | $ 6.45 |  | $ 10.13 |  | $ 15.22 | 
 | Yield |  | 97.6% |  | 94.0% |  | 90.2% |  | 85.1% | 
Memory Cube Module Cost |  |  | $ 16.6 |  | $ 34.4 |  | $ 54.1 |  | $ 78.0 | 
64GB Build Cost |  | # of modules | $ 133 | 8 | $ 138 | 4 | $ 163 | 3 (72GB) | $ 156 | 2

## Slide 6: 800GB/s modules and Benchmark
800GB/s Module | Package | Size [mm2] | Cost | Ch | GB | pJ/b | BW/mm | Node | Gb/Die | # Module | Height | # Die
TMC Mock-1 | TMC | 8x ( 9.9X7) | $133 | 32 | 64 | 1.9 | 14.3 | 1b | 16 | 8 | 4 | 32
TMC Mock-2 |  | 4X (11.7x7) | $138 |  |  |  | 28.6 |  |  | 4 | 8 | 
TMC Mock-3 |  | 2x (14.9x7) | $156 |  |  |  | 57.1 |  |  | 2 | 16 | 
TMC Mock-3
TMC Moc-2

## Slide 7: TMC Technical Risk Assessment
Memory die
TSV die
Voids in die gap filling
Irregular die-gap space makes EMC filling incomplete more easily to cause voids trapped.
Narrow vertical die-gap may block MUF filling capability or make NCF bleeding at die edge.
Wafer warpage
Thick EMC with high molding ratio may cause high warpage in final TMC wafer to fail final bumping process.
Risk definition
Low
Medium
Med-High
Showstopper
Concern with existing solutions.
Issue with confident mitigation plan.
Issue need several DOEs to explore solutions.
Foreseen issue w/o any potential solutions.
Difficulty for die height control
Stacking across 2 die with large z-height gap cause non-bond or crack. Z-height gap results from:
  TTV within wafer from thinning process
  Intrinsic co-planarity variation of μ-bump
  Cumulative gaps after multiple tiers stacking
…
Non-bonded
crack
THK variation
bump co-planarity
Die bond alignment
Die-bond accuracy will decrease while high-tier die use ground alignment marks due to large level difference of focal plane. As well, accuracy of overlay shift metrology is impacted.
TCB for thin die handling
Die stacking is processed with its final thickness of 40~50um, which is close to capability limitation of TCB process. The thin die is fragile to cause yield loss, especially under compression.
crack
thin die
void

## Slide 8
Risk Level | Risk Item | Fail Mode | Root Cause | Mitigation Plan
High | Difficulty for die height variation control | Non-bonded Die crack | Intra- or inter- wafer TTV by thinning Bump height variation Cumulative variation after multi-tier joint | Improve die THK control: Die binning by inline THK for CoW recon Enhance thinning performance by adding metal reflection layer(like Ta) before ILD Absorb variation impact: TSV cube stacking first High solder volume Mold+grind per 4-tier stack TCB for die-bond with new nozzle design NCF as gap control
Med ~ High | High IMC volume by process thermal budget | Solder brittle Higher R | High thermal budget due to long TCB process time. | Decrease thermal budget: Partial TCB + 1x MR + MUF FCB+MR with MUF TCB + MUF (backup) Full IMC joint (backup) Optimize IMC barrier metal/THK
Low | Stacked wafer warpage too high | Wafer reject by tools | High molding-to-Si ratio | Low modulus MUF material selection 2nd carrier for C4 bump + high modulus carrier selection
TMC Technical Risk Assessment Summary
Risk definition
Low
Concern with reference data
Medium
No data but experienced mitigation plan
High
No data but guessed mitigation plan
Showstopper
Foreseen issue w/o any potential solutions.
…
Non-bonded
crack
THK variation
bump co-planarity
IMC (Cu6Sn5 or Cu3Sn)
solder
* Underline : Primary solution to mitigate risk.

## Slide 9: TMC Mitigation Plan
Inline THK
inspection
Binning
48-51 um
51-54 um
54-57 um
…
…
(example)
Equally-distributed
die-attach
THK Bin
Mitigation Plan 1 – TSV cube first
Mitigation Plan 2 – THK binning

## Slide 10: TMC Mitigation Plan for TRA
Risk Level | Risk Item | Fail Mode | Root Cause | Mitigation Plan
Med-High | Difficulty for die height control | Non-bonded Die crack | Pre-tier is not flat due to cumulative variation from die THK or bump stand-off height. | 
Med | TCB for thin die handling | Die crack | Die THK is too thin, resulting in insufficient rigidity, then out of TCB handling capability. | 
Low | Die bond alignment inaccuracy | Die overlay shift | Different z-level between die placement and focal plane of alignment mark induces camera inaccuracy. | 
Med | Voids in die gap filling | Void-induced popcorn effect | Irregular die gap . Thin bump height because of total module height limitation. NCF or NCP bleeding blocks EMC fluidity. | 
Low | Stacked wafer warpage too high | Out of machine capability in: LIT or PLAT Transfer-mount | Molding ratio is too high with thick EMC height. | 

## Slide 11: TMC Development Timeline
Year |  | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  | 
Month |  | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
WW |  | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 |  |  |  |  |  |  |  | 
Key milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Supplier engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DCTV development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Memory mimic die |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | TSV die |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Interposer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Process BSL setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CIP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Reliability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Characterization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IPTV developing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Disclaimer:
  Schedule is estimated by engineering experience.
  Real timeline should be confirmed by OSAT after kick-off.
Jaguar Shores TO
Supplier scouting
TRA + design rule pre-define
Kick-off + SOW
JDA
** Assume JDA not gate engagement
TO
PDK v0.1
PDK v0.5
Layout design
Wafer fabrication
Layout design
Wafer fabrication
Layout design
Mask fabrication
Tooling preparation
Process development
PDK v0.01
CIP
E-test
RA
Memory design
Milestone Definition :
PDK v0.01 –
Pure paper-guess & simulation
PDK v0.1 –
Prototype build & process baseline
T0 yield > 50%
PDK v0.5 –
PDK v0.9 –
T0 yield > 90% + Pre-Qual pass
Full-Qual pass
PDK v1.0 –
Jaguar Shores EC??