## Sheet1
O: objective | Quarterly Objectives |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
Objective / Goal | Interim Milestone / Sub Goal | Customers | Sponsors | dependency | As Measured by | ECD | Owners | Status / Tracking | As Measured by | ECD | Owners | Status / Tracking | As Measured by | ECD | Owners | Status / Tracking
Material exploration L0/L1E scorecard achieves 2 weeks info turn | L1E Process flow, test flow and data analysis qualified for electrode, PM and SD scorecard assessment | MWG | Max, DerChang |  | · MID structural yield > 90% @L0P0 for all route flavors (Electrode/SD/PM) - 6 lots | WW20 | Fuga, Abhishek, Hank
[5 empty] | · MID functionality yield > 90% @L1P1 for all route flavors (E's/SD/BiSM/PM) and meeting DTS screening needs - 6 lots | WW27 | Fuga, Abhishek, Hank
L0 Process Flow, Metrology ready for electrode, PM, SD scorecard assessment
P1241 Definition Closure | W2W tcycle < 300ns | P1241 TD | Sanjay, Darren | Spider Structure yield and comp. match ATF41 | Spider 3.54 sigma tnuc < 160ns (near) | WW44 | Lu, Kumar, Hemant, Dan, John | · tnuc: Volume S26 data suggest D2 is the worst, 193ns vs. 80ns required. PM thickness DOE shows weak improvement (<15ns reduction at 0.5 R2) ==> project ATF tnuc ~355ns (~195ns gap) · Early segmentation suggest deck/polarity dependency more than segregation slope. Seeking for a integrated RA/RM (all owners) by the end of WW40. | Spider 3.54 sigma tnuc < 160ns | WW44 | Lu, Kumar, Hemant, Dan, John | · tnuc: Volume S26 data suggest D2 is the worst, 193ns vs. 80ns required. PM thickness DOE shows weak improvement (<15ns reduction at 0.5 R2) ==> project ATF tnuc ~355ns (~195ns gap) · Early segmentation suggest deck/polarity dependency more than segregation slope. Seeking for a integrated RA/RM (all owners) by the end of WW40. | Spider 3.54 sigma tnuc < 160ns (near) | WW44 | Lu, Kumar, Hemant, Dan, John | · tnuc: Volume S26 data suggest D2 is the worst, 193ns vs. 80ns required. PM thickness DOE shows weak improvement (<15ns reduction at 0.5 R2) ==> project ATF tnuc ~355ns (~195ns gap) · Early segmentation suggest deck/polarity dependency more than segregation slope. Seeking for a integrated RA/RM (all owners) by the end of WW40.
[5 empty] | Spider 3.54 sigma tgrow < 60ns | WW44 | Lu, Kumar, Hemant, Dan, John | No new data since WW35 (pending healthy spider validation) ≈≈≈≈≈≈≈≈ (from Q3) S26 (38nm) · Deck mismatch show up after first reset fire, Odd deck slower due to Tsolidus. · D3 is worst (90ns) with leading model on Seal subject to array via anneal. Projection to ATF (32nm) · -5ns/nm for even and -2ns/nm for odd decks. · 30ns D3 gap is expected closed with PM thickness scaling | Spider 3.54 sigma tgrow < 60ns | WW44 | Lu, Kumar, Hemant, Dan, John | No new data since WW35 (pending healthy spider validation) ≈≈≈≈≈≈≈≈ (from Q3) S26 (38nm) · Deck mismatch show up after first reset fire, Odd deck slower due to Tsolidus. · D3 is worst (90ns) with leading model on Seal subject to array via anneal. Projection to ATF (32nm) · -5ns/nm for even and -2ns/nm for odd decks. · 30ns D3 gap is expected closed with PM thickness scaling | Spider 3.54 sigma tgrow < 60ns | WW44 | Lu, Kumar, Hemant, Dan, John | No new data since WW35 (pending healthy spider validation) ≈≈≈≈≈≈≈≈ (from Q3) S26 (38nm) · Deck mismatch show up after first reset fire, Odd deck slower due to Tsolidus. · D3 is worst (90ns) with leading model on Seal subject to array via anneal. Projection to ATF (32nm) · -5ns/nm for even and -2ns/nm for odd decks. · 30ns D3 gap is expected closed with PM thickness scaling
| P1241 cell MTS and DTS validated | P1241 TD | Sanjay, Darren |  | ∆VT and program current DTS met with Spider | WW40 | Lu, Vikram | · 150mV ∆VT reduction due to 32nm PM (25mV/nm·6nm) is expected to be recovered by CD reduction (41p->33.5p) ≈≈≈≈≈ decoupling ∆VT = ƒ(∆CD) ≈≈≈≈ · S26 ∆VT and sigma improvement suggests odd decks recovery are needed (60mV for D1 and 120mV for D3). · ∆VT segmentation indicates odd vs. even delta comes from memory effects. (low confidences in ideas and solutions) · 30mV High confidence recovery plan on AVDM and 8% Rho reduction of 2nd Cut W. | ∆VT and program current DTS met with Spider | WW40 | Lu, Vikram | · 150mV ∆VT reduction due to 32nm PM (25mV/nm·6nm) is expected to be recovered by CD reduction (41p->33.5p) ≈≈≈≈≈ decoupling ∆VT = ƒ(∆CD) ≈≈≈≈ · S26 ∆VT and sigma improvement suggests odd decks recovery are needed (60mV for D1 and 120mV for D3). · ∆VT segmentation indicates odd vs. even delta comes from memory effects. (low confidences in ideas and solutions) · 30mV High confidence recovery plan on AVDM and 8% Rho reduction of 2nd Cut W. | ∆VT and program current DTS met with Spider | WW40 | Lu, Vikram | · 150mV ∆VT reduction due to 32nm PM (25mV/nm·6nm) is expected to be recovered by CD reduction (41p->33.5p) ≈≈≈≈≈ decoupling ∆VT = ƒ(∆CD) ≈≈≈≈ · S26 ∆VT and sigma improvement suggests odd decks recovery are needed (60mV for D1 and 120mV for D3). · ∆VT segmentation indicates odd vs. even delta comes from memory effects. (low confidences in ideas and solutions) · 30mV High confidence recovery plan on AVDM and 8% Rho reduction of 2nd Cut W.
[5 empty] | ATF41 function & meet S26 reset current spec | WW41 | Fuga, Kumar, Ananth | · CN1a @ 2D1 functioning with reset current lower than spec requirement, 2D lead lot fab out ECD ==> WW40.5 · 2nd Cut PVD W Rho/elasticity optimization: WSix ATF41 Fabout: 2D1/WW42, 2D0/WW44 | ATF41 function & meet S26 reset current spec | WW41 | Fuga, Kumar, Ananth | · CN1a @ 2D1 functioning with reset current lower than spec requirement, 2D lead lot fab out ECD ==> WW40.5 · 2nd Cut PVD W Rho/elasticity optimization: WSix ATF41 Fabout: 2D1/WW42, 2D0/WW44 | ATF41 function & meet S26 reset current spec | WW41 | Fuga, Kumar, Ananth | · CN1a @ 2D1 functioning with reset current lower than spec requirement, 2D lead lot fab out ECD ==> WW40.5 · 2nd Cut PVD W Rho/elasticity optimization: WSix ATF41 Fabout: 2D1/WW42, 2D0/WW44
P1250 Exit Pathfinding | Enabling SXP full stack space scaling from 19nm to 13nm | Max and PI | Ted, Al |  | 193i overlay |  |  |  | 193i overlay |  |  |  | 193i overlay
[5 empty] | (toppling) |  |  |  | (toppling) |  |  |  | (toppling)
[5 empty] | (1st and 2nd Cut) |  |  |  | (1st and 2nd Cut) |  |  |  | (1st and 2nd Cut)
[5 empty] | (Liner/Seal) |  |  |  | (Liner/Seal) |  |  |  | (Liner/Seal)
| CMOS/Metallization meet LRP goals (array 26.5p 4Kx4Kx4D) | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al | 2kx4kx4d decision | Pass BWF DR at nom and the w.c. on TC03 | WW51 | Lu, Khaled |  | Pass BWF DR at nom and the w.c. on TC03 | WW51 | Lu, Khaled |  | Pass BWF DR at nom and the w.c. on TC03 | WW51 | Lu, Khaled
|  |  |  | 2kx4kx4d decision | TC03 silicon results meet speculative DTS | WW51 | Lu, Baofu | 2 info turn planned @WW45 and WW52 | TC03 silicon results meet speculative DTS | WW51 | Lu, Baofu | 2 info turn planned @WW45 and WW52 | TC03 silicon results meet speculative DTS | WW51 | Lu, Baofu | 2 info turn planned @WW45 and WW52
|  |  |  | 2kx4kx4d decision | Metallization scheme to meet CoT target | WW51 | Khaled, Eddie |  | Metallization scheme to meet CoT target | WW51 | Khaled, Eddie |  | Metallization scheme to meet CoT target | WW51 | Khaled, Eddie
| BiSM meet Bow Falls LRP goal | Max (PI), Brian (DE), Kiran (MI) | DerChang, Al | SD only spider process | Iprogram < 40uA at 30% PG4 yield or higher | WW51 | Dan,Fuga,Ananth,Cathy | not started, gated by full stack spider yield | Iprogram < 40uA at 30% PG4 yield or higher | WW51 | Dan,Fuga,Ananth,Cathy | not started, gated by full stack spider yield | Iprogram < 40uA at 30% PG4 yield or higher | WW51 | Dan,Fuga,Ananth,Cathy | not started, gated by full stack spider yield
[5 empty] | Die Size energy meet LRP goal | WW51 | Balaji | decoder footprint on par with unipolar, tracking to WW39 | Die Size energy meet LRP goal | WW51 | Balaji | decoder footprint on par with unipolar, tracking to WW39 | Die Size energy meet LRP goal | WW51 | Balaji | decoder footprint on par with unipolar, tracking to WW39
| 1.5b/c | Kiran | Chuck, Al |  | (Algo work, read disturb and cycling endurance) |  | Sanjay, Hemant |  | (Algo work, read disturb and cycling endurance) |  | Sanjay, Hemant |  | (Algo work, read disturb and cycling endurance) |  | Sanjay, Hemant
[5 empty] | (Design work, circuit, energy, cycle time, bw) |  | Sandeep |  | (Design work, circuit, energy, cycle time, bw) |  | Sandeep |  | (Design work, circuit, energy, cycle time, bw) |  | Sandeep
[5 empty] | SD material ID'd with 600mV delta Vt and 70mV sigma | WW? | Dan, Fuga | L0 & MID yield gating: Next check point ~ ww38 | SD material ID'd with 600mV delta Vt and 70mV sigma | WW? | Dan, Fuga | L0 & MID yield gating: Next check point ~ ww38 | SD material ID'd with 600mV delta Vt and 70mV sigma | WW? | Dan, Fuga | L0 & MID yield gating: Next check point ~ ww38
| POR decision for 2Kx4Kx4D | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al |  | (Circuit) |  | Sandeep, Balaji |  | (Circuit) |  | Sandeep, Balaji |  | (Circuit) |  | Sandeep, Balaji
[5 empty] | (CMOS/DR) |  | Balaji, Luo |  | (CMOS/DR) |  | Balaji, Luo |  | (CMOS/DR) |  | Balaji, Luo
[5 empty] | (Metallization/Routing) |  | Sandeep, Khaled |  | (Metallization/Routing) |  | Sandeep, Khaled |  | (Metallization/Routing) |  | Sandeep, Khaled
Beyond Roadmap | JProgram reduction path to meet theoretical limit | P1250 and beyond | DerChang, Max |  | · Quantify Goal with BK mechanism | WW38 | Fuga | Analytical & numerical model being created:ww39 | · Quantify Goal with BK mechanism | WW38 | Fuga | Analytical & numerical model being created:ww39 | · Quantify Goal with BK mechanism | WW38 | Fuga | Analytical & numerical model being created:ww39
[5 empty] | · Add'l 20% reduction of ATF41 Ireset (85uA) | WW46 | Fuga, Kumar | CN2a @ 2D1 exhibit 90uA of scaling current: 2D read w/ full I3 Vs. E3 WD RA ~ ww39 | · Add'l 20% reduction of ATF41 Ireset (85uA) | WW46 | Fuga, Kumar | CN2a @ 2D1 exhibit 90uA of scaling current: 2D read w/ full I3 Vs. E3 WD RA ~ ww39 | · Add'l 20% reduction of ATF41 Ireset (85uA) | WW46 | Fuga, Kumar | CN2a @ 2D1 exhibit 90uA of scaling current: 2D read w/ full I3 Vs. E3 WD RA ~ ww39
[5 empty] | · Jprogram reduction goal met | WW51 | Fuga, Kumar | Pending 2D read on TECN options | · Jprogram reduction goal met | WW51 | Fuga, Kumar | Pending 2D read on TECN options | · Jprogram reduction goal met | WW51 | Fuga, Kumar | Pending 2D read on TECN options
| Seasoning elimination | P1241 TD | DerChang, Max |  | 50% ΔVFORM or 'seasoning' cycles on MID | WW48 | Fuga | Al2O3 interface reduces ∆Vt (evolution) by 100mV The followings not changing ∆Vt but increase rate of change: MECN decrease rate of change: HiK Seal, PLaST, 82, 67 anneal | 50% ΔVFORM or 'seasoning' cycles on MID | WW48 | Fuga | Al2O3 interface reduces ∆Vt (evolution) by 100mV The followings not changing ∆Vt but increase rate of change: MECN decrease rate of change: HiK Seal, PLaST, 82, 67 anneal | 50% ΔVFORM or 'seasoning' cycles on MID | WW48 | Fuga | Al2O3 interface reduces ∆Vt (evolution) by 100mV The followings not changing ∆Vt but increase rate of change: MECN decrease rate of change: HiK Seal, PLaST, 82, 67 anneal
[5 empty] | 50% ΔVFORM or 'seasoning' cycles on ATF41 | Q1 | Fuga |  | 50% ΔVFORM or 'seasoning' cycles on ATF41 | Q1 | Fuga |  | 50% ΔVFORM or 'seasoning' cycles on ATF41 | Q1 | Fuga
| C-cell bias elimination | P1241 TD | DerChang, Max |  | Critical metric & S26 based pareto | WW40 | Dany |  | Critical metric & S26 based pareto | WW40 | Dany |  | Critical metric & S26 based pareto | WW40 | Dany
| TC04 definition and Test chip methodology | RTD | DerChang, Erv, Mase
| (3DIC) | Optane PF | DerChang |  |  |  | Sandeep, Prashant |  |  |  | Sandeep, Prashant |  |  |  | Sandeep, Prashant
| (Decoder) | Optane PF | DerChang, Mase |  |  |  | Sandeep, Balaji |  |  |  | Sandeep, Balaji |  |  |  | Sandeep, Balaji
| 3D Tier | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang |  |  |  | Max, Khaled, DerChang |  |  |  | Max, Khaled, DerChang
| 3D Tier with Pillar select | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang |  |  |  | Max, Khaled, DerChang |  |  |  | Max, Khaled, DerChang
| Stack with Deck Select | Optane PF | DerChang, Al |  |  |  | Max, Khaled |  |  |  | Max, Khaled |  |  |  | Max, Khaled
| 3DXP stacking architecture scaling limit | Optane PF | DerChang |  | Unipolar full stack MTS scaling limits |  | Lu |  | Unipolar full stack MTS scaling limits |  | Lu |  | Unipolar full stack MTS scaling limits |  | Lu
[5 empty] | Bipolar SD only MTS scaling limits |  | Fuga | Ab-initio and L0 for predictive IV model release | Bipolar SD only MTS scaling limits |  | Fuga | Ab-initio and L0 for predictive IV model release | Bipolar SD only MTS scaling limits |  | Fuga | Ab-initio and L0 for predictive IV model release
[5 empty] | BW, Density scaling limits (circuit/Algo) |  | Dany, Balaji |  | BW, Density scaling limits (circuit/Algo) |  | Dany, Balaji |  | BW, Density scaling limits (circuit/Algo) |  | Dany, Balaji
[5 empty] | Monolithic CMOS scaling limits |  | Luo |  | Monolithic CMOS scaling limits |  | Luo |  | Monolithic CMOS scaling limits |  | Luo
| Diode select reverse inhibit architecture | Optane PF | DerChang |  | DTS and T-spec |  | Dany |  | DTS and T-spec |  | Dany |  | DTS and T-spec |  | Dany
HK oxide material scaling

## WW40
O: objective | Quarterly Objectives |  |  |  | Key Results
Objective / Goal | Interim Milestone / Sub Goal | Customers | Sponsors | dependency | As Measured by | ECD | Owners | Status / Tracking
Material exploration L0/L1E scorecard achieves 2 weeks info turn | L1E Process flow, test flow and data analysis qualified for electrode, PM and SD scorecard assessment | MWG | Max, DerChang |  | · MID structural yield > 90% @L0P0 for all route flavors (Electrode/SD/PM) - 6 lots | WW51 | Fuga, Abhishek, Hank | · Lead Si shows zero yield, w/ fail pareto dominated by SHORT (>90%) · 2nd lot (additional 2 wafers), show fail pareto change to OPEN @ matched process cond’s. Baseline in segmentation · EFA/PFA id short site at corners of MOAT. Focus on DEFMET predictability enablement (ww40) · Actively seeking for 6 weeks NF in 11 weeks!!!
[5 empty] | · MID functionality yield > 90% @L1P1 for all route flavors (E's/SD/BiSM/PM) and meeting DTS screening needs - 6 lots | WW51 | Fuga, Abhishek, Hank | WW38->WW43+ SD lot fab out; gated by Structural Yield
L0 Process Flow, Metrology ready for electrode, PM, SD scorecard assessment
P1241 Definition Closure | W2W tcycle < 300ns | P1241 TD | Sanjay, Darren | Spider Structure yield and comp. match ATF41 | Spider 3.54 sigma tnuc < 160ns (near) | WW44 | Lu, Kumar, Hemant, Dan, John | · tnuc: Volume S26 data suggest D2 is the worst, 193ns vs. 80ns required. PM thickness DOE shows weak improvement (<15ns reduction at 0.5 R2) ==> project ATF tnuc ~355ns (~195ns gap) · Early segmentation suggest deck/polarity dependency more than segregation slope. Seeking for a integrated RA/RM (all owners) by the end of WW40.
[5 empty] | Spider 3.54 sigma tgrow < 60ns | WW44 | Lu, Kumar, Hemant, Dan, John | No new data since WW35 (pending healthy spider validation) ≈≈≈≈≈≈≈≈ (from Q3) S26 (38nm) · Deck mismatch show up after first reset fire, Odd deck slower due to Tsolidus. · D3 is worst (90ns) with leading model on Seal subject to array via anneal. Projection to ATF (32nm) · -5ns/nm for even and -2ns/nm for odd decks. · 30ns D3 gap is expected closed with PM thickness scaling
| P1241 cell MTS and DTS validated | P1241 TD | Sanjay, Darren |  | ∆VT and program current DTS met with Spider | WW40 | Lu, Vikram | · 150mV ∆VT reduction due to 32nm PM (25mV/nm·6nm) is expected to be recovered by CD reduction (41p->33.5p) ≈≈≈≈≈ decoupling ∆VT = ƒ(∆CD) ≈≈≈≈ · S26 ∆VT and sigma improvement suggests odd decks recovery are needed (60mV for D1 and 120mV for D3). · ∆VT segmentation indicates odd vs. even delta comes from memory effects. (low confidences in ideas and solutions) · 30mV High confidence recovery plan on AVDM and 8% Rho reduction of 2nd Cut W. | 138
[5 empty] | ATF41 function & meet S26 reset current spec | WW41 | Fuga, Kumar, Ananth | · CN1a @ 2D1 functioning with reset current lower than spec requirement, 2D lead lot fab out ECD ==> WW40.5 · 2nd Cut PVD W Rho/elasticity optimization: WSix ATF41 Fabout: 2D1/WW42, 2D0/WW44
P1250 Exit Pathfinding | Enabling SXP full stack space scaling from 19nm to 13nm | Max and PI | Ted, Al |  | 193i overlay
(toppling)
(1st and 2nd Cut)
(Liner/Seal)
| CMOS/Metallization meet LRP goals (array 26.5p 4Kx4Kx4D) | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al | 2kx4kx4d decision | Pass BWF DR at nom and the w.c. on TC03 | WW51 | Lu, Khaled
|  |  |  | 2kx4kx4d decision | TC03 silicon results meet speculative DTS | WW51 | Lu, Baofu | 2 info turn planned @WW45 and WW52
|  |  |  | 2kx4kx4d decision | Metallization scheme to meet CoT target | WW51 | Khaled, Eddie
| BiSM meet Bow Falls LRP goal | Max (PI), Brian (DE), Kiran (MI) | DerChang, Al | SD only spider process | Iprogram < 40uA at 30% PG4 yield or higher | WW51 | Dan,Fuga,Ananth,Cathy | not started, gated by full stack spider yield
[5 empty] | Die Size energy meet LRP goal | WW51 | Balaji | decoder footprint on par with unipolar, tracking to WW39
| 1.5b/c | Kiran | Chuck, Al |  | (Algo work, read disturb and cycling endurance) |  | Sanjay, Hemant
[5 empty] | (Design work, circuit, energy, cycle time, bw) |  | Sandeep
[5 empty] | SD material ID'd with 600mV delta Vt and 70mV sigma | WW? | Dan, Fuga | L0 & MID yield gating: Next check point ~ ww38
| POR decision for 2Kx4Kx4D | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al |  | (Circuit) |  | Sandeep, Balaji
[5 empty] | (CMOS/DR) |  | Balaji, Luo
[5 empty] | (Metallization/Routing) |  | Sandeep, Khaled
Beyond Roadmap | JProgram reduction path to meet theoretical limit | P1250 and beyond | DerChang, Max |  | · Quantify Goal with BK mechanism | WW38 | Fuga | Analytical & numerical model being created:ww39
[5 empty] | · Add'l 20% reduction of ATF41 Ireset (85uA) | WW46 | Fuga, Kumar | CN2a @ 2D1 exhibit 90uA of scaling current: 2D read w/ full I3 Vs. E3 WD RA ~ ww39
[5 empty] | · Jprogram reduction goal met | WW51 | Fuga, Kumar | Pending 2D read on TECN options
| Seasoning elimination | P1241 TD | DerChang, Max |  | 50% ΔVFORM or 'seasoning' cycles on MID | WW48 | Fuga | Al2O3 interface reduces ∆Vt (evolution) by 100mV The followings not changing ∆Vt but increase rate of change: MECN decrease rate of change: HiK Seal, PLaST, 82, 67 anneal
[5 empty] | 50% ΔVFORM or 'seasoning' cycles on ATF41 | Q1 | Fuga
| C-cell bias elimination | P1241 TD | DerChang, Max |  | Critical metric & S26 based pareto | WW40 | Dany
| TC04 definition and Test chip methodology | RTD | DerChang, Erv, Mase
| (3DIC) | Optane PF | DerChang |  |  |  | Sandeep, Prashant
| (Decoder) | Optane PF | DerChang, Mase |  |  |  | Sandeep, Balaji
| 3D Tier | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang
| 3D Tier with Pillar select | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang
| Stack with Deck Select | Optane PF | DerChang, Al |  |  |  | Max, Khaled
| 3DXP stacking architecture scaling limit | Optane PF | DerChang |  | Unipolar full stack MTS scaling limits |  | Lu
[5 empty] | Bipolar SD only MTS scaling limits |  | Fuga | Ab-initio and L0 for predictive IV model release
[5 empty] | BW, Density scaling limits (circuit/Algo) |  | Dany, Balaji
[5 empty] | Monolithic CMOS scaling limits |  | Luo
| Diode select reverse inhibit architecture | Optane PF | DerChang |  | DTS and T-spec |  | Dany
HK oxide material scaling

## WW35 2020
O: objective | Quarterly Objectives |  |  |  | Key Results
Objective / Goal | Interim Milestone / Sub Goal | Customers | Sponsors | dependency | As Measured by | ECD | Owners | Status / Tracking
Material exploration L0/L1E scorecard achieves 2 weeks info turn | L1E Process flow, test flow and data analysis qualified for electrode, PM and SD scorecard assessment | MWG | Max, DerChang |  | · MID structural yield > 90% @L0P0 for all route flavors (Electrode/SD/PM) - 6 lots | WW51 | Fuga, Abhishek, Hank | WW36 lead lot shipped to SC
[5 empty] | · MID functionality yield > 90% @L1P1 for all route flavors (E's/SD/BiSM/PM) and meeting DTS screening needs - 6 lots | WW51 | Fuga, Abhishek, Hank | WW38 SD lot fab out; gated by Structural Yield
L0 Process Flow, Metrology ready for electrode, PM, SD scorecard assessment
P1241 Definition Closure | W2W tcycle < 300ns | P1241 TD | Sanjay, Darren | Spider Structure yield and comp. match ATF41 | Spider 3.54 sigma tnuc < 160ns (near) | WW44 | Lu | · tnuc: Volume S26 data suggest D2 is the worst, 144ns vs. 80ns required. PM thickness DOE shows weak improvement (<20ns reduction at 0.5 R2) ==> project ATF tnuc ~250ns (~90ns gap) · Back to early segmentation stage. with a focus on degradation mechanism and nuc sigma.
[5 empty] | Spider 3.54 sigma tgrow < 60ns | WW44 | Lu | S26 (38nm) · Deck mismatch show up after first reset fire, Odd deck slower due to Tsolidus. · D3 is worst (90ns) with leading model on Seal subject to array via anneal. Projection to ATF (32nm) · -5ns/nm for even and -2ns/nm for odd decks. · 30ns D3 gap is expected closed with PM thickness scaling
| P1241 cell MTS and DTS validated | P1241 TD | Sanjay, Darren |  | ∆VT and program current DTS met with Spider | WW40 | Lu | · PR11 on set algo optimization see the gap to 150mV (vs. 1150mV goal). Key issues is process health to reduce variability and ambient control (>400mV lot to lot) | 138
[5 empty] | ATF41 function & meet S26 reset current spec | WW41 | Fuga, Lu, Ananth | · CN1a @ 2D1 functioning with reset current lower than spec requirement, 2D lead lot fab out ECD WW39 · 2nd Cut PVD W elasticity optimization required due to WSiN removal: 33.5P L1D results ~ ww38
P1250 Exit Pathfinding | Enabling SXP full stack space scaling from 19nm to 13nm | Max and PI | Ted, Al |  | 193i overlay
(toppling)
(1st and 2nd Cut)
(Liner/Seal)
| CMOS/Metallization meet LRP goals (array 26.5p 4Kx4Kx4D) | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al | 2kx4kx4d decision | Pass BWF DR at nom and the w.c. on TC03 | WW51 | Lu, Khaled
|  |  |  | 2kx4kx4d decision | TC03 silicon results meet speculative DTS | WW51 | Lu, Baofu | 2 info turn planned @WW45 and WW52
|  |  |  | 2kx4kx4d decision | Metallization scheme to meet CoT target | WW51 | Khaled, Eddie
| BiSM meet Bow Falls LRP goal | Max (PI), Brian (DE), Kiran (MI) | DerChang, Al | SD only spider process | Iprogram < 40uA at 30% PG4 yield or higher | WW51 | Dan,Fuga,Ananth,Cathy | not started, gated by full stack spider yield
[5 empty] | Die Size energy meet LRP goal | WW51 | Balaji | decoder footprint on par with unipolar, tracking to WW39
| 1.5b/c | Kiran | Chuck, Al |  | (Algo work, read disturb and cycling endurance) |  | Sanjay, Hemant
[5 empty] | (Design work, circuit, energy, cycle time, bw) |  | Sandeep
[5 empty] | SD material ID'd with 600mV delta Vt and 70mV sigma | WW? | Dan, Fuga | L0 & MID yield gating: Next check point ~ ww38
| POR decision for 2Kx4Kx4D | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al |  | (Circuit) |  | Sandeep, Balaji
[5 empty] | (CMOS/DR) |  | Balaji, Luo
[5 empty] | (Metallization/Routing) |  | Sandeep, Khaled
Beyond Roadmap | JProgram reduction path to meet theoretical limit | P1250 and beyond | DerChang, Max |  | · Quantify Goal with BK mechanism | WW38 | Fuga | Analytical & numerical model being created:ww39
[5 empty] | · Add'l 20% reduction of ATF41 Ireset (85uA) | WW46 | Fuga, Kumar | CN2a @ 2D1 exhibit 90uA of scaling current: 2D read w/ full I3 Vs. E3 WD RA ~ ww39
[5 empty] | · Jprogram reduction goal met | WW51 | Fuga, Kumar | Pending 2D read on TECN options
| Seasoning elimination | P1241 TD | DerChang, Max |  | 50% ΔVFORM or 'seasoning' cycles on MID | WW48 | Fuga | Al2O3 interface and MECN results to be reviewed: > 40% opportunity (S15C/S26A SORT/WLR/WLB)
[5 empty] | 50% ΔVFORM or 'seasoning' cycles on ATF41 | Q1 | Fuga
| C-cell bias elimination | P1241 TD | DerChang, Max |  | Critical metric & S26 based pareto | WW40 | Dany
| TC04 definition and Test chip methodology | RTD | DerChang, Erv, Mase
| (3DIC) | Optane PF | DerChang |  |  |  | Sandeep, Prashant
| (Decoder) | Optane PF | DerChang, Mase |  |  |  | Sandeep, Balaji
| 3D Tier | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang
| 3D Tier with Pillar select | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang
| Stack with Deck Select | Optane PF | DerChang, Al |  |  |  | Max, Khaled
| 3DXP stacking architecture scaling limit | Optane PF | DerChang |  | Unipolar full stack MTS scaling limits |  | Lu
[5 empty] | Bipolar SD only MTS scaling limits |  | Fuga | Ab-initio and L0 for predictive IV model release
[5 empty] | BW, Density scaling limits (circuit/Algo) |  | Dany, Balaji
[5 empty] | Monolithic CMOS scaling limits |  | Luo
| Diode select reverse inhibit architecture | Optane PF | DerChang |  | DTS and T-spec |  | Dany

## WW3
O: objective | Quarterly Objectives |  |  |  | Key Results
Objective / Goal | Interim Milestone / Sub Goal | Customers | Sponsors | dependency | As Measured by | ECD | Owners | Status / Tracking
| P1241 cell MTS and DTS validated | P1241 TD | Sanjay, Darren |  | ∆VT and program current DTS met with Spider | WW40 | Lu, Vikram | · 150mV ∆VT reduction due to 32nm PM (25mV/nm·6nm) is expected to recovered by CD reduction (41p->33.5p) · S26 ∆VT and sigma improvement suggests odd decks recovery are needed (60mV for D1 and 120mV for D3). · ∆VT segmentation indicates odd vs. even delta comes from memory effects. (low confidences in ideas and solutions) · 30mV High confidence recovery plan on AVDM and 8% Rho reduction of 2nd Cut W. | 138
[5 empty] | ATF41 function & meet S26 reset current spec | WW41 | Fuga, Lu, Ananth | · CN1a @ 2D1 functioning with reset current lower than spec requirement, 2D lead lot fab out ECD ==> WW40.5 · 2nd Cut PVD W Rho/elasticity optimization: WSix ATF41 Fabout: 2D1/WW42, 2D0/WW44
P1250 Exit Pathfinding | Enabling SXP full stack space scaling from 19nm to 13nm | Max and PI | Ted, Al |  | 193i overlay
(toppling)
(1st and 2nd Cut)
(Liner/Seal)
| CMOS/Metallization meet LRP goals (array 26.5p 4Kx4Kx4D) | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al | 2kx4kx4d decision | Pass BWF DR at nom and the w.c. on TC03 | WW51 | Lu, Khaled
|  |  |  | 2kx4kx4d decision | TC03 silicon results meet speculative DTS | WW51 | Lu, Baofu | 2 info turn planned @WW45 and WW52
|  |  |  | 2kx4kx4d decision | Metallization scheme to meet CoT target | WW51 | Khaled, Eddie
| BiSM meet Bow Falls LRP goal | Max (PI), Brian (DE), Kiran (MI) | DerChang, Al | SD only spider process | Iprogram < 40uA at 30% PG4 yield or higher | WW51 | Dan,Fuga,Ananth,Cathy | not started, gated by full stack spider yield
[5 empty] | Die Size energy meet LRP goal | WW51 | Balaji | decoder footprint on par with unipolar, tracking to WW39
| 1.5b/c | Kiran | Chuck, Al |  | (Algo work, read disturb and cycling endurance) |  | Sanjay, Hemant
[5 empty] | (Design work, circuit, energy, cycle time, bw) |  | Sandeep
[5 empty] | SD material ID'd with 600mV delta Vt and 70mV sigma | WW? | Dan, Fuga | L0 & MID yield gating: Next check point ~ ww38
| POR decision for 2Kx4Kx4D | Erv(PI), Brian(DE), Kiran(MI) | DerChang, Al |  | (Circuit) |  | Sandeep, Balaji
[5 empty] | (CMOS/DR) |  | Balaji, Luo
[5 empty] | (Metallization/Routing) |  | Sandeep, Khaled
Beyond Roadmap | JProgram reduction path to meet theoretical limit | P1250 and beyond | DerChang, Max |  | · Quantify Goal with BK mechanism | WW38 | Fuga | Analytical & numerical model being created:ww39
[5 empty] | · Add'l 20% reduction of ATF41 Ireset (85uA) | WW46 | Fuga, Kumar | CN2a @ 2D1 exhibit 90uA of scaling current: 2D read w/ full I3 Vs. E3 WD RA ~ ww39
[5 empty] | · Jprogram reduction goal met | WW51 | Fuga, Kumar | Pending 2D read on TECN options
| Seasoning elimination | P1241 TD | DerChang, Max |  | 50% ΔVFORM or 'seasoning' cycles on MID | WW48 | Fuga | Al2O3 interface reduces ∆Vt (evolution) by 100mV The followings not changing ∆Vt but increase rate of change: MECN decrease rate of change: HiK Seal, PLaST, 82, 67 anneal
[5 empty] | 50% ΔVFORM or 'seasoning' cycles on ATF41 | Q1 | Fuga
| C-cell bias elimination | P1241 TD | DerChang, Max |  | Critical metric & S26 based pareto | WW40 | Dany
| TC04 definition and Test chip methodology | RTD | DerChang, Erv, Mase
| (3DIC) | Optane PF | DerChang |  |  |  | Sandeep, Prashant
| (Decoder) | Optane PF | DerChang, Mase |  |  |  | Sandeep, Balaji
| 3D Tier | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang
| 3D Tier with Pillar select | Optane PF | DerChang, Al |  |  |  | Max, Khaled, DerChang
| Stack with Deck Select | Optane PF | DerChang, Al |  |  |  | Max, Khaled
| 3DXP stacking architecture scaling limit | Optane PF | DerChang |  | Unipolar full stack MTS scaling limits |  | Lu
[5 empty] | Bipolar SD only MTS scaling limits |  | Fuga | Ab-initio and L0 for predictive IV model release
[5 empty] | BW, Density scaling limits (circuit/Algo) |  | Dany, Balaji
[5 empty] | Monolithic CMOS scaling limits |  | Luo
| Diode select reverse inhibit architecture | Optane PF | DerChang |  | DTS and T-spec |  | Dany
HK oxide material scaling

## Pathfinding Categorization
Category |  | Problems and/or Objectives |  | Owners
I. | To improve incumbent technology by leveraging existing capability (Incumbent: 41p/33.5p Full Stack SXP)
|  | 1 | C-Cell bias eliminations | Dany
|  | 2 | Seasoning eliminations | Fuga
|  | 3 | Program current density reduction | Fuga, Lu
|  | 4 | Sigma Reductions | Vikram (Koushik)
II. | To explore technology features needed for next technology node (POR 3DXP scaling)
|  | 1 | PM2A3 phase change | Kumar
|  | 2 | SD2 threshold switching | Kumar
|  | 3 | W scaling limits | Kumar
|  | 4 | Thermal disturb scaling limits | Lu
|  | 5 | Toppling scaling limits | Dan, Max
|  | 6 | Liner/seal/gapfill scaling limits | Todd, Frank
|  | 7 | Tile capacity scaling | Sandeep, Balaji
|  | 8 | HVT scaling | Luo, Baofu
III. | Deep research topics to prep for roadmap candidates (Disrupter: beyond Full Stack SXP 4-Deck stacking)
|  | 1 | Full Stack 1.5b/c | Sanjay, Hemant, Saad
|  | 2 | BiSM | Fuga, Dany, Balaji
|  | 3 | iPCM | Kumar, Lu (Charles, Kaan)
|  | 4 | thin film low leakage diode | (Charles, Kaan)
|  | 5 | Diode Select 3DXP | Dany
|  | 6 | "Float" inhibit decoder | Balaji, Dany
|  | 7 | Multi-bit Access | Mase
|  | 8 | non-planar HVT for decoder | Prashant, DerChang, Erv
|  | 9 | 3DIC | Prashant
|  | 10 | 3DXP array construction by tiering | Khaled, Max
|  | 11 | Deck select | Max, Prashant
|  | 12 | Pillar select | Max, Prashant