## Optane TD Org Goals
[6 empty] | Mid Quarter Update |  |  |  |  | End of Quarter Update
Pillar | Category | Current vs. Old IMBO | Staff Sponsor | Owner | Q1'21 Goals | Status (mid qtr) | Trend (mid qtr) | Q1 Mid Quarter Comments | Date of Update (mid qtr) | Date of Review by Staff Sponsor (mid qtr) | Status (EOQ) | Trend (EOQ) | Comments (Q1 EOQ) | Date of Review by Staff Sponsor (EOQ) | Date of Review by Ted/Al (EOQ) | Q2'21 Goals | Status (mid qtr) | Trend (mid qtr) | Q1 Mid Quarter Comments | Date of Update and Rvw (EOQ) | Status (EOQ) | Trend (EOQ) | Comments (Q1 EOQ) | Q3'21 Goals | Status (mid qtr) | Trend (mid qtr) | Q1 Mid Quarter Comments | Date of Update and Rvw (EOQ) | Status (EOQ) | Trend (EOQ) | Comments (Q1 EOQ) | Q4'21 Goals | Status (mid qtr) | Trend (mid qtr) | Q1 Mid Quarter Comments | Date of Update and Rvw (EOQ) | Status (EOQ) | Trend (EOQ) | Comments (Q1 EOQ)
Technology | S26A | Current IMBO | Narahari Ramanuja | Sarah Williams / Bharat K. | Storage baseline yield avg >70% and line yield >90% | 2 | 2 | RTD baseline avg stg yield ~ 65% due to 55 flakes; LY >90% | [7 empty] | 1) EOL PG1 capability demonstration with sort and WLR consistent with 9.3 baseline and PG1 PRQ requirements. 2) Storage baseline yield avg >70% and line yield >90% | [7 empty] | 1) Storage baseline yield avg >70% and line yield >90% | [7 empty] | 1) Storage baseline yield avg >70% and line yield >90%
| ATF | Current IMBO | Chuck Dennison | Darren DeNardis / Veera Dandu | 1) 1D Spider >10% PG4 Structure Yield Demo 2) NPI complete for ATF 1D. | 2 | 2 | 1.) For 10% PG4 SY: Need WL / BL / Opens > 50%. Demo Status: WL > 50%; BL: > 50%; Opens: 0% (15X to goal). Opens in segmentation with SD void / small CD ID’d 2) NPI: On track for ww12 to intercept ATF 1st Si with latest learning | 2021-02-13 | [6 empty] | 1.) Move development from 41nm to 33.5 nm 2) ATF 2D NPI and 2D Si with Structural yield demo 3) ATF 4D NPI complete | [7 empty] | 1) ATF 2D PG4 Si yield demo by ww30 and >5% by ww39. 2) Xfer to ATF of PLS capable cell (1-step FC FP) 3) ATF 4D PG4 structural yield | [7 empty] | 1) ATF PLS achievement (demo 2D PG4 30%, etc.): 2) ATF 4D PG4 yield demo
| Optane CMOS | Current IMBO | Chuck Dennison | Erv Hill/ Summer Hollingsworth | 1) ATF NTI and ATF SA yield >0 2) TC03 modification for BWF process file defined 3) ATF device meets DTS | 3 | 3 | NTI SA sort tracking to mid WW13 at sort – all indications are yield > 0 achievable TC03 modification def’n on track DTS compliance at 90% based on ALF/TC03 data | 2021-02-11 |  |  |  | 1) 2) 75% - ontrack for CMOS and 4WNF on interconnect 3) |  |  | 1) ATF SA Yield >50% 2) BWF Rev 0 DTS gap assessment complete | [7 empty] | 1) ATF SA >70% yield 2) ATF SA meeting PLS-C criteria” drive-to date: ww36 3) Roadmap to close BWF DTS defined | [7 empty] | 1) ATF SA >75% yield 2) ATF HTOL DPM <1K 3) BWF 2Kx4K DTS met
| Pathfinding | Current IMBO | Derchang Kau | Max Hineman / Frank Goodwin | 1) (MLC) tnuc sigma segmentation complete, algo/process model developed | 2 | 2 | Electrical fingerprint of tnuc sigma complete and TEM submission for physical CoV analysis is WIP. Rev0 roadmap defined for the two intermediate state options and roadmap validation with proposed algo is planned for the second half of the quarter. | 2021-02-09 |  |  |  | 1) 0% - a) Empirically identified nucleation avoidance by increasing read current. Model for distribution engineering is in progress b) memory effect fingerprint added to iMBO in WW10: SD only completed; 3 WNF on full stack fingerprint | WW13 |  | 1) (Space scaled) ALD nitride liner seal skews enabled for ATF41 2) (Materials PF) MID vehicle capability demonstrated | [7 empty] | 1) (space scaled) At pitch structure enabled @ scaled pitch 2) (MLC) Read Disturb model validated for 1.5b/c 3) Single Chal Spider vehicle enabled for 1.5b/c and BiSM 4) MID correlation to 41pitch silicon completed | [7 empty] | 1) Pitch Scaling a. ALD nitride liner/seal validation on n-1/2 node b. Toppling capability demonstration at pitch 2) MLC a. Tnuc distribution engineering roadmap demonstration b. SD memory window validated 3) BiSM a. Cell scalability validated
Cost | Technology Cost | Current IMBO | Narahari Ramanuja | Veera / Darren / Summer / Erv / Sarah / Bharat / Zach | 1) Deliver high/med/low confidence CL technology roadmap for $450 CPW savings (at 15k GF) 2) Convert CL savings from 15k GF to 4k YF equivalent + complete min-tech reuse eval | [10 empty] | 2) Deliver high/med/low confidence CL technology roadmap for $XX CPW savings (at 4k YF), ECN $XX savings into MOR (pending CL conversion to 4k YF & min-tech reuse completion) 3) Convert MOR step-cost-model from 15k GF to 4k YF | [7 empty] | 2) ECN $XX savings into MOR | [7 empty] | 2) ECN $XX savings into MOR 2) Meet PLS Cost Criteria: Deliver MOR (cmos + array) HVM wafer cost roadmap to close gaps by mid of 2022. ($Path to 3067)
| Mfg Affordability | Current IMBO | Tash Anestos | Jam Sorooshian / Zach Sigmon | 1) LRP Mfg Affordability: Identify and load through 2025 w/line-of-sight to $4k CPW at 4k wspw by Q4-2024, with assumptions and owners identified. | 3 | 0 | Currrent LRP forecast at $3935/wafer in Q4'24. In process of vetting miscellaneous inputs | 2021-02-11 | [6 empty] | 1) LRP Mfg Affordability: Validate 4/4/4 w/new demand and fully vetted miscellaneous BTI inputs 2) Identify other opportunities to pull in $4k WC to Q1'24 3) $4k CPW projects fully scoped by owners through 2025, complete 2021/2022 actions (25%) | [7 empty] | 1) Opportunities from Q2'21 are ratified and loaded in Q3'21 LRP 2) LRP Mfg Affordability: Validate 4/4/4 with new demand 2) LRP Mfg Affordability: Complete 2021/2022 actions (75%) | [7 empty] | 1) DPOR'22 assumptions committed 2) LRP Mfg Affordability: Complete 2021/2022 actions (100%)
| Capital | Current IMBO | Tash Anestos | James DeForrest /Matthew Smith | 1) Fully integrate into DPG Capital Process 2) Q1 Capex and DPN within 5% of MPOR 3) HVM Tool Install costs trending to 12.5% of M&E | 0 | 0 | 1) Work with DPG underway 2) Awaiting M2 Update 3) Previous cost trending to 12.8%, awaiting 4k tool list | [7 empty] | 1) Q2 CapEx and DPN within 5% of MPOR 2) HVM Tool Install costs trending to 12% of M&E | [7 empty] | 1) Q3 CapEx and DPN within 5% of JPOR 2) HVM Tool Install costs trending to 11.5% of M&E | [7 empty] | 1) Q4 CapEx and DPN within 5% of SPOR 2) HVM Tool Install costs trending to 11% of M&E
| OPEX | Current IMBO | Tash Anestos | Jill Staveley/Cristina Whitely-North | 1) RTD spending within 3% POR (R&D/OCOS) 2) RTD spending within 3% compared to M2 update (R&D/OCOS) 3) RTD Array commodities budget vs. actuals within +/- 7% of POR consumption. Commodities close split by consumption/non-consumption. 4) RTD TW spend +/- 10% $400k/ qtr stretch goal. | 1 | 1 | 1) R&D/OCOS split trending >1% of POR due to higher ATF moves split. 2) M2 Update not yet complete - trend will be >3%. 3) Consumption currently below POR by 3%. Project Q1 will be > 7% IMBO goal due to GNC consumption (WW6 trend is 2X over POR) with possible offset of spares PCK (est >8% to 15%) 4) WW6 TW currently 15% below stretch goal (53% below POR) - expect to continue through end of quarter. | 2021-02-09 | [6 empty] | 1) RTD spending within 3% of POR (R&D/OCOS) 2) RTD spending within 3% compared to M2 (R&D/OCOS) 3) RTD Array commodities actuals within +/- 6% of POR consumption 4) RTD TW spend +/- 10% $400k/ qtr stretch goal. | [7 empty] | 1) RTD spending within 3% of POR (R&D/OCOS) 2) RTD spending within 3% compared to M2 (R&D/OCOS) 3) RTD Array commodities actuals within +/- 6% of POR consumption 4) RTD TW spend +/- 10% $400k/ qtr stretch goal. | [7 empty] | 1) RTD spending within 3% of POR (R&D/OCOS) 2) RTD spending within 3% compared to M2 (R&D/OCOS) 3) RTD Array commodities actuals within +/- 6% of POR consumption 4) RTD TW spend +/- 10% $400k/ qtr stretch goal.
People | Staffing & Retention | Current IMBO | Tash Anestos | Roy Jacques/ Gina Gutierrez | Staffing: 1) HC target 85% achieved RTD Retention: 2) Retain >95% annualized of NSG RTD staff | 3 | 3 | Staffing: 1) HC target 85% achieved - RTD - Actual headcount= 349 with a POR of 371 = 94% - Expecting to close out the quarter ~355/371=96% - F11X - Actual headcount=336 with a POR of 338 - 101% RTD Retention: 2) Retain >95% annualized of NSG RTD staff | 2021-02-19 |  | 3 | 3 | Staffing: 1) HC target 85% achieved *Team added Kiran's headcount (23), and removed Venkat's headcount (42) this quarter. *With changes, POR=329, and actuals expected to come in at 310 = 94%. RTD Retention: 2) Retain >95% annualized of NSG RTD staff |  |  | Staffing: 1) HC target 95% achieved - changed from 100%, as we usually have some backfills in process. RTD Retention: 2) Retain >95% annualized of NSG RTD staff | [7 empty] | Staffing: 1) HC target 100% achieved RTD Retention: 2) Retain >95% annualized of NSG RTD staff | [7 empty] | Staffing: 1) HC target 100% achieved RTD Retention: 2) Retain >95% annualized of NSG RTD staff
| Org Capab | Current IMBO | Tash Anestos | Rod Spaulding/ Randy Hancock | 1) L4 MT Training for FSE Reduction (15% PAS) 2) RIHV standards completed (10) & new Mgr/Coach Certs (2/4) 3) Manager Training (70%), Safety Training (100%) + Wellnomics <5% Overall High-Risk | 3 | 3 | 1) 22% L4 (Note: F11X areas are still creating their L4 packages; ECD WW13) 2) 7 standards completed, 1 manager & 2 coaches 3) 61% manager training, 94% safety training (all), 12% HRU (all) | 2021-02-18 | [6 empty] | 1) L4 MT Training for FSE Reduction (33% PAS) 2) RIHV standards completed (15) & new Mgr/Coach Certs (2/4) 3) Manager Training (80%), Safety Training (100%) + Wellnomics <5% Overall High-Risk | [7 empty] | 1) L4 MT Training for FSE Reduction (67% PAS) 2) RIHV standards completed (25) & new Mgr/Coach Certs (2/4) 3) Manager Training (90%), Safety Training (100%) + Wellnomics <5% Overall High-Risk | [7 empty] | 1) L4 MT Training for FSE Reduction (100% PAS) 2) RIHV standards completed (35) & new Mgr/Coach Certs (2/4) 3) Manager Training (100%), Safety Training (100%) + Wellnomics <5% Overall High-Risk
| Culture and OD | Current IMBO | Ted Taylor | PLT/ Gina Guetierrez | 1) >80% EES participation rate 2) Rewards 100% complete 3) Leadership culture commitments (1 pager) finalized and communicated to team. 4) Culture steward roles and responsibilities defined | [10 empty] | 1) Review EES feedback, align teams, and develop action plans 2) Insights completion at 95% (April) 3) MDF (Mgr. Dev. Feedback) Campaign launched with 80% participation | [7 empty] | 1) Achieve EES targets at or above Intel avg 2) Achieve MDF targets at or above Intel avg 3) Insights completion 95% (July) 4) Achieve >/= 4 in culture scores from leadership team. | [7 empty] | 1) Insights completion at 95% (Nov) 2) 2022 goals set by EoY 3) Establish and resource BWF teams in TD
Operations | Cycle Time | Current IMBO | Tash Anestos | Chris Charrlin / Iris Galvez | 1) ATF CMOS avg CT 34d (2.0 SF, 25wf) 2) ATF CMOS BEOL avg CT 7d 3) ALF CMOS avg CT 32d (2.0 SF, 25 wf) 4) ALF CMOS BEOL avg CT 7d 5) 20S Array 4D+BEOL avg CT 73d (2.6 SF, 25wf) 6) ATF Array 1D+BEOL avg CT 35d (4.0 SF, 12wf) 7) ATF 1D Array+BEOL 12wf CT for HB5=21 days, for HB9=14 days 8) ATF Array 2D+BEOL avg CT 64d (4.0 SF, 12wf) | 2 | 3 | CMOS CT trending down - gaps are all due to OAK extended downs (ANI, HEI, EDT, SNI) S26A Array CT mostly flat in 80s - gap driven by LRW/PRO in January, then SAU reticle and Cu migration in February ATF Array CT significant improvement from 60's to 30's avg ATF Array HB CT also significantly improved and running at/near goal No ATF Array 2D starts yet | 2021-02-18 | [6 empty] | 1) ATF CMOS avg CT 34d (2.0 SF, 25wf) 2) ATF CMOS BEOL avg CT 7d 3) ALF CMOS avg CT 32d (2.0 SF, 25 wf) 4) ALF CMOS BEOL avg CT 7d 5) 20S Array 4D+BEOL avg CT 73d (2.6 SF, 25wf) 6) ATF Array 1D+BEOL avg CT 26d (3.0 SF, 12wf) 7) ATF 1D Array+BEOL 12wf CT for HB5=21 days, for HB9=14 days 8) ATF Array 2D+BEOL avg CT 50d (3.0 SF, 12wf) 9) ATF Array 4D avg CT 91d (3.0 SF, 12wf) | [7 empty] | 1) ATF CMOS avg CT 34d (2.0 SF, 25wf) 2) ATF CMOS BEOL avg CT 7d 3) ALF CMOS avg CT 32d (2.0 SF, 25 wf) 4) ALF CMOS BEOL avg CT 7d 5) 20S Array 4D+BEOL avg CT 73d (2.6 SF, 25wf) 6) ATF Array 1D+BEOL avg CT 22d (2.6 SF, 12wf) 7) ATF 1D Array+BEOL 12wf CT or HB5=18 days, for HB9=13 days 8) ATF Array 2D+BEOL avg CT 43d (2.6 SF, 12wf) 9) ATF Array 4D avg CT 79d (2.6 SF, 12wf) | [7 empty] | 1) ATF CMOS avg CT 34d (2.0 SF, 25wf) 2) ATF CMOS BEOL avg CT 7d 3) ALF CMOS avg CT 32d (2.0 SF, 25 wf) 4) ALF CMOS BEOL avg CT 7d 5) 20S Array 4D+BEOL avg CT 73d (2.6 SF, 25wf) 6) ATF Array 1D+BEOL avg CT 22d (2.6 SF, 12wf) 7) ATF 1D Array+BEOL 12wf CT or HB5=18 days, for HB9=13 days 8) ATF Array 2D+BEOL avg CT 43d (2.6 SF, 12wf) 9) ATF Array 4D avg CT 79d (2.6 SF, 12wf) 10) ATF Array 4D avg CT 135d (2.6 SF, 25wf)
| Availability Efficiency (AE) & Output Effic.(OE) | Current IMBO | Narahari Ramanuja | Chris Charrlin / Iris Galvez | All P1240 tools >78% conf Ae for at least 8/13 weeks in QTR | 1 | 1 | Zero weeks hitting goal Areq changed from dynamic/inv based to MOR WW08 Availability WG kicking off WW09 | 2021-02-18 | [6 empty] | All P1240 tools >78% conf Ae for at least 8/13 weeks in QTR | [7 empty] | All P1240 tools >78% conf Ae for at least 8/13 weeks in QTR | [7 empty] | All P1240 tools >78% conf Ae for at least 8/13 weeks in QTR
| Fab and Lab Capacity | Current IMBO | Tash Anestos | Iris Galvez/ Gavin Corcoran | Fab: Based on WW4.2 WSC (WSPW) S26A: 561 ATF: 452 (Pull in of KGX594/KFX595 based on Task Force feedback) Combined: 670 Lab: Combined manual TEM/AutoTEM weekly sample capacity: 160 | 1 | 1 | Fab S26A: Loadport impact on KFX591/592/593 ATF: SPU XLR2 capacity impact Combined: PROcn, Side1/2 lock out for toppling impacting both S26A and ATF Fab: Based on WW7.3 WSC (WSPW) S26A: 362 ATF: 268 Combined: 417 | 2021-02-11 | [6 empty] | Fab: Based on WW4.2 WSC (WSPW) S26A: 561 ATF: 452 Combined: 730 Lab: Combined manual TEM/AutoTEM weekly sample capacity: 160 | [7 empty] | Fab: Based on WW4.2 WSC (WSPW) S26A: 561 ATF: 500 Combined: 730 Lab: Combined manual TEM/AutoTEM weekly sample capacity: 220 | [7 empty] | Fab: Based on WW4.2 WSC (WSPW) S26A: 561 ATF: 740 Combined: 890 Lab: Combined manual TEM/AutoTEM weekly sample capacity: 240
FEB | FEB | Current IMBO | Chuck Dennison | Tiffany/Chris/Erv/Summer | 1) Quality: NSG O26A 4D Die Yield > goal, 4wk rolling avg 2) ATF skip array lead-lot through factory and yield demonstrated >0% | 2 | 2 | O26 4D Eng DY missing goal - 51L flakes, defects ATF cmos skip array lot is ~2 days behind schedule | 2021-02-18 | [6 empty] | Goals get proposed during last week of each quarter. | [7 empty] | Goals get proposed during last week of each quarter. | [7 empty] | Goals get proposed during last week of each quarter.
Support Groups | TIQ | Current IMBO | Narahari Ramanuja | Randy Hawkins/ EPCOT | Tools with planned Finishes this Qtr * Design = 8 tools * Construction (SL2) = 24 tools * eMRCL(Process Tools) = 22 tools * ATF Construction Costs within $35.1M budget. * Zero Safety Incidences • Zero Factory ITPs due to construction • Zero Construction Quality Incidences. • Zero Construction Recordables/On Site COVID transmissions. | [10 empty] | Tools with planned Finishes this Qtr All of these will increase as more tools are added. * Design = 0. * Construction (SL2) = 13 * eMRCL(Process Tools) = 6 Costs within $194.3M budget. Zero Safety Incidences • Zero Factory ITPs due to construction • Zero Construction Quality Incidences. | [7 empty] | Tools with planned Finishes this Qtr All of these will increase as more tools are added. * Design = 0. * Construction (SL2) = 4 * eMRCL(Process Tools) = 3 • Costs within $194.3M budget. •Zero Safety Incidences • Zero Factory ITPs due to construction • Zero Construction Quality Incidences. | [7 empty] | Tools with planned Finishes this Qtr All of these will increase as more tools are added. * Design = 0. * Construction (SL2) = 9 * eMRCL(Process Tools) = 5 • Costs within $194.3M budget. •Zero Safety Incidences • Zero Factory ITPs due to construction • Zero Construction Quality Incidences.
| M&O Automation | Current IMBO | Tash Anestos | Harmanjit Katoch | - Meet/beat RTD Opex KPI’s (Moveloss - 0,ITP - 1, Scrap - 0) - Automated NPI (SPC) - WW10 - Rainbow LOT training RTD stakeholders - WW08 - Critical Q-Time (CQT) Hold Lot Breach - WW08 - SIF Notification and Approval - WW10 | 2 | 3 | - Meet/beat RTD Opex KPI’s (Moveloss - 0,ITP - 1, Scrap - 0) => Zero incident in Q1 so far. - Automated NPI (SPC) - WW10 '=> On track to deliver - Rainbow LOT training RTD stakeholders - WW08 => Working on training documentation and wiki. Will finish by WW10 - Critical Q-Time (CQT) Hold Lot Breach - WW08 => Deployment is in progress - SIF Notification and Approval - WW10 '=> On track to deliver | 2021-02-19 | [6 empty] | will update by ww26 '2021
| Supply Chain Operations | Current IMBO | Narahari Ramanuja | Kristina Torsiello | Enable RTD capital savings (2%) & COS (4%) Develop (w/PLT) F11X & RTD MT/FSE (3rd party) resource model - as MTs attrit backfill with 3rd party Commodities Performance Metrics: -Zero Bin = <1.5% -High Risk Days of Inventory = <1.7% -Customer Wait Time SLA = >96% -FOAK BOM Fill Rate = >95% Tool Availability Metrics: -IQ PAS -SDD/RDD gaps do not impact CND Quality Performance: -Fail on install = <0.20% -80% MQIs closed in < 9 months and no repeat MQIs | 2 | 2 | Savings: Capital Target: 2% ($2M) Current Status: $73.36K Major Projects Completed: Optane ADDC for TZS591 Eval: $53.36K TEL GTV581 Shipping Charge: $20K Major Projects In Progress: Various Price Negotiations ongoing for the $32M Capital Spends including eval tools for TD/LVM COS Target: 4% ($1.04M) Current Status: $550K Major Projects Completed Q1: EPI Wafer price reduction: $50K Virgin Test Wafer Price reduction: $100K Photo OPD4262 Tote Packaging Conversion: $400K Major Projects In Progress: PVD Target Price Reductions: $600K Several G&C Direct/Alternate Source Qual Opportunities being pursued in RTD/NMDM O-ring Direct/Alternate Source Projects LAM Commit to Source | 2021-02-11 | [6 empty] | Commodities Performance Metrics: -Zero Bin = <1.5% -High Risk Days of Inventory = <1.7% -Customer Wait Time SLA = >96% -FOAK BOM Fill Rate = >95% Tool Availability Metrics: -IQ PAS -SDD/RDD gaps do not impact CND Quality Performance: -Fail on install = <0.20% -80% MQIs closed in < 9 months and no repeat MQIs | [7 empty] | Commodities Performance Metrics: -Zero Bin = <1.5% -High Risk Days of Inventory = <1.7% -Customer Wait Time SLA = >96% -FOAK BOM Fill Rate = >95% Tool Availability Metrics: -IQ PAS -SDD/RDD gaps do not impact CND Quality Performance: -Fail on install = <0.20% -80% MQIs closed in < 9 months and no repeat MQIs | [7 empty] | Commodities Performance Metrics: -Zero Bin = <1.5% -High Risk Days of Inventory = <1.7% -Customer Wait Time SLA = >96% -FOAK BOM Fill Rate = >95% Tool Availability Metrics: -IQ PAS -SDD/RDD gaps do not impact CND Quality Performance: -Fail on install = <0.20% -80% MQIs closed in < 9 months and no repeat MQIs
Note on A3: Marria, Mona: Roll these up IOG
Note on Q11: Marria, Mona: Refine for chems/gases/soares

## Optane TD Staff Goals
Owner | Department | Current vs. Old | Staff Sponsor | Q1'21 Goals | Q2'21 Goals | Q3'21 Goals | Q4'21 Goals
Narahari Ramanuja | Optane Process Development | Current IMBO | Ted Taylor | Build dedicated Architecture and Pilot development teams to support 24x7 TD + Ramp. (a) 100% Leaders in place, (b) fill critical gaps, and (c) TD AM’s and ATF PE freed up from S26A. >90% of ATF spider steps are L2 PRI complete. Close ATF TD staffing gaps | >95% of steps at PRI L3 for ATF spider 1D. (MTS + 24x7 OPS + Line Control). 2) 24x7 team takes over 100% of P3 + P2 ATF steps. 3) Finalize ATF ambient strategy and decision on integrated tool as ATF intercept. | >95% of steps at PRI L3 for ATF Array 2D. (MTS + 24x7 + Line Control) Finish hiring and close 24x7 shift engineering gaps. Demonstrate Architecture elements with early Si work needed for BWF startup in 2022 Q1. | Hit PLS criteria. (a)>95% of steps at PRI L4 for ATF Array 2D, (b) Enable >30% PG4 yield on 2D ATF, and (c) Capacity in place to run ATF line at goal.
Chuck Dennison | Optane Process Integration | Current IMBO | Ted Taylor | 1) Sucessfully roll out and communicate across x-fucnt teams new PI Org structure to increase support to ATF. 2) Finalize criteria and primary owernship for PLS-C (CMOS), PLS (2D), PLS (4D extension) 3) Start reporting out status to glidepath for ATF PLS-C / PLS on monthly cadence with select access for viewing (similar to CMOS dashboard) 4) Open reqs and initiate recruiting for all reqs open in Q1/Q2 | 1) Review new PI org structure in terms of A) effectiveness toward achieiven ATF goals B) empowerment/motivation of ATF/S26A PI team C) x-funct. cooperation and make adjustments as appropriate 2) Finalize LVM criteria (Path to PRQ is required vs. actual PRQ achievement) 3) Incorporate output from Analytics RIHV Analytics for more effective ATF yield segmentation and faster feedback to process/PI 4) Prioritize hiring/recruting on open req's with closure on critical gaps. 5)Incorporate weekly metrics to PLS glidepath into ATF CMOS/Array weekly program meetings. 6) Align on ATF sample plan between multiple x-functional teams | 1) Primary goal is to have all required elements of ATF PLS/PRQ glidepaths on track and prioritize resources to meet drive-to dates. Call out all gaps and propose plan to close. 2) On track for hiring on all available reqs 3) Finalize execution of early ATF sample plan 4) ATF Yield Technical capability goal (TBD) - jointly owned by yield/cell/analytics teams | 1) ATF PLS (2D) achievement 2) On glidepath schedule for ATF PRQ achievement 3) Execute on ATF sample plan
Tash Anestos | Optane Business Operations | Current IMBO | Ted Taylor | 1) Partner w/F11X to support LRP Mfg Affordability: Identify opportunities to enable $4k CPW at 4k wspw by Q4-2024, with assumptions and owners identified (for TD items). 2) Materials Introduction: Process established w/success indicators, PD trained and process tested | 1) Partner w/F11X to support LRP Mfg Affordability: Identify opportunities to pull-in $4k CPW at 4k wspw by Q1-2024 (for Q3'21 LRP cycle), identify clear roadmap with assumptions and owners identified (for TD items). 2) Materials Introduction: Success measured and gaps closed to success indicators, process executing efficiently, PD customers satisfied (feedback survey) | 1) ATF HVM Transfer: Define transfer methodology | 1) DPOR'22 plan that meets Q3'21 LRP spend 2) ATF HVM Transfer: Define R&Rs and plan for 2022 HVM transfer
Todd Lukanc | Optane Tape out/ Mask Operations | Current IMBO | Ted Taylor | 1) Generate and deliver masks at or ahead of agreed upon fab need dates 2) Provide review coordinates and verify with Litho mask meets or exceed quality specs 3) Co-design and build test masks to support next node process development 4) Support sister NAND team GEN / OPC / TO functions as needed | 1) Generate and deliver masks at or ahead of agreed upon fab need dates, review and verify masks meet or exceed quality specs within 4 weeks of wafer printing 2) Enhance OPC solutions to match Litho / module patternign updates - new models within 8 weeks of data collection, build new masks to agreed upon FNDs 3) Support sister NAND team GEN / OPC / TO functions as needed 4)Establish full set of skills needed and plan to cross train for fully independant GEN / OPC / TO team by 2022 post NAND / Optane split | 1) Generate and deliver masks at or ahead of agreed upon fab need dates, review and verify masks meet or exceed quality specs within 4 weeks of wafer printing 2) Enhance OPC solutions to match Litho / module patternign updates - new models within 8 weeks of data collection, build new masks to agreed upon FNDs 3) Co-design and start to finalize BWF Spider mask specs and methods to make masks 4) Support sister team and Implement skills training across team to ensure fully independant Optane GEN / OPC / TO team by 2022 | 1) Generate and deliver masks at or ahead of agreed upon fab need dates, review and verify masks meet or exceed quality specs within 4 weeks of wafer printing - supporting BWF Spider mask set 2) Enhance OPC solutions to match Litho / module patternign updates - new models within 8 weeks of data collection, build new masks to agreed upon FNDs 3) Support sister team and Implement skills training across team to ensure fully independant Optane GEN / OPC / TO team by 2022
Derchang Kau | Optane Pathfinding | Current IMBO | Al Fazio | Pathfinding matrix organization iMBO alignment complete | HC +1 (Critical hire) | 1. MBA: 2bit/tile access silicon feasible on paper and exploration plan ratified 2. Establish roadmap intercept to reduce/eliminate Seasoning and C-cell invocation? | 100% HC (+4) IPM/ADM ?
Kiran Pangal | Optane Media Architecture | Current IMBO | Al Fazio | 1) S25D/S26A: a) S25D Component Qual b) ADS Line released 2) ATF: 1D Spider >10% PG4 Structure Yield Demo Periphery Test for 1st Si >75% Quality and Full Coverage 3) Pathfinding: a) Rev-2 MLC Algo for DE path-finding b) 15% SLC Energy Risk assessment c) Rev-2 BWF IO/PHY/Package aligned path for Tester Definition d) Tile arch defined | 1) S25D/S26A: a) S25D in BPS Qual b) F11X PG1 Demo c) CR9.31 Media Qual d) PG4 Yield E4 impact<1% 2) ATF: a) ATF 2D Si with Structural yield demo b) Array test for 1st Si >75% Quality and Full coverage 3) PF: a) Rev-2 BWF Cspec and Policy and consistent Controller strategy with closure on IO/PHY/Package b) Partition arch and 2kX4k feasibility | 1) ATF: a) ATF 2D PG4 Si yield demo by ww30 and >5% by ww39. b) ATF 4D PG4 structural yield c) ES0 Test Quality >90% and Full coverage d) Meet ATF Component ES0 e) Meet ATF in CPS PO and ADS PO Exit 2) PF: a) Rev-1 BWF CSpec and Policy and consistent Controller IAS0.x b) CMOS/Ckt reliability assessment for 2kx4k | 1) S25D/S26A: a) S26A/S25D in CPS Qual b) S25D MMG-based Media Qual 2) ATF: a) ATF PLS achievement (demo 2D ES1/PG4 30%, etc.): ATF 4D PG4 yield demo b) ES1 Test Quality >90% and Full Coverage c) Test for manufacturability >75% criteria met d) On track for ATF in CPS and ATF in ADS ES0 in Q1’22 3) PF: Rev0.0 BWF CSpec and Policy including architecture and technology and consistent Controller IAS0.y

## Instructions
Instructions to Update MBO's
1) Update the Status Column
|  | Status | Entry Value | Definition
|  | 0 | 0 | Not started or canceled.
|  | 1 | 1 | Forecast to not meet goal by end of quarter. Add reason, impact and mitigation plan to comments.
|  | 2 | 2 | Goal at risk. Note recovery plan in comments.
|  | 3 | 3 | Forecast to meet goal by end of quarter. Add status to comments.
2) Update the Trend Column
|  | Trend | Entry Value | Definition
|  | -1 | 1 | Status is trending worse vs. previous 'Review Date'
|  | 0 | 2 | Status is trending equal to previous 'Review Date'
|  | 1 | 3 | Status is trending improved vs. previous 'Review Date'
3) Update the iMBO columns
| Mid Quarter Updates | Status (mid qtr) | See point 1
|  | Trend (mid qtr) | See point 2
|  | Q1 Mid Quarter Comments | Cut and paste your MBO text to this column and provide update for each point with Prefix 'Actuals'. Color code your commments to match the stop lights listed above (green, yellow, red)
|  | Date of Update (mid qtr) | Date when you make your Mid Quarter Update
| End of Quarter Updates | Status (EOQ) | See point 1
|  | Trend (EOQ) | See point 2
|  | Comments (Q1 EOQ) | Cut and paste your MBO text to this column and provide update for each point with Prefix 'Actuals'. Color code your commments to match the stop lights listed above (green, yellow, red)
|  | Date of Review (EOQ) | DO NOT Fill this - iMBO Mgr will fill with date of review meeting
MBO Management Details
Levels
|  | Tab = 'Optane TD Org Goals' | are all Optane TD goals. Technology goals from this tab are rolled up to IOG level
|  | Tab = 'Optane TD Staff Goals' | are TD Staff goals and have to be updated by TD Staff.
|  | Department Goals | Each staff will have their own Department Level Goals and their own goal sheet which they will manage.
|  | IOG Level iMBOs: | 2021 IOG iMBO Tracking Document.xlsx (sharepoint.com)
Frequency based on 13 week quarter
|  | IOG Level iMBOs: | Each IOG Staff Member identifies their top 3-4 critical deliverables for each quarter, add to tracking sheet with success measure. | Technology goals
At mid-quarter, each IOG Staff Member scores the deliverables and adds an update comment
TA tallies mid quarter scoring and organizes Staff report out at mid-quarter
At end of quarter, each IOG Staff Member scores the deliverbles and adds an update comment
TA tallies end of quarter scoring and organizes Staff report out at end of quarter
|  | Optane TD Org goals | week 6-7 | 1) mid-quarter status, 2) finalize next Qtr
|  |  | week 12-13 | 1) end of quarter status, 2) assure next quarter MBO is updated, 3) Assure 4 Qtrs of MBOs
|  | Optane TD Staff goals | week 1-2 | 1) end of quarter MBO status, 2) next quarter MBO in forums listed below
|  |  | week 7-9 | 1) mid-quarter status, completed offline after MBO's are updated (NO FORMAL REVIEW IN ANY MEETING)
Miscellaneous Administration
Make a snapshot of each IMBO at least every 2 months (add a row for each IMBO to show a history of each IMBO) This was Ted's request (Optane no included)
Make a monthly copy of the IMBO file and put it in the Archive folder

## Calendar and Process
Mid quarter | Email/Task reminder for all owners
End of Quarter Reviews | 3 meetings - - Tech + Cost + People - Operations + FEB + SGs - Use 1 staff meeting to review TD staff goals | With Staff Sponsors
Ted/Al Staff | Staff Sponsor to report out |  |  | Q1 |  | Q2 |  | Q3 |  | Q4
|  |  |  | Mid quarter | End of Quarter | Mid quarter | End of Quarter | Mid quarter | End of Quarter | Mid quarter | End of Quarter
Pillar | Category | Staff Sponsor | Owner | WW07 | WW14/15 | WW20 | WW27/28 | WW33 | WW40/41 | WW46 | WW02/03 - 2022
Technology | S26A | Narahari Ramanuja | Sarah Williams / Bharat K. | [8 empty] | IOG 2021 iMBO Due Dates
| ATF | Chuck Dennison | Darren DeNardis / Veera Dandu | [8 empty] | Quarter | Mid-Qtr Check | End of Qtr
| Optane CMOS | Chuck Dennison | Erv Hill/ Summer Hollingsworth | [8 empty] | Q1 | WW07 Feb 12 | WW14 Mar 29
| Pathfinding | Derchang Kau | Max Hineman / Frank Goodwin | [8 empty] | Q2 | WW20 May 14 | WW27 June 28
[12 empty] | Q3 | WW33 Aug 13 | WW40 Sept 28
Cost | Technology Cost | Narahari Ramanuja | Veera / Darren / Summer / Erv / Sarah / Bharat / Zach | [8 empty] | Q4 | WW46 Nov 12 | WW02 Jan 6, 2022
| Capital | Tash Anestos | James DeForrest / Matthew Smith
| OPEX | Tash Anestos | Jill Staveley/ Cristina Whitely-North
People | Staffing & Retention | Tash Anestos | Roy Jacques / Gina Gutierrez
| Org Capab | Tash Anestos | Rod Spaulding/ Randy Hancock
| Culture and OD | Ted Taylor | PLT/ Gina Guetierrez
Operations | Cycle Time | Tash Anestos | Chris Charrlin / Young Spaulding
| Availability Efficiency (AE) & Output Effic.(OE) | Narahari Ramanuja | Chris Charrlin / Young Spaulding
| Fab and Lab Capacity | Tash Anestos | Young Spaulding/ Gavin Corcoran
FEB | FEB | Chuck Dennison | Tiffany/Chris/Erv/Summer
Support Groups | TIQ | Narahari Ramanuja | Randy Hawkins/EPCOT
| NSG Automation | Tash Anestos | Harmanjit Katoch
| Supply Chain Operations | Tash Anestos | Kristina Torsiello
TD Staff Goals | All departments | Ted/Al | TD Staff
Note on A7: Marria, Mona: Roll these up IOG