## Template
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
Actionable, |  | Specific | [5 empty] | Yes
Significant |  | Measurable | [5 empty] | No
Concete |  | Attainable | [5 empty] | Simple
Inspirational |  | Relevant
Time-bound
1 | FTE.1: Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | 1 | A winning High Capacity Cache strategy |  | FTiP, FTiD |  | Andy, Dany, Klaus, (team Kingsley) | 1 | Technology selection based on density and process capability | 2022-04-29 | Q2
[8 empty] | 2 | SRAM process flow and cell construct with patterning count on par of better than N6 1P9M | 2022-07-01 | Q2
[8 empty] | 3 | Array defined and density meeting requirement (within 10% of N2) | 2022-09-30 | Q3
[8 empty] | 4 | Down select based on PPA assessment | 2022-12-30 | Q4
|  | 2 | A winning N2 companion chip strategy |  | FTiP, FTiD |  | Klaus, Long, Stephen, Dany | 1 | Identify top 3 external technology candidates and companion chip function for N2 compute tile | 2022-07-01 | Q2
[8 empty] | 2 | Establish Technology capability meeting signal integrity and power delivery success criteria (pre UCIe spec) | 2022-09-30 | Q3
[8 empty] | 3 | Silicon Validation Plan in place | 2022-12-30 | Q4
|  | 3 | N2 "Design collateral" exceeds Supplier's baseline capability |  | FTiP, FTiD |  | Angada, Atul, Wenjie, Hank | 1 | Methodology in place | 2022-04-15 | Q2
[8 empty] | 2 | N2 Logic L1 PPA delivered and meet paper target | 2022-07-01 | Q2
[8 empty] | 3 | N2 Logic L2 PPA delivered and meet paper target | 2022-09-30 | Q3
[8 empty] | 4 | 5% PPA improvement demonstrated | 2022-12-30 | Q4
|  | 4 | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics |  | FTiP, EPAE |  | Max, Jason, Hank, Angada | 1 | Module Level KPI delivered | 2022-04-15 | Q2
[8 empty] | 2 | Flow Integration (Inter Module) KPI delivered | 2022-07-01 | Q2
[8 empty] | 3 | Common metric based DTCO methodology established | 2022-09-30 | Q3
[8 empty] | 4 | Paper based L2 metric quantification capability validated | 2022-12-30 | Q4
2 | FTE.2: Meet or exceed Intel’s external capacity demand roadmap | 1 | Establish ADM base die dual drive for 2023-2025 NTI intercept | Integrated and Discrete Graphics Owners and Architects | FTE |  | Mike, Max | 1 | Technology selected and landing zone defined for Dual-Drive | 2022-04-28 | Q2
[8 empty] | 2 | Die Size and Process Cost at 95% confidence for NPI decision for 2023 Tapein intercept | 2022-07-01 | Q2
[8 empty] | 3 | Die Size and Process Cost at 95% confidence for NPI decision for 2024 Tape in intercept | 2022-12-30 | Q3
3 | FTE.4 Build a world class GEMS team with BIC talent, culture, systems & processes | 1 | Meeting Plan'22 HC goal (6HC) |  | FTE |  | Angada | 1 | one Physical Design Engineer and one Memory technologies | 2022-04-29 | Q2
[8 empty] | 2 | Prashant and Peihua back fill | 2022-07-01 | Q2
[8 empty] | 3 | Two TCAD/Model Engineer | 2022-09-02 | Q3
[8 empty] | 4 | Jeff back fill | 2022-12-30 | Q4
|  | 2 | Incubate technical pipe line by collaborating with research institutes |  | FTE |  | Max, Per, Angada, Prashant | 1 | Sponsor one University Research Project on 3DIC characterization methodology and benchmark | 2022-07-01 | Q2
[8 empty] | 2 | Establish one captive research in STCO with world leaders in research consortia | 2022-09-02 | Q3

## 2022 Tech Pathfinding iMBO
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Customer | Stakeholder | Sponsor | Critical Path (Interim Milestone or Sub Goal) |  |  |  | Key Results
[5 empty] | # | Milestone | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
1 | A winning High Capacity Cache strategy and Technology | CCG -- Bob Royer DEG (DCG) -- ? | Chee How Lim Changhong Dai | DerChang Kau Kingsley Lai | 1 | Paper Based Technology Selected (HD, HC, HS, RF) |  |  | 1
2
[5 empty] | 2 | Test chip Tapeout |  |  | 1
2
[5 empty] | 3 | Down Select Technology |  |  | 1
2
[5 empty] | 4 | Lead Product POR |  |  | 1 |  | 2023-03-31
2
2 | 2nm Mockup demonstrate 1.3X performance and denensity scaling of 3nm node | Srini Rajagopolan | Chee How Lim | DerChang Kau | 1 | MTS, DTS, Design Rules |  |  | 1
[5 empty] | 2 | L0/L1 PPA meet success criteria |  |  | 2
[5 empty] | 3 | L2 PPA meeting success criteria |  |  | 3 |  | 2022-12-31
3 | DTCO | Andy Wei | Srini Rajagopolan | DerChang Kau | 1 | Scalable Device Model |  |  | 1
[5 empty] | 2 | L1 PPA on design and technology options |  |  | 2
[5 empty] | 3 | L2 PPA for DTCO |  |  | 3 |  | 2022-10-31
4 | 3DIC… |  |  |  | 1 |  |  |  | 1
[5 empty] | 2 |  |  |  | 2
[5 empty] | 3 |  |  |  | 3 |  | 2022-12-31

## Sheet1
Category | Topic | Leads | Tentative Date
3DIC | PoC of Logic-on-Logic, HBI, PDN and test Chip | Per/Long | Mid Q2
| STCO initiative with IMEC and industrial leaders | Per | End Q2
| 3DIC Cookbook Ingredient Chapter Review | Max/Jason | WW16
4LPP Pathfinding | Test Chip OSIR | Po-yao/Fangxing | WW15
| Test Chip Database Q2 pulsing (Shuttle T/I: end of Aug) | Po-yao/Fangxing | June (WW24?)
SRAM Disagg. | SRAM Cell Level Metric: Methodology and Metrology | Dany | WW19
| SRAM Array level Metric | Dany | WW23
| SRAM 3C KPI and benchmark N6, N4, N3E, 4LPP | Klaus/Andy | WW27
| System integration strategy and decision process | Klaus/Andy | May
| High Capacity Cache Strategy and Selection for N3E/N2 | Klaus/Andy | WW27 in N2 WG
| ADM Dual Drive / BU engagement learning | DerChang/Mike | WW18
PF General | Beyond N2 | Andy/Srini/Klaus | June (WW26?)
| Blockchain and challenge in Design and Technology | Srini | WW21
N2 Pathfinding in N2 WG (Srini to coordinate) | L1 PPA methodology and automation | Angada | WW16 in N2 WG
| N5/N7 DR vs. physical calibration for N2 parasitics projection | Andy | May
| High Capacity Cache Strategy and Selection for N3E/N2 | Klaus/Andy | June
| N3E silicon vs. sim | Ning/Atul | W20
| Cell Library, custom ip? | ? Srini | June
| I/O, Power Management, Analogy strategy for N2/SiP | Long/Per/Andy | June
Agenda Horizon:
WW23 – Mike on Foundry Technologies Competitive Analytics and FTE dual drive response
WW24 – Dany, Jiajing and Ping on Disagg. High Capacity Cache PoC, expectation and DOE on TSMC and SF shuttle plan
WW25 – Angada and Wenjie on Standard cell design automation (SLiC) learning and next step
WW26 – Poyao and Fangxing on First Creek midpoint pulsing
Other topic in preparation (Q3 Agenda)
N2 Technology Mock: Design Rule and Cost, Cost of transition N3E (Andy, Klaus)
N2 L2 PPA (Angada)
HCC: Spec (electrical and Physical), expected learning and decision path (Dany, Jiajing and Ping)
Memory Disaggregation Strategy (Memory architects from CCG/DCAI/AXG)
Packaging-product roadmap co-development: PLC methodology with a focus on pathfinding (Jason, Max)
De-Cap survey: Design and Technology vs. Super-MiM (Per, Long and Hank)
Power management disaggregation: eco system and trend (Mike and Don Nguyen)
First Creek TO post mortem (Poyao and Fungxing)
HBI: 3DIC PoC TO pulsing (Per)

## Sheet2
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
1 | FTE.1: Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | 1 | A winning High Capacity Cache strategy |  | FTiP, FTiD |  | Andy, Dany, Klaus, (team Kingsley) | 1 | Technology selection based on density and process capability | 2022-04-29 | Q2
[8 empty] | 2 | SRAM process flow and cell construct with patterning count on par of better than N6 1P9M | 2022-07-01 | Q2
[8 empty] | 3 | Array defined and density meeting requirement (within 10% of N2) | 2022-09-30 | Q3
[8 empty] | 4 | Down select based on PPA assessment | 2022-12-30 | Q4
|  | 2 | A winning N2 companion chip strategy |  | FTiP, FTiD |  | Klaus, Long, Stephen, Dany | 1 | Identify top 3 external technology candidates and companion chip function for N2 compute tile | 2022-07-01 | Q2
[8 empty] | 2 | Establish Technology capability meeting signal integrity and power delivery success criteria (pre UCIe spec) | 2022-09-30 | Q3
[8 empty] | 3 | Silicon Validation Plan in place | 2022-12-30 | Q4
|  | 3 | N2 "Design collateral" exceeds Supplier's baseline capability |  | FTiP, FTiD |  | Angada, Atul, Wenjie, Hank | 1 | Methodology in place | 2022-04-15 | Q2
[8 empty] | 2 | N2 Logic L1 PPA delivered and meet paper target | 2022-07-01 | Q2
[8 empty] | 3 | N2 Logic L2 PPA delivered and meet paper target | 2022-09-30 | Q3
[8 empty] | 4 | 5% PPA improvement demonstrated | 2022-12-30 | Q4
|  | 4 | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics |  | FTiP, EPAE |  | Max, Hanwen, Jason, Hank, Angada | 1 | Module Level KPI delivered | 2022-04-15 | Q2
[8 empty] | 2 | Flow Integration (Inter Module) KPI delivered | 2022-07-01 | Q2
[8 empty] | 3 | Common metric based DTCO methodology established | 2022-09-30 | Q3
[8 empty] | 4 | Paper based L2 metric quantification capability validated | 2022-12-30 | Q4
2 | FTE.2: Meet or exceed Intel’s external capacity demand roadmap | 1 | Establish ADM base die dual drive for 2023-2025 NTI intercept | Integrated and Discrete Graphics Owners and Architects | FTE |  | Mike, Max | 1 | Technology selected and landing zone defined for Dual-Drive | 2022-04-28 | Q2
[8 empty] | 2 | Die Size and Process Cost at 95% confidence for NPI decision for 2023 Tapein intercept | 2022-07-01 | Q2
[8 empty] | 3 | Die Size and Process Cost at 95% confidence for NPI decision for 2024 Tape in intercept | 2022-12-30 | Q3
3 | FTE.4 Build a world class GEMS team with BIC talent, culture, systems & processes | 1 | Meeting Plan'22 HC goal (6HC) |  | FTE |  | Angada | 1 | one Physical Design Engineer and one Memory technologies | 2022-04-29 | Q2
[8 empty] | 2 | Prashant and Peihua back fill | 2022-07-01 | Q2
[8 empty] | 3 | Two TCAD/Model Engineer | 2022-09-02 | Q3
[8 empty] | 4 | Jeff back fill | 2022-12-30 | Q4
|  | 2 | Incubate technical pipe line by collaborating with research institutes |  | FTE |  | Max, Per, Angada, Prashant | 1 | Sponsor one University Research Project on 3DIC characterization methodology and benchmark | 2022-07-01 | Q2
[8 empty] | 2 | Establish one captive research in STCO with world leaders in research consortia | 2022-09-02 | Q3