## 2022.OKRs
| FTE ID | Workstream Objective | WS | Owner | ww25.1 | Status | % Done | Q | Key Result | Comments
GEMS.1.1 | FTE.1 | FTE Objective Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | *FTE* | *FTE* |  |  |  | Q2 | KR1: Align and Close on Client PTL/Server CWF Dual Drive Direction in PC KR2: Establish & Document Dual Drive Framework in UPLC Q2 Release | 80% 80%
GEMS.1.1 | FTE.1 | FTE Objective Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | *FTE* | *FTE* |  |  |  | Q1 | KR1: Recommend N3E Intercept for Client PTL for '25 PRQ at GEMS/DEG Level KR2: Propose Dual Drive Framework to CPG/DEG Staff KR3: Complete PPA assessment of N3E v0.5 vs N3 v1.0 KR4: Initiate regular N2 meeting with TSMC, and start PPA assessment | 100% 100% 80% 40%
GEMS.1.1 | GEMS.1.1 | GEMS Objective Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | *GEMS* | *GEMS* |  |  |  |  | Deliver 3CRM refresh and align with DEG/BU for Server and Client product roadmap in compliance with the GLADIUS framework/New Development Model (Quarterly cadence). - TY/CD/Jerry
GEMS.1.1 | ETPP.1 | Recommend Platform Options for Key Products for '24-25 PRQ | ETPP | Chee How | Updated | On Track | 80% | Q2 | KR2: Align and Close on Client PTL/Server CWF Dual Drive Direction in PC | Proposed PTL S/H compute on N3E, but CCG roadmap changes still volatile. CWF trending 1276.4 as continuation from SRF (ability to influence is limited).
GEMS.1.1 | ETPP.2 | Define Si/IP/Pkg Portfolio and TCs to demonstrate Technology Platforms | ETPP | Chee How | Updated | On Track | 70% | Q2 | KR2: Finalize Content for Testchip (NVL/COR) for Execution with FTE Staff | Phased Testchip Plans reviewed in ETPP-CM to enable product roadmap options, but alignment is not closed yet.
GEMS.1.1 | ETPP.1 | Recommend Platform Options for Key Products for '24-25 PRQ | ETPP | Chee How | Updated | DONE | 100% | Q1 | KR1: Recommend N3E Intercept for Client PTL for '25 PRQ at GEMS/DEG Level
GEMS.1.1 | ETPP.4 | Deliver Quarterly Reports on Advanced Technology Capability & Cost | ETPP | Chee How | Updated | On Track | 80% | Q2 | KR1: Publish first Quarterly Report on Leading Edge Silicon, Packaging and Wafer Cost Roadmap | Content is in progress, drafts are being prepared.
GEMS.1.1 | ETPP.1 | Recommend Platform Options for Key Products for '24-25 PRQ | ETPP | Chee How |  |  |  | Q4 | KR3: Align on PTL/CWF Dual Drive Direction in EC
GEMS.1.1 | ETPP.2 | Define Si/IP/Pkg Portfolio and TCs to demonstrate Technology Platforms | ETPP | Chee How | Updated | DONE | 100% | Q1 | KR1: Define N3E Platform Portfolio & Testchip Plan (NVL/COR) with FTE Staff | ETPP-CM review WW14.2
GEMS.1.1 | ETPP.5 | Develop 3DIC Cost Model and Align with Quarterly Roadmap | ETPP | Chee How | Updated | On Track | 80% | Q2 | KR2: Synchronize with Quarterly Roadmap | Model is in progress, drafts are being prepared.
GEMS.1.X | EPAE.4 | Validate 2.3D technology for Cost Sensitive HPC applications | EPAE | Thomas | Updated | On Track | 30% | Q3 | KR1: Finalize BLRT in Q3'22 | Difficulties seen, Project not yet behind, but depending on root cause finding for cracks in the package middle
GEMS.1.1 | ETPP.2 | Define Si/IP/Pkg Portfolio and TCs to demonstrate Technology Platforms | ETPP | Chee How |  |  |  | Q4 | KR4: Establish Long-Term Testchip Framework at GEMS Level
GEMS.1.1 | ETPP.6 | Develop 3DIC Capability Roadmap and Align with Quarterly Roadmap | ETPP | Chee How | Updated | On Track | 80% | Q2 | KR2: Synchronize with Quarterly Roadmap | Content is in progress, drafts are being prepared.
GEMS.1.1 | ETPP.5 | Develop 3DIC Cost Model and Align with Quarterly Roadmap | ETPP | Chee How | Updated | DONE | 100% | Q1 | KR1: Propose & Review Initial 3DIC Cost Model with FTE Staff | ETPP-CM review WW14.2
GEMS.1.1 | ETPP.6 | Develop 3DIC Capability Roadmap and Align with Quarterly Roadmap | ETPP | Chee How | Updated | DONE | 100% | Q1 | KR1: Propose & Review Initial 3DIC Capability Roadmap with FTE Staff | Pending Thomas' response
GEMS.1.1 | FTiP.1 | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics | FTiP | DerChang | Updated | DONE | 95% | Q1 | KR1: Module Level KPI delivered | Final Peer Review planned WW16.2 (Tawian holiday in WW15) ; road-show demo to be followed in WW16/17
GEMS.1.1 | FTiP.1 | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics | FTiP | DerChang | Updated | DONE | 100% | Q2 | KR2: Flow Integration (Inter Module) KPI delivered | Prioritization on key pathfinding enabling projects (FO-EB-T on CCG and AxG);
GEMS.1.1 | FTiP.1R | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics | FTiP | DerChang | Updated | ZBB |  |  | KR3: DTCO methodology established (Q3) | 3DIC KR need to be changed pending on FO-EB-T engagment with CCG and DCG and product roadmap alignment with SPIL
GEMS.1.1 | FTiP.1R | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics | FTiP | DerChang | Updated | ZBB |  |  | KR4: Paper based L2 metric quantification capability validated (Q4)
GEMS.1.2 | FTiP.2 | Predictive DTCO for logic, SRAM exploration (GAA) and optimization (N3) | FTiP | DerChang | Updated | DONE | 90% | Q1 | KR1: Complete definition of DTCO methodology | tracking to WW15 vs. ECD WW16. Including 1) LPE, 2) compact model and 3) demonstration of L1PPA
GEMS.1.2 | FTiP.2 | Predictive DTCO for logic, SRAM exploration (GAA) and optimization (N3) | FTiP | DerChang | Updated | Behind | 50% | Q2 | KR2: L1 PPA capability demonstrated | Restructured with Technology Architecture WG. Revised Mockup methodology;
GEMS.1.2 | FTiP.2R | Predictive DTCO for logic, SRAM exploration (GAA) and optimization (N3) | FTiP |  | Updated | ZBB |  |  | KR3: L2 PPA capability demonstrated (Q3) | DTCO okr revision needed; Focus on N2 Mockup to prepared for N2 engagement in 2023
GEMS.1.2 | FTiP.2R | Predictive DTCO for logic, SRAM exploration (GAA) and optimization (N3) | FTiP |  | Updated | ZBB |  |  | KR4: 5% PPA demonstrated with N3 Process and Layout change (Q4)
| FTiP.2 | N2 Mockup demonstrate performance and density scaling | FTiP | DerChang | Updated | On Track | 25% | Q3 | KR3: Scaling options and process flow as manifested in MTS, DTS and Design Rules
| FTiP.2 | N2 Mockup demonstrate performance and density scaling | FTiP | DerChang |  |  |  | Q3 | KR4: L0/L1 PPAC meet success Criteria
| FTiP.2 | N2 Mockup demonstrate performance and density scaling | FTiP | DerChang |  |  |  | Q4 | KR5: Scaling options and process flow as manifested in design collaterals
| FTiP.2 | N2 Mockup demonstrate performance and density scaling | FTiP | DerChang |  |  |  | Q4 | KR6: All viable options run through L1 metric and compared to N3E baseline
| FTiP.2 | N2 Mockup demonstrate performance and density scaling | FTiP | DerChang |  |  |  | Q4 | KR7: Top 2 viable options run through L2 metric and compared to N3E baseline
GEMS.1.2 | FTiP.3 | Create a Cache Memory Disaggregation Strategy | FTiP | DerChang | Updated | DONE | 100% | Q1 | KR1: GAA based SRAM process flow and cell construct | Instead of pending N2 engagement, High Capacity Cache disagg. strategy estalbished based on ranking of $/bit.
| FTiP.3 | Create a Cache Memory Disaggregation Strategy | FTiP | DerChang | Updated | DONE | 100% | Q2 | KR2: Array design complete and density optimized
GEMS.1.2 | FTiP.3R | Create a Cache Memory Disaggregation Strategy | FTiP |  | Updated | On Track | 75% | Q4 | KR3: Down select based on PPA assessment
| FTiP.3 | A winning High Capacity Cache strategy and Technology | FTiP | DerChang | Updated | On Track | 75% | Q3 | KR3: Technology and Array Configurations identified that meet L3 cache PPAC requirements
| FTiP.3 | A winning High Capacity Cache strategy and Technology | FTiP | DerChang |  |  |  | Q4 | KR4: 2 disagg. SRAM Test Chip Tapeout
| FTiP.3 | A winning High Capacity Cache strategy and Technology | FTiP | DerChang |  |  |  | Q1'23 | KR5: Si validation of disagg. L3 cache
GEMS.1.2 | FTiP.4 | Create MRAM LLC Optionality | FTiP | DerChang | Updated | DONE | 100% | Q2 | KR1: MRAM viability based on Best In Class STTM publication | Collab with IOG design team; no reliable MRAM capable for "data" application. Project ZBB.
GEMS.1.2 | FTiP.4R | Create MRAM LLC Optionality | FTiP |  | Updated | ZBB |  |  | KR2: Array design complete and density optimized (Q3) | MRAM Close in Q2; Pathfinding effort should be on test chip for Oct (N6) and Dec (4LPP) tapeout and Product roadmap intercept meeting success indicator in 1h'23
GEMS.1.2 | FTiP.4R | Create MRAM LLC Optionality | FTiP |  | Updated | ZBB |  |  | KR3: Down select based on PPA assessment (Q4)
GEMS.2.2 | EPAE.1 | Enable CCG MTL PCH-S Multi-sourcing at OSAT (PTI &ASE) | EPAE | Thomas | Updated | On Track | 20% | Q3 | KR2: Achieve GRC qual for pipecleaner
GEMS.1.X | EPAE.6 | Provide early enabling of 2.3D bridge as a drop in compatible tech to EMIB | EPAE | Thomas | Updated | On Track | 20% | Q3 | KR2: First read out of Phase 1 (mechanical validation of technology) 2Q after kick off estimated in Q3 | Supplier project start after Neg plan
GEMS.1.2 | ETPP.7 | Achieve Corporate Alignment for Dual Drive Strategy | ETPP | Chee How | Updated | On Track | 80% | Q2 | KR2: Establish & Document Dual Drive Framework in UPLC Q2 Release | This appears to be duplicate with Lonn's OKR (on-track). However, the overall dual drive framework at corporate level is facing headwinds for adoption.
GEMS.1.1 | SOI.12 | Enable D2D BIC Standardization on external foundries and Intel and enable path for CXI | SOI | Stephen | Updated | DONE | 100% | Q1 | KR1: Complete D2D landscape technical comparison
GEMS.1.1 | SOI.12 | Enable D2D BIC Standardization on external foundries and Intel and enable path for CXI | SOI | Stephen | Updated | DONE | 100% | Q1 | KR1: Ensure specs aligned with key internal customers for a standardized D2D interface (protocol/signaling) for 2.5D designs
GEMS.1.1 | SOI.12 | Enable D2D BIC Standardization on external foundries and Intel and enable path for CXI | SOI | Stephen | Updated | DONE | 100% | Q1 | KR2: Ensure competitive specs completed for a standardized D2D interface (protocol/signaling) for 2.5D designs
GEMS.1.1 | SOI.12 | Enable D2D BIC Standardization on external foundries and Intel and enable path for CXI | SOI | Stephen |  |  |  | Q4 | KR3: Enable CXi IP on external foundry
GEMS.1.1 | SOI.12 | Enable D2D BIC Standardization on external foundries and Intel and enable path for CXI | SOI | Stephen |  |  |  | Q4 | KR4: Secure commit for die to die UCIe adoption with Foundry and IP partners (assumes sufficient spec progress)
GEMS.1.2 | GEMS.1.2 | GEMS Objective Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | *GEMS* | *GEMS* |  |  |  |  | Complete detailed study and business case analysis for Dual Drive Strategy for N3E and N2 to mitigate revenue risk to facilitate a decision by June’22 - TY/CD/Jerry
GEMS.1.2 | ETPP.7 | Achieve Corporate Alignment for Dual Drive Strategy | ETPP | Chee How | Updated | DONE | 100% | Q1 | KR1: Propose Dual Drive Framework to Key CPG/DEG Staff | Reviewed with multiple DEG staff and CSO members
GEMS.1.2 | FTiD.2 | Develop Automatic PPA data analysis system; deliver PPA for N3E/N2/220A/18A/3GAP | FTiD | Kingsley | Updated | DONE | 100% | Q1 | KR1: Complete PPA assessment of N3E v0.5 vs N3 v1.0
GEMS.1.2 | FTiD.2 | Develop Automatic PPA data analysis system; deliver PPA for N3E/N2/220A/18A/3GAP | FTiD | Kingsley | Updated | NOT DONE | 20% | Q1 | KR2: Enable N2 early engagement with TSMC for initial PPA assessment | tsmc declined intel early access for N2
GEMS.1.1 | ETPP.2 | Define Si/IP/Pkg Portfolio and TCs to demonstrate Technology Platforms | ETPP | Chee How |  |  |  | Q3 | KR3: Define Long-Term Testchip Framework (ZZC/YYC-like), review with FTE Staff
GEMS.1.2 | FTiP.6 | Engage with TSMC on N2 Definition, DTCO/STCO, and TR for best Intel Products | FTiP | Srini | Updated | Behind | 50% | Q2 | KR3: Baseline PPA assessment based on mock N2 libraries
GEMS.1.3 | FTiP.5 | Enable 4LPP/3GAP/N2 technology through Testchips; provide Si data to product teams | FTiP | Srini | Updated | DONE | 80% | Q1 | KR1: bring up a test chip core team and infrastructure
GEMS.1.3 | FTiP.5 | Enable 4LPP/3GAP/N2 technology through Testchips; provide Si data to product teams | FTiP | Srini |  |  |  | Q4 | KR3: Tape out ready by Oct, 2022
GEMS.1.3 | FTiP.5 | Enable 4LPP/3GAP/N2 technology through Testchips; provide Si data to product teams | FTiP | Srini |  |  |  | Q4 | KR4: Start N2 test chip design
GEMS.1.2 | FTiP.8 | Open up alternate sourcing options (dual drive) for volume constrained Intel products | FTiP | Srini | Updated | DONE | 100% | Q2 | KR1. ADP-S at GF HVM ramp decision by ww20.
GEMS.1.2 | FTiP.6 | Engage with TSMC on N2 Definition, DTCO/STCO, and TR for best Intel Products | FTiP | Srini | Updated | NOT DONE | 60% | Q1 | KR1: Initiate regular N2 meeting with TSMC
GEMS.1.2 | FTiP.6 | Engage with TSMC on N2 Definition, DTCO/STCO, and TR for best Intel Products | FTiP | Srini | Updated | NOT DONE | 25% | Q1 | KR2: Define product intercept and technology requirements
GEMS.2.2 | ETPP.3 | Establish 2nd source foundry options for legacy products (>28nm) | ETPP | Chee How |  |  |  | Q3 | KR3: Align on PSG 180eF Sourcing Direction with PSG
GEMS.1.3 | GEMS.1.3 | GEMS Objective Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | *GEMS* | *GEMS* |  |  |  |  | Establish Samsung sourcing strategy to increase influence and develop into a viable sourcing option. - CS/CD
GEMS.1.1 | FTiP.7 | Assess and bring Foundry/OSAT 3DIC technology to Intel products | FTiP | Srini | Updated | DONE | 70% | Q1 | KR1: Quantify power delivery goodness through electrical models
GEMS.3.1 | FTiD.1 | Enable N3B product TOs on time, NPI ramp on schedule, and N3E engagement with TSMC | FTiD | Kingsley | Updated | Behind | 50% | Q3 | KR2: ARL-C A0 TI: ww26-ww30, Secure engineering wafers and cycle time support to meet product needs | ARL-C TO is postponed to ww01-03'23 due to LNC readiness
GEMS.1.1 | FTiP.7 | Assess and bring Foundry/OSAT 3DIC technology to Intel products | FTiP | Srini |  |  |  | Q4 | KR3: TFM for logic on logic 75% ready for BZM
GEMS.1.3 | FTiP.5 | Enable 4LPP/3GAP/N2 technology through Testchips; provide Si data to product teams | FTiP | Srini | Updated | On Track | 75% | Q2 | KR2: Full chip floor plan and block level instantiation
GEMS.1.3 | SOI.11 | Enable CPL IP for Samsung 4LPP | SOI | Stephen | Updated | On Track | 90% | Q2 | KR1: Define CPL IP requirements | LPDDR5X and USB redefinition needed due to N6 process switch
GEMS.1.3 | SOI.11 | Enable CPL IP for Samsung 4LPP | SOI | Stephen | Updated | On Track | 50% | Q2 | KR2: RFQ and vendor selection
GEMS.1.4 | GEMS.1.4 | GEMS Objective Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | *GEMS* | *GEMS* |  |  |  |  | Deliver cost savings of ~$450M 2022-2025 (Q1'22 LRP will provide annualized numbers) through cost savings and cost avoidance projects across all groups (eg: technology/yield cost base improvement, secondary sourcing) - MA/CD/TY/CS/AP
GEMS.1.4 | Finance.1 | Drive $150M Savings Via Value Engineering Programs | Finance | Lamin |  |  |  | Q4 | Kingsley!!
GEMS.1.4 | Finance.1 | Drive $150M Savings Via Value Engineering Programs | Finance | Lamin |  |  |  | Q4 | KR1: Meet or exceed (by at least 10%) yield improvement cost-savings goals on FY2022 focus products
GEMS.1.4 | Finance.1 | Drive $150M Savings Via Value Engineering Programs | Finance | Lamin |  |  |  | Q4 | Rajesh!!
GEMS.1.4 | Finance.1 | Drive $150M Savings Via Value Engineering Programs | Finance | Lamin |  |  |  | Q4 | Srini!!
GEMS.1.4 | Finance.1 | Drive $150M Savings Via Value Engineering Programs | Finance | Lamin |  |  |  | Q4 | Thomas!!
GEMS.1.X | EPAE.3 | Introduce Industry Standard Passivation on Intel Wafers | EPAE | Thomas | Updated | DONE | 100% | Q1 | KR1: Complete Phase2 and deliver samples to Aloha Fab for characterization and stress test (result will set direction for further engagement) | Process window confirmed for flat and topo versions, all wafers sent to AFO for stress test, stresstest RO in Q2 for definition of furhter proceeding
GEMS.4.2 | FTiD.3 | Build a full Std Cell Customization Capability and enable a Memory Customization Capability | FTiD | Kingsley | Updated | On Track | 60% | Q3 | KR2: Build SRAM customization capability covering circuit and mask designs | 3 memory designers on-board in Q2. Continue for another 2 hirings
GEMS.1.X | EPAE.6 | Provide early enabling of 2.3D bridge as a drop in compatible tech to EMIB | EPAE | Thomas | Updated | DONE | 100% | Q1 | KR1: Frame project proposal, define deliverables, planned schedule, biz case and get green light to start engagement Q1'22 | Project apporved Feb 10th, Neg plan released Feb 28th, Negotiation will start in ww11
GEMS.4.2 | FTiD.4 | Enable Design Service Capability for Test chips, 3DIC design flow | FTiD | Kingsley | Updated | On Track | 50% | Q3 | KR1: Support Samsung 4LPP TC planned in Q3'22 KR2: Build 3DIC design flow using BZM3 as a test case
GEMS.2.1 | FTE.2 | FTE Objective Meet or exceed Intel’s external capacity demand roadmap | *FTE* | *FTE* |  |  |  | Q2 | KR1: Achieve process freeze milestone for pipecleaner for MTL PCH-S @ OSAT KR2: Achieve ADPS @ GF risk ramp start in Q2'22 (ww20'22) KR3: Drive baseline yield on ADPS-GF @ PRQ to match D0 roadmap of 83.1% and achieve/demonstrate on engineering wafers. | 125% 100% 70%
GEMS.2.1 | FTE.2 | FTE Objective Meet or exceed Intel’s external capacity demand roadmap | *FTE* | *FTE* |  |  |  | Q1 | KR1: Complete technical assessment and feasibility closure for PSG's Max10 2nd source with GF 55nm EFF and enable business team to proceed with commercial negotiations KR2: Drive first WCS product (GfP2) test readiness @ 3rd OSAT (Sigurd) | 100% 100%
GEMS.2.1 | GEMS.2.1 | GEMS Objective Meet or exceed Intel’s external capacity demand roadmap | *GEMS* | *GEMS* |  |  |  |  | Deliver >10% upside/pull ins to address shortages (Q1'22 goal of >2000 wafers). - CS
GEMS.2.2 | GEMS.2.2 | GEMS Objective Meet or exceed Intel’s external capacity demand roadmap | *GEMS* | *GEMS* |  |  |  |  | Create and ratify a multi-sourcing policy to improve capacity flexibility and BCP. Complete 2nd source substrate qualifications for flexibility (>4 quals by EOQ1) - CS/TY (CD?)
GEMS.2.2 | FTiM.1a | A successful realization of 2nd sourcing ADPS NPI to PRQ @ GF | FTiN | Sourav | Updated | On Track | 30% | Q3 | KR2: Achieve ADPS @ GF PRQ in Q3'22 (WW36-39'22) | PRQ moving to WW36-39 due to CPI issues.
GEMS.2.2 | EPAE.1 | Enable CCG MTL PCH-S Multi-sourcing at OSAT (PTI &ASE) | EPAE | Thomas | Updated | DONE | 100% | Q2 | KR1: Achieve process freeze milestone for pipecleaner for MTL PCH-S @ OSAT | Project on track for certification, process freeze was 2 weeks pushed out due to missing B2B link from SEC to get wafer data; PTI PF granted in ww17, ASE PF granted in ww21'22
GEMS.2.2 | ETPP.3 | Establish 2nd source foundry options for legacy products (>28nm) | ETPP | Chee How | Updated | DONE | 100% | Q1 | KR1: Create & Communicate PSG 65eF RFP to at least 1 Foundry Option | RFQ completed and initiated communication with HHGrace/UMC
GEMS.2.2 | FTiM.1a | A successful realization of 2nd sourcing ADPS NPI to PRQ @ GF | FTiN | Sourav | Updated | On Track | 30% | Q3 | KR4: Drive ADPS-GF @ PRQ to be within 5% across all key perf metrics compared to SF process (stretch goal: meet SF performance)
GEMS.2.2 | ETPP.3 | Establish 2nd source foundry options for legacy products (>28nm) | ETPP | Chee How | Updated | On Track | 90% | Q2 | KR2: Create & Communicate PSG 180eF RFP to at least 1 Foundry Option and Align on PSG 65eF Sourcing Direction with PSG | GEMS exploration and RFP are completed. Alignment with PSG on their direction is pending.
GEMS.2.2 | FTiM.1a | A successful realization of 2nd sourcing ADPS NPI to PRQ @ GF | FTiN | Sourav | Updated | On Track | 70% | Q3 | KR3: Drive baseline yield on ADPS-GF @ PRQ to match D0 roadmap of 83.1% and achieve/demonstrate on engineering wafers. | WW19 Average yield is at 79.4/14wfs but 36/225 wfrs beat 83.1% target. Best wfr is at 84.7% beating target. PRQ pushed out to WW36-39 due to CPI issues.
GEMS.2.3 | TPSE.2 | Enable CCD, PCH, WCS tests at OSATs | FTiN | Sourav |  |  |  | Q3 | KR3: Hayden Bridge (Thunderbolt product family) test capability ready for HVM @ Sigurd, Burnside Bridge (Thunderbolt product family) test capability ready for HVM @ SPIL & ATK
GEMS.2.2 | FTiM.6 | Support technical assessments of multi sourcing external foundry capabilities in strong collaboration with BU and EMS partners | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR1: Complete technical assessment and feasibility closure for PSG's Max10 2nd source with GF 55nm EFF and enable business team to proceed with commercial negotiations
GEMS.2.2 | FTiM.1a | A successful realization of 2nd sourcing ADPS NPI to PRQ @ GF | FTiN | Sourav | Updated | DONE | 125% | Q2 | KR1: Achieve ADPS @ GF risk ramp start in Q2'22 (ww20'22)
GEMS.2.2 | FTiM.6 | Support technical assessments of multi sourcing external foundry capabilities in strong collaboration with BU and EMS partners | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR2: PDK V0.9 delivery for Filmore Peak @ SF 14LPU 2nd source
GEMS.2.2 | FTiM.6 | Support technical assessments of multi sourcing external foundry capabilities in strong collaboration with BU and EMS partners | FTiN | Sourav |  |  |  | Q4 | KR4: Complete Post Si analysis for Filmore Peak @ SF 14LPU 2nd source
GEMS.3.2 | FTiM.1c | Enable Flawless MTL NPI; satisfy Platform Requirements for MTL si manufactured externally | FTiN | Sourav | Updated | On Track | 50% | Q3 | KR1: Drive baseline yield improvements across all MTL tiles through CIP to BEAT BU yield targets and MEET ENG yield targets
GEMS.2.2 | FTiM.6 | Support technical assessments of multi sourcing external foundry capabilities in strong collaboration with BU and EMS partners | FTiN | Sourav | Updated | DONE | 100% | Q2 | KR3: PDK V0.9.3 delivery and TO Testchip and DRC for Filmore Peak @ SF 14LPU 2nd source
GEMS.2.3 | GEMS.2.3 | GEMS Objective Meet or exceed Intel’s external capacity demand roadmap | *GEMS* | *GEMS* |  |  |  |  | Identify with BU partnership the top 5 programs and commit to mitigating ~ $10B (Q1'22 LRP will update this number) of ‘23-’25 shortages. Deliver committed program milestones for upside capacity (16nm, GF ADL PCH on track for H2'22 ramp). - CS/CD
GEMS.2.3 | FTiM.4 | Qualify PSG eASIC Diamond Mesa DM6 Array on TSMC 16FFC | FTiN | Sourav |  |  |  | Q4 | KR1: Qualification samples, hardware, and test setup delivery readiness completed by Q4 for Normal Band
GEMS.2.3 | FTiM.4 | Qualify PSG eASIC Diamond Mesa DM6 Array on TSMC 16FFC | FTiN | Sourav |  |  |  | Q1'23 | KR2: Generate and deliver qualification reports to ePG BU by Q1’23 for Normal Band
GEMS.2.3 | FTiM.4 | Qualify PSG eASIC Diamond Mesa DM6 Array on TSMC 16FFC | FTiN | Sourav |  |  |  | Q1'23 | KR3: Qualification samples, hardware, and test setup delivery readiness completed by Q1’23 for MOC3.0 TC
GEMS.2.3 | FTiM.4 | Qualify PSG eASIC Diamond Mesa DM6 Array on TSMC 16FFC | FTiN | Sourav |  |  |  | Q2'23 | KR4: Generate and deliver qualification reports to ePG BU by Q2’23 for MOC3.0 TC
GEMS.2.3 | FTiM.4a | Qualify alternative suppliers and material production sites for ePG's eASIC platforms. | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR1: Complete quals for N5X ATK+Kinsus supplier
GEMS.2.3 | FTiM.4a | Qualify alternative suppliers and material production sites for ePG's eASIC platforms. | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR2: Complete alternate substrate supplier qual for SEMCO (Using Mt. Bryce as qual vehicle)
GEMS.2.3 | FTiM.4a | Qualify alternative suppliers and material production sites for ePG's eASIC platforms. | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR3: Complete PKG qual for Henkel adhesive mfg. site change (using Main Controller N2X as qual vehicle)
GEMS.2.3 | FTiM.4a | Qualify alternative suppliers and material production sites for ePG's eASIC platforms. | FTiN | Sourav | Updated | DONE | 100% | Q2 | KR4: Complete PKG qual for core material SHOWA DENKO site change using NR-100M as qual vehicle
GEMS.2.3 | TPSE.4 | Provide Comprehensive Testing Solutions spanning DFT to Production Test | FTiN | Sourav | Updated | On Track | 70% | Q2 | KR1: Initiate pathfinding and architect rev0 solution for hybrid bond test | Draft of whitepaper; Start DFT implementation on BZM3 testchip
GEMS.2.3 | TPSE.2 | Enable CCD, PCH, WCS tests at OSATs | FTiN | Sourav |  |  |  | Q4 | KR1: Enable MTL-S PCH Final Test @ OSATs​, Production infrastructure setup (ULT/DFF/iSEED) @ OSATs (60% completeness by Q4’22)​, Complete alignment with Intel internal (MPE, ATM, FTE ..) and OSATs on test enabling​. Initiate engagement with stakeholders on support during HVM
GEMS.2.3 | TPSE.2 | Enable CCD, PCH, WCS tests at OSATs | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR2: Drive first WCS product (GfP2) test readiness @ 3rd OSAT (Sigurd)
GEMS.3.2 | FTiM.1c | Enable Flawless MTL NPI; satisfy Platform Requirements for MTL si manufactured externally | FTiN | Sourav | Updated | On Track | 50% | Q3 | KR2: Meet performance targets across all MTL tiles within 3 to 5% of spice model closest to PRQ @ iso-lkg and iso-yield through SMP/RO measurements
GEMS.2.3 | TPSE.2 | Enable CCD, PCH, WCS tests at OSATs | FTiN | Sourav |  |  |  | Q4 | KR4: Burnside Bridge (Thunderbolt product family) test capability ready for HVM @ Sigurd
GEMS.2.3 | SOI.05 | Drive Improvement To On Time Tape Out of Intel products on TSMC | SOI | Minxi | Updated | DONE | 100% | Q2 | OTTO Align KPI Grading Mechanism with product teams
GEMS.3.2 | FTiM.1c | Enable Flawless MTL NPI; satisfy Platform Requirements for MTL si manufactured externally | FTiN | Sourav | Updated | On Track | 30% | Q3 | KR4: Enable MTPS PCH on SF to meet A0 PO by EOQ3'22 | PO timeline pushing out to WW34-36 (Sort and Class)
GEMS.2.3 | SOI.05 | Drive Improvement To On Time Tape Out of Intel products on TSMC | SOI | Minxi | Updated | On Track | 25% | Q4 | Track 2022 OTTO improvements over 2021 baseline and identify further optimization to tracking and design execution methodologies
GEMS.2.4 | GEMS.2.4 | GEMS Objective Meet or exceed Intel’s external capacity demand roadmap | *GEMS* | *GEMS* |  |  |  |  | Provide 2023 demand signal to all foundries by end of Jan'22 - CS
GEMS.3.1 | FTE.3 | FTE Objective On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | *FTE* | *FTE* |  |  |  | Q2 | KR1: ARL-G A0 TI: ww22-25, ensure PDK release on time, align sign-off methodology and margin to ensure process variation is covered. KR2: Enable a working sort TP @TSMC using PVCXT CT on N5 KR3: Achieve package qual for C0 stepping at SPIL before PRQ (ww23'22) to support Wi-Fi 6 demand (MrPk) | 75% 90% 100%
GEMS.3.1 | FTE.3 | FTE Objective On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | *FTE* | *FTE* |  |  |  | Q1 | KR1: Complete ubump probing DOE on assembly test vehicle KR2: Settle Intel N3E TCs plan with TSMC for Sep'22 and Jan'23 shuttles | 100% 100%
GEMS.3.1 | GEMS.3.1 | GEMS Objective On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | *GEMS* | *GEMS* |  |  |  |  | Deliver tech readiness and successful tape out operations for N3B (ARL-GPU, ARL-CPU, LNL-M) - CD
GEMS.3.2 | FTiM.8c | Enable flawless NPI for Hawk River product family on TSMC 16FFC RF | FTiN | Sourav |  |  |  | Q3 | KR1: Support HKR1 with E-Test sample selection and analysis; follow through to product KPI, product issue resolution (2022/Q1-Q3).
GEMS.3.1 | FTiD.1 | Enable N3B product TOs on time, NPI ramp on schedule, and N3E engagement with TSMC | FTiD | Kingsley | Updated | Behind | 20% | Q4 | KR2: LNL-M A0 TI: ww44-48, Secure engineering wafers and cycle time support to meet product needs | LNL-M TO is postponed to ww53'22 due to LNC readiness
GEMS.3.1 | FTiD.1 | Enable N3B product TOs on time, NPI ramp on schedule, and N3E engagement with TSMC | FTiD | Kingsley | Updated | DONE | 100% | Q1 | KR3: Settle Intel N3E TCs plan with TSMC for Sep'22 and Jan'23 shuttles | Sep'22 shuttle is confirmed with tsmc except area negotiation WIP. Jan'23 shuttle information is provided to tsmc and wait for further confirmation
GEMS.3.1 | FTiD.1 | Enable N3B product TOs on time, NPI ramp on schedule, and N3E engagement with TSMC | FTiD | Kingsley | Updated | Behind | 75% | Q2 | KR1: ARL-G A0 TI: ww22-25, ensure PDK release on time, align sign-off methodology and margin to ensure process variation is covered. | No critial gating item but impacted by ARL-PX cancellation. Pending MTL-PX decision
GEMS.3.1 | FTiD.1 | Enable N3B product TOs on time, NPI ramp on schedule, and N3E engagement with TSMC | FTiD | Kingsley | Updated | DONE | 100% | Q2 | KR3: Settle Intel N3E TCs plan with TSMC for Jan'23 shuttle | Confirmed N3E Jan'23 shuttle support for 28 mm^2
GEMS.3.1 | FTiM.1b | Enable Flawless N3B NPI: Satisfy Platform Requirements for ARL-GPU, ARL-CPU, and LNL-M | FTiN | Sourav |  |  |  | Q4 | KR1: Drive baseline yield improvements across all ARL tiles and LNL-M through CIP to BEAT BU yield targets and MEET ENG yield targets (To be udpated w/ yield #'s @ transfer)
GEMS.3.1 | FTiM.1b | Enable Flawless N3B NPI: Satisfy Platform Requirements for ARL-GPU, ARL-CPU, and LNL-M | FTiN | Sourav |  |  |  | Q4 | KR2: Meet performance targets across all ARL tiles and LNL-M within 10% of spice model closest to PRQ @ iso-lkg and iso-yield through SMP/RO measurements
GEMS.3.2 | GEMS.3.2 | GEMS Objective On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | *GEMS* | *GEMS* |  |  |  |  | Deliver N6 MTL SoC A0 and sample volume and meet MTL SoC D0 targets - CD/AP/CS
GEMS.3.2 | EPAE.2 | Execute MrP2 NPI program according product targets (schedule, quality, cost) | EPAE | Thomas | Updated | DONE | 100% | Q2 | KR1: Achieve package qual for C0 stepping at SPIL before PRQ (ww23'22) to support Wi-Fi 6 demand (MrP/MdPk) | MS on track but critical, package issue solved, final stress test running. So package certification will be available before ww23'22, but PRQ endangered due to low yield (not package related). Package qualification complete (even though MrP was cancelled). Will benefit FmP, GaP
GEMS.4.2 | FTiM.7 | Ramp EMP ownership of ext. foundry HVM: transfer checklist, KPI status, and lessons learnt | FTiN | Sourav |  |  |  | Q3 | KR3: Successfully handoff/transfer to EMP MEV, PVC-XT, Arno River, ADPS-GF
GEMS.4.2 | TPSE.3 | Establish IFS Support Model For Test | FTiN | Sourav | Updated | DONE | 100% | Q3 | KR1: Finalize RnR for supporting IFS customers
GEMS.4.2 | TPSE.4 | Provide Comprehensive Testing Solutions spanning DFT to Production Test | FTiN | Sourav | Updated | On Track | 50% | Q3 | KR1: Complete hiring to build TPSE expertise for Pathfinding, DFT and manufacturing test
GEMS.3.2 | FTiM.2 | Enable Yield Explorer for Fast Yield Learning on Modular Products | FTiN | Sourav |  |  |  | Q4 | KR1: Demonstrate 1Q reduction in yield learning ramp time on MTL
GEMS.3.2 | FTiM.2 | Enable Yield Explorer for Fast Yield Learning on Modular Products | FTiN | Sourav |  |  |  | Q4 | KR3: Enable NPI multi-chip ULT capability in YE for Class to Sort traceability. Ready for MTL in Q4'22
GEMS.3.2 | FTiM.2 | Enable Yield Explorer for Fast Yield Learning on Modular Products | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR4: Enable obfuscated and raw ETEST access through YE across relevant Intel groups through streamlined AGS access control procedures and integrated obfuscation methodology
GEMS.3.2 | FTiM.1c | Enable Flawless MTL NPI; satisfy Platform Requirements for MTL si manufactured externally | FTiN | Sourav | Updated | DONE | 110% | Q2 | KR3: Enable MTL SoC pilot lead Si to meet 10.2 wk TPT and meet MTL sample demand
GEMS.3.2 | FTiM.2 | Enable Yield Explorer for Fast Yield Learning on Modular Products | FTiN | Sourav |  |  |  | Q4 | KR6: Enable obfuscated and raw ETEST access through YE across relevant Intel groups through streamlined AGS access control procedures and integrated obfuscation methodology validated on ARL N3B tiles
GEMS.3.2 | FTiM.8b | Enable flawless NPI for Wifi7 products on TSMC 16FFC RF | FTiN | Sourav |  |  |  | Q4 | KR3: RF Device KPI Monitoring: Collection of RF-KPI and evaluation of RF-BIST vs Traditional RF KPI over a statistically significant data volume.
GEMS.4.3 | FTiM.5 | Create a web based Yield & Performance Dashboard for Real-time Project status | FTiN | Sourav | Updated | On Track | 30% | Q3 | KR1: Establish an online yield and performance dashboard and automate daily / weekly / monthly emails. | N5 PVCXT demostrated on SiliconDash Evaluation server (ww21). SiliconDash SOW and PR signature in process (ww24)
GEMS.3.2 | FTiM.8c | Enable flawless NPI for Hawk River product family on TSMC 16FFC RF | FTiN | Sourav |  |  |  | Q4 | KR2: Drive resolution of technology evaluation issues for HKR2 (e.g. MRAM, 11ML stack support) to enable timely tape-out of HKR2 2022/Q3.
GEMS.3.2 | FTiM.8c | Enable flawless NPI for Hawk River product family on TSMC 16FFC RF | FTiN | Sourav |  |  |  | Q4 | KR3: Tape-out, skew definition, silicon delivery, skew evaluation for HKR2.
GEMS.3.2 | FTiM.2 | Enable Yield Explorer for Fast Yield Learning on Modular Products | FTiN | Sourav | Updated | DONE | 125% | Q2 | KR5: Enable obfuscated and raw ETEST access through YE across relevant Intel groups through streamlined AGS access control procedures and integrated obfuscation methodology validated on MTL N6 tiles | Pulled in by 1Q. Thus 125%
GEMS.3.2 | FTiM.2 | Enable Yield Explorer for Fast Yield Learning on Modular Products | FTiN | Sourav | Updated | DONE | 100% | Q2 | KR2: Enable NPI multi-chip ULT capability in YE for Class to Sort traceability. Ready for PVC-XT in Q2'22
GEMS.3.2 | FTiM.8 | Enable flawless NPI for Wifi6 products on TSMC 16FFC RF | FTiN | Sourav | Updated | ZBB | 50% | Q2 | KR1: Drive baseline yield improvements for MrP2 to meet ENG yield targets (70% by WW23’22 when PRQ is scheduled) | Room temp. yield ~ 60% vs tgt 70%. Low T low V yield @ ~40%. Yield fallout primraly driven by design and methodology issues. Silicon issues expected to be 0 by WW23 PRQ date
GEMS.3.2 | FTiM.8 | Enable flawless NPI for Wifi6 products on TSMC 16FFC RF | FTiN | Sourav | Updated | ZBB | 90% | Q2 | KR2: MrP Fmax recovery of ~350 GHz to expected targets through reducing the DC Gate Resistance | Gate resistance recovered and stable at E-Test. RF characterization on-going (Q2).
GEMS.3.2 | FTiM.8 | Enable flawless NPI for Wifi6 products on TSMC 16FFC RF | FTiN | Sourav | Updated | ZBB | 80% | Q2 | KR3: Support BU for resolution of PRQ-gating qual fails on multiple samples failing edge damage monitor | Thermal Cycle Package Qualification Set. Results expected W22. Confidence high.
GEMS.3.2 | FTiM.8 | Enable flawless NPI for Wifi6 products on TSMC 16FFC RF | FTiN | Sourav | Updated | On Track | 80% | Q3 | KR4: RF Evaluation / Qualification of MIM-CAP module in Fab15B for WCS capacity expansion | Test-chip silicon in Munich. Qualification delayed by Scan Fail Yield Loss. Poor communication with TSMC on exact deadline. TSMC deadline request of May/E comes as "surprise". RF characterization on Si is inline with expectations. prod Rel qual on track.
GEMS.3.2 | FTiM.8b | Enable flawless NPI for Wifi7 products on TSMC 16FFC RF | FTiN | Sourav | Updated | DONE | 100% | Q2 | KR1: Haifa Mask-Set Tape-out, Definition and Delivery of High Quality Silicon for WCS Next-Gen WiFi (WiFi7) FmP/GaP/BnJ | Lead lot IMWAT E-Test on target, Rgate good ~ 85 Ohm/Sq, Tgt A0 BSL 90-100 Ohm/Sq
GEMS.3.2 | FTiM.8b | Enable flawless NPI for Wifi7 products on TSMC 16FFC RF | FTiN | Sourav | Updated | ZBB | 80% | Q2 | KR2: RF Performance (Fmax ~350 GHz) achieved through process targeting learnings from Paris-to-London mask-set transition. | Rgate DC low, suggesting good RF KPI. Munich RF characterization expected June/E. TEG OKR should NOT have been included FTE. Needs to be removed from FTE OKR.
GEMS.3.3 | GEMS.3.3 | GEMS Objective On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | *GEMS* | *GEMS* |  |  |  |  | Enable engineering NPI Sort @ TSMC for N3B ARL-CPU (targeting WW42-50) - CD/AP
GEMS.3.3 | TPSE.1 | Launch Sort @ TSMC for N3B Products | FTiN | Sourav | Updated | DONE | 100% | Q2 | Enable a working sort TP @TSMC using PVCXT CT on N5
GEMS.3.3 | TPSE.1 | Launch Sort @ TSMC for N3B Products | FTiN | Sourav |  |  |  | Q4 | Demonstrate 2-week sort test program update cadence at TSMC and enable 90% of planned test content
GEMS.3.3 | TPSE.1 | Launch Sort @ TSMC for N3B Products | FTiN | Sourav |  |  |  | Q1'23 | Install TSMC wafer level testing and probing technology for Arrow Lake CPU dice
GEMS.3.3 | TPSE.1 | Launch Sort @ TSMC for N3B Products | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR1: Complete ubump probing DOE on assembly test vehicle
GEMS.3.3 | TPSE.1 | Launch Sort @ TSMC for N3B Products | FTiN | Sourav |  |  |  | Q4 | KR2: Deliver eFA results within 2 weeks of receiving sort test data
GEMS.3.3 | TPSE.1 | Launch Sort @ TSMC for N3B Products | FTiN | Sourav | Updated | DONE | 100% | Q2 | Pipeclean PFA N5 samples from Intel to TSMC
GEMS.3.4 | GEMS.3.4 | GEMS Objective On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | *GEMS* | *GEMS* |  |  |  |  | Deliver HVM with quality, cycle time, cost savings and yield targets for all outsourced Si/product - AP
GEMS.4.1 | FTE.4 | FTE Objective Build a world class team with BIC talent, Culture, Systems & Processes | *FTE* | *FTE* |  |  |  | Q1 | KR1: Hire 31 HC KR2: Implement secure SharePoints for Foundry MRC, Sourcing Board and GEMS Sourcing Board KR3: Complete EMP handoff: Successfully transfer DG2-128, Tofino2, Thunderbay. | 100% 100% 100%
GEMS.4.1 | FTE.4 | FTE Objective Build a world class team with BIC talent, Culture, Systems & Processes | *FTE* | *FTE* |  |  |  | Q2 | KR1: Build full std cell customization capability from circuit design to QA KR2: Establish a working model between TPSE and EMP to support NPI and production KR3: Successfully handoff/transfer to EMP DG2-512, BZM2, MEV KR4: Hire 58 67 HC Cumulative | 100% 100% 50% 100%
GEMS.4.1 | GEMS.4.1 | GEMS Objective Build a world class GEMS team with BIC talent, culture, systems & processes | *GEMS* | *GEMS* |  |  |  |  | Hire and onboard >90% (225 POR) employees EOY'22 - AP/CD/CS/TY
GEMS.4.1 | SOI.01 | Drive and Deliver Completion of FTE Hiring Goals for 2022 ( 90% of POR ) | SOI | JM | Updated | DONE | 100% | Q1 | KR1: Hire 31 HC | Hit 31 on 22ww12.1
GEMS.4.1 | SOI.01 | Drive and Deliver Completion of FTE Hiring Goals for 2022 ( 90% of POR ) | SOI | JM |  |  |  | Q4 | KR4: Drive FTE HC to 90% of hiring target: 220 244 (excluding backfills)
GEMS.4.1 | SOI.01 | Drive and Deliver Completion of FTE Hiring Goals for 2022 ( 90% of POR ) | SOI | JM | Updated | DONE | 100% | Q2 | KR2: Hire 58 (67) HC Cumulative
GEMS.4.2 | GEMS.4.2 | GEMS Objective Build a world class GEMS team with BIC talent, culture, systems & processes | *GEMS* | *GEMS* |  |  |  |  | Deliver key business processes (consignment, selection policies and procedure, contracting, Meteorlake B2B readiness) - CS/TY/CD/DK
GEMS.4.2 | FTiD.3 | Build a full Std Cell Customization Capability and enable a Memory Customization Capability | FTiD | Kingsley | Updated | DONE | 100% | Q2 | KR1: Build full std cell customization capability from circuit design to QA | Standalone capability complete
GEMS.4.2 | FTiM.7 | Ramp EMP ownership of ext. foundry HVM: transfer checklist, KPI status, and lessons learnt | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR1: Successfully handoff/transfer to EMP DG2-128, Tofino2, Thunderbay
GEMS.1.2 | FTiP.6 | Engage with TSMC on N2 Definition, DTCO/STCO, and TR for best Intel Products | FTiP | Srini | Updated | Behind | 50% | Q3 | KR4: DTCO optimization (X'tors, interconnect, 2D and 3D IP topology)
GEMS.4.2 | FTiM.7 | Ramp EMP ownership of ext. foundry HVM: transfer checklist, KPI status, and lessons learnt | FTiN | Sourav |  |  |  | Q4 | KR4: Successfully handoff/transfer to EMP DG2-256, Hawk River
GEMS.4.2 | FTiM.7 | Ramp EMP ownership of ext. foundry HVM: transfer checklist, KPI status, and lessons learnt | FTiN | Sourav | Updated | DONE | 100% | Q2 | KR2: Successfully handoff/transfer to EMP DG2-512, BZM2 | PVC-XT handoff will move into Q3'22 due to PRQ delays. BZM2 PRQ in WW23.4 and MEV PRQ to be WW25+, transfer completion move to Q3
GEMS.1.1 | FTiP.7 | Assess and bring Foundry/OSAT 3DIC technology to Intel products | FTiP | Srini | Updated | On Track | 80% | Q3 | KR2: Complete one value proposition for hybrid bonding by Q1, 2022 and implement this PoC by Q3, 2022
GEMS.4.2 | TPSE.3 | Establish IFS Support Model For Test | FTiN | Sourav |  |  |  | Q4 | KR2: Complete hiring of support engineers for first IFS customers
GEMS.4.1 | SOI.01 | Drive and Deliver Completion of FTE Hiring Goals for 2022 ( 90% of POR ) | SOI | JM |  |  |  | Q3 | KR3: Hire 85 (102) HC Cumulative
GEMS.4.2 | TPSE.4 | Provide Comprehensive Testing Solutions spanning DFT to Production Test | FTiN | Sourav |  |  | 5% | Q4 | KR2: Provide DFT and manufacturing test support for business groups by partnering with custom silicon and graphics products
GEMS.4.2 | TPSE.4 | Provide Comprehensive Testing Solutions spanning DFT to Production Test | FTiN | Sourav |  |  | 5% | Q4 | KR3: Complete rev0 assessment of major OSAT current capabilities and roadmap in test
GEMS.4.2 | TPSE.5 | Ramp up EMP team to be fully capable of owning and driving production test | FTiN | Sourav | Updated | DONE | 100% | Q2 | Establish a working model between TPSE and EMP to support NPI and production
GEMS.4.2 | TPSE.5 | Ramp up EMP team to be fully capable of owning and driving production test | FTiN | Sourav | Updated | DONE | 100% | Q1 | KR1: Complete transfer of existing TPSE HVM test engineers to EMP
GEMS.4.2 | SOI.15 | Improve BTI Tracking and Forecasting Methodology for FTE | SOI | JM |  |  |  | Q3 | Identify where extra FTE spending is coming from; update PLAN'23 forecast to account for it.
GEMS.4.2 | SOI.02 | Create an IP/EDA Strategy & Enablement Team | SOI | Stephen | Updated | On Track | 0% | Q4 | KR3: Hire and ramp up new EDA members
GEMS.4.2 | SOI.08 | Improve FTE Org Health, Communication & Employee Growth | SOI | JM |  |  |  | Q4 | Monitor and Evaluate effectiveness of FTE WS hand offs in 2H; reassess in Q4
GEMS.4.2 | SOI.02 | Create an IP/EDA Strategy & Enablement Team | SOI | Stephen | Updated | Behind | 0% | Q2 | KR1: Complete Transition from PDE; own 3rd Party EDA/IP vendor Technical BU Support for External Foundry Programs | Behind on hiring of the team.
GEMS.4.2 | SOI.09 | Systematize Pathfinding, Collaboration and TC evals by establishing proper process | SOI | Mario | Updated | DONE | 100% | Q1 | Drive and establish communication forum, foundation for creating metrics, partner alignment and TC plan methodology | Expectations established
GEMS.4.2 | SOI.10 | Implement GEMS Partner Sync Model | SOI | Minxi/Yu-Wen | Updated | NOT DONE | 50% | Q1 | Assess Team of X 3-Pillar Opation value as a solution for cross team communication
GEMS.4.2 | SOI.10 | Implement GEMS Partner Sync Model | SOI | Minxi/Yu-Wen | Updated | On Track | 0% | Q4 | Drive Team of X 3-Pillar implementation
GEMS.4.3 | SOI.03 | Implement IP security system for External Confidential Information (ECI) to meet legal req. | SOI | Lonn | Updated | On Track | 10% | Q3 | Complete transition of External Confidential Information (ECI) Firewall responsibilities to new team under Richard Antonellis.
GEMS.4.2 | SOI.08 | Improve FTE Org Health, Communication & Employee Growth | SOI | JM | Updated | On Track | 70% | Q2 | Complete First mapping session and document handoff between FTiN/FTiD
GEMS.4.2 | SOI.08 | Improve FTE Org Health, Communication & Employee Growth | SOI | JM | Updated | DONE | 100% | Q2 | EMP: Drive completion of critical leadership hires, complete Interim support (CoS/Ops/Admin) and team roles/charter by end of Q2
GEMS.4.2 | SOI.08 | Improve FTE Org Health, Communication & Employee Growth | SOI | Mario | Updated | DONE | 100% | Q2 | Drive FTE to EMP roles and hand offs mapping sessions/alignment early Q2, document and review with FTE+EMP
GEMS.4.2 | SOI.10 | Implement GEMS Partner Sync Model | SOI | Minxi/Yu-Wen | Updated | On Track | 90% | Q2 | Formulate Team of X 3-Pillar operation model proposal | Mario - Follow up with Venky
GEMS.4.2 | SOI.13 | Update UPLC process to support external suppliers | SOI | Lonn | Updated | On Track | 80% | Q3 | Complete ratification of LRP and Dual Drive concepts for Q4 UPLC. Unify UPLC metrics for internal and external sourcing.
GEMS.4.2 | SOI.14 | Improve standardization of EMS contracting procedures | SOI | Lonn | Updated | DONE | 100% | Q2 | Review existing TOP contracts, refine neg plan review and Sourcing Board procedures. Deliver updated training to EMS team. | TOP completed. Other contract forms still in progress (as planned).
GEMS.4.2 | SOI.15 | Improve BTI Tracking and Forecasting Methodology for FTE | SOI | JM |  |  |  | Q4 | Establish comprehensive BTI tracker and forecast for PLAN'23 (ideally DARC report for FTE's needs)
GEMS.2.3 | SOI.05 | Drive Improvement To On Time Tape Out of Intel products on TSMC | SOI | Minxi | Updated | On Track | 50% | Q3 | Collaborate with DEG on OTTO KPI automation
GEMS.4.2 | SOI.15 | Improve BTI Tracking and Forecasting Methodology for FTE | SOI | JM | Updated | On Track | 50% | Q2 | Establish BTI tracking system to link actuals to WS's. Roll out training to team on PO filing for trackable BTIs.
GEMS.4.2 | SOI.16 | Taiwan Site Strategy | SOI | Yu-Wen | Updated | DONE | 70% | Q2 | >85% completion of Hsinchu Site Strategy KRs
GEMS.4.3 | GEMS.4.3 | GEMS Objective Build a world class GEMS team with BIC talent, culture, systems & processes | *GEMS* | *GEMS* |  |  |  |  | Deliver End to End funded IT Systems to drive systems, data reliability, operationalization and efficiency - AP/CS/DK
GEMS.4.3 | SOI.07 | Deploy Ext Foundry/OSAT Support Filing System | SOI | Minxi | Updated | On Track | 40% | Q3 | Release rev0 production deployment for Issue Management System for pilot function TSMC N3
GEMS.4.3 | FTiM.5 | Create a web based Yield & Performance Dashboard for Real-time Project status | FTiN | Sourav | Updated | On Track | 50% | Q4 | KR2: Add interactive features to be fully applicable to MTL and ARL products | MTL IOE-P / GPU-M / GPU-P data will be loaded to SiliconDash evalution server (ww24) for assessment before official deployment (1Aug'22)
GEMS.4.3 | SOI.03 | Implement IP security system for External Confidential Information (ECI) to meet legal req. | SOI | Lonn | Updated | DONE | 100% | Q1 | KR1: Implement secure SharePoints for Foundry MRC, Sourcing Board and GEMS Sourcing Board
GEMS.4.2 | SOI.10 | Implement GEMS Partner Sync Model | SOI | Minxi/Yu-Wen | Updated | On Track | 0% | Q3 | Drive Team of X 3-Pillar operation resolution alignment at GEMS level
GEMS.4.3 | SOI.06 | Establish SharePoint for FTE customers, partners and members | SOI | Minxi | Updated | DONE | 100% | Q1 | KR1: Complete FTE SharePoint rev 0 content implementation for all workstreams
GEMS.4.3 | SOI.07 | Deploy Ext Foundry/OSAT Support Filing System | SOI | Minxi | Updated | On Track | 1% | Q4 | Enhance TSMC N3 support filing system with access control that support FTE extension
GEMS.4.2 | SOI.02 | Create an IP/EDA Strategy & Enablement Team | SOI | Stephen | Updated | On Track | 20% | Q3 | KR2: Hire and ramp up new IP team members
GEMS.4.3 | SOI.07 | Deploy Ext Foundry/OSAT Support Filing System | SOI | Minxi | Updated | DONE | 100% | Q2 | Release rev0 JIRA production deployment for SoW Tracking System for pilot function TSMC N3

## FTE.Q1'22.OKRs
GEMS 2022 |  |  |  | FTE Q1 2022
| Objectives | # | Key Results | Key Results
1 | Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | 1 | Deliver 3CRM refresh and align with DEG/BU for Server and Client product roadmap in compliance with the GLADIUS framework/New Development Model (Quarterly cadence). - TY/CD/Jerry | KR1: Recommend N3E Intercept for Client PTL for '25 PRQ at GEMS/DEG Level KR2: Propose Dual Drive Framework to CPG/DEG Staff KR3: Complete PPA assessment of N3E v0.5 vs N3 v1.0 KR4: Initiate regular N2 meeting with TSMC, and start PPA assessment | Report out on 22ww15.1
|  | 2 | Complete detailed study and business case analysis for Dual Drive Strategy for N3E and N2 to mitigate revenue risk to facilitate a decision by June’22 - TY/CD/Jerry
|  | 3 | Establish Samsung sourcing strategy to increase influence and develop into a viable sourcing option. - CS/CD
|  | 4 | Deliver cost savings of ~$450M 2022-2025 (Q1'22 LRP will provide annualized numbers) through cost savings and cost avoidance projects across all groups (eg: technology/yield cost base improvement, secondary sourcing) - MA/CD/TY/CS/AP
2 | Meet or exceed Intel’s external capacity demand roadmap | 1 | Deliver >10% upside/pull ins to address shortages (Q1'22 goal of >2000 wafers). - CS | KR1: Complete technical assessment and feasibility closure for PSG's Max10 2nd source with GF 55nm EFF and enable business team to proceed with commercial negotiations KR2: Drive first WCS product (GfP2) test readiness @ 3rd OSAT (Sigurd)
|  | 2 | Create and ratify a multi-sourcing policy to improve capacity flexibility and BCP. Complete 2nd source substrate qualifications for flexibility (>4 quals by EOQ1) - CS/TY (CD?)
|  | 3 | Identify with BU partnership the top 5 programs and commit to mitigating ~ $10B (Q1'22 LRP will update this number) of ‘23-’25 shortages. Deliver committed program milestones for upside capacity (16nm, GF ADL PCH on track for H2'22 ramp). - CS/CD
|  | 4 | Provide 2023 demand signal to all foundries by end of Jan'22 - CS
3 | On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | 1 | Deliver tech readiness and successful tape out operations for N3B (ARL-GPU, ARL-CPU, LNL-M) - CD | KR1: Complete ubump probing DOE on assembly test vehicle KR2: Settle Intel N3E TCs plan with TSMC for Sep'22 and Jan'23 shuttles
|  | 2 | Deliver N6 MTL SoC A0 and sample volume and meet MTL SoC D0 targets - CD/AP/CS
|  | 3 | Enable engineering NPI Sort @ TSMC for N3B ARL-CPU (targeting WW42-50) - CD/AP
|  | 4 | Deliver HVM with quality, cycle time, cost savings and yield targets for all outsourced Si/product - AP
4 | Build a world class GEMS team with BIC talent, culture, systems & processes | 1 | Hire and onboard >90% (225 POR) employees EOY'22 - AP/CD/CS/TY | KR1: Hire 31 HC KR2: Implement secure SharePoints for Foundry MRC, Sourcing Board and GEMS Sourcing Board KR3: Complete EMP handoff: Successfully transfer DG2-128, Tofino2, Thunderbay.
|  | 2 | Deliver key business processes (consignment, selection policies and procedure, contracting, Meteorlake B2B readiness) - CS/TY/CD/DK
|  | 3 | Deliver End to End funded IT Systems to drive systems, data reliability, operationalization and efficiency - AP/CS/DK

## ZBB
GEMS ID | FTE ID | Workstream Objective | WS | Owner | Status | % Done | Q
[8 empty] | Key Result | Comments
GEMS.4.3 | SOI.04 | Implement GEMS Partner Survey to Identify FTE Service Improvement Opportunities | SOI | Mario | ZBB | 70% | Q1 | KR1: Align Rev 0 partner survey across GEMS team | Taken over by EMS team, inputs provided
GEMS.4.3 | SOI.04 | Implement GEMS Partner Survey to Identify FTE Service Improvement Opportunities | SOI | Mario | ZBB | 0% | Q3 | KR2: Send out first survey

## GEMS rolled up - Q4'21
GEMS 2021 |  | FTE 2021 |  | FTE Q1
# | Top 5 Goals | # | Top 10 Goals
1 | Deliver uninterrupted supply that fully supports Intel’s 2021 revenue plan, with 15-20% potential demand flexibility | 1 | Execute to achieve all committed NPI/HVM project schedule and yield targets using external manufacturing | Support TO/NPI of MTL SoC, IOEM/P, Tofino3, BarlowRidge. Complete new fab (GF Fab 8) setup for ADPS and ensure smooth supply chain to internal bump/sort/assembly.
2 | Create 3-year supply chain devmnt roadmap with annual execution milestones for systems, supplier technologies, processes, policies | 2 | Manage successful end-to-end execution of Branch projects from supplier deliverables to product engineering | Drive N3B key technical closure, resolve N3 specific bump challenges and drive other key items including: CuRDL/bump, HV methodology, reliability, design methodology, ESD arch, etc, for ARL, SRF, LNL products. Hybrid bonding POC value propositions identified; Testchip plans established.
|  | 3 | Expand competitive analysis and ecosystem learning to improve Intel product quality & development efficiency
3 | Establish integrated capability, capacity, cost roadmap for key GEMS areas to deliver product leadership; execute according to 2021 plan | 4 | Complete Samsung 4LPP and 3GAP process evaluation/definition including test chip strategy and execution | Close 3GAP testchip plans with Samsung. testchip floor plan in place. Resources in place for execution to enable Q3, 2022 TI. Enhance Gladius framework to incorporate product portfolio and capacity requirements early enough to minimize schedule risks
|  | 5 | Drive TSMC N3P and N2 DTCO/STCO with feature requirements for Intel product roadmap & differentiation
|  | 6 | Evaluate and experiment key assembly & packaging capabilities from OSAT including 2.3D and hybrid bonding
|  | 7 | Build engineering capability and infrastructure for FOM and block level PPA assessment/optimization
|  | 8 | Support Multi-Sourcing / 2-Way Door initiatives between Intel & external foundry processes for product flexibility
4 | Create a 3-year organizational development plan for people, talent, culture, geo strategy, org structure, and execute according to quarterly POR | 9 | Grow FTE capability and the new mindset needed to support Intel’s mainstream products; meet 2021 hiring target | Complete PLAN'22 for both FTE and EMP. Recommend and establish engagement with alternate supplier for legacy products, specifically PSG legacy and Silicon photonics
5 | Deliver/exceed cost saving commits, aligned with BUs, and including multi-year cost saving project execution in 2021 | 10 | Enable Sort/Test data throughput for fast yield learning required for leading edge foundry engagement | Enable 1XTD2 ubump probing solution buyoff and ubump reflow process in TSMC. Enable YE scan diagnosis/memory capabilities for eFA/pFA for disagg products. NPI Test data integration to YE: provide fast & automatic feedback test tata to foundries for products (DG2, MTL G, MTL SOC)
Need to update and send out

## Lookups
FTE WS
*GEMS*
*FTE*
FTiP
FTiD
FTiN
EPAE
ETPP
Finance
SOI
Status
On Track
Behind
NOT DONE
DONE
ZBB
Updated?
Updated

## EPAE
Key Results
GEMS ID | FTE ID | Workstream Objective | WS | Owner | Status | % | Q |  | comment
| ws.# | High-level statement, visionary/inspirational. Need not be SMART | [5 empty] | SMART KRs, as many as meaningful.
GEMS.1.1 | FTE.1 | FTE Objective Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | *FTE* | *FTE* |  |  |  | (Yellow ones below)
GEMS.1.1 | EPAE.3 | Introduce Industry Standard Passivation on Intel Wafers | EPAE | Alois | Done | 100% | Q1 | KR1: Complete Phase2 and deliver samples to Aloha Fab for characterization and stress test (result will set direction for further engagement)
GEMS.1.1 | EPAE.4 | Validate 2.3D technology for Cost Sensitive HPC applications | EPAE | David |  |  | Q3 | KR1: Finalize BLRT in Q3'22
GEMS.1.1 | EPAE.5 | Ensure product leadership through external 3DIC /Hybrid Bonding Technology | EPAE | Max/Jason | Done | 100% | Q1 | KR1: align with FTIP testvehicle plan and frame project in Q1 | Proposal for 3-step approach discussed, framework in preparation
GEMS.1.1 | EPAE.5 | Ensure product leadership through external 3DIC /Hybrid Bonding Technology | EPAE | Max/Jason | On Track | 95% | Q2 | KR2: Drive project proposal to sourcing forum and start Supplier WG | Proposal in alignment phase. Supplier WG start not before Q4
GEMS.1.1 | EPAE.6 | Enable 2.3D with bridge as a drop in compatible technology to EMIB (fallback option) and provide early access to this technology in order to bridge availability gap (ODI in 2025) | EPAE | David/Evelyn | Done | 100% | Q1 | KR1: Frame project proposal, define deliverables, planned schedule, biz case and get green light to start engagement Q1'22 (awaiting approval)
GEMS.1.1 | EPAE.6 | Enable 2.3D with bridge as a drop in compatible technology to EMIB (fallback option) and provide early access to this technology in order to bridge availability gap (ODI in 2025) | EPAE | David/Evelyn | On Track | 90% | Q2 | KR2: First read out of Phase 1 (mechanical validation of technology) 2Q after kick off estimated in Q3 | Execution on track TO will happen in May, but delay of milestones due to long negotiations (~2m) all milestones shift accordingly 1:1
GEMS.1.2 | EPAE.6 | Enable 2.3D with bridge as a drop in compatible technology to EMIB (fallback option) and provide early access to this technology in order to bridge availability gap (ODI in 2025) | EPAE | Hans-Gerd/ Andreas | On Track | 90% | Q2 | KR3: finalize Test chip design | design on track, tape out planned for end May, beginning June, rest see above
GEMS.1.1 | EPAE.7 | Create OSAT/Substrate supplier generic design rule document, on FC-CSP/BGA/Hybrid/MCM packages, for Intel BUs' use, to create competitive roadmaps for Intel business at OSATs. | EPAE | Aruna | On Track | 90% | Q2 | KR1: Create Generic DRZ document and ensure access to BUs with firewall. | Generic DR compiled, in alignment with desing teams
GEMS.2.1 | FTE.2 | FTE Objective Meet or exceed Intel’s external capacity demand roadmap | *FTE* | *FTE* |  |  |  | (Yellow ones below)
GEMS.2.2 | EPAE.1 | Enable CCG MTL PCH-S Multi-sourcing at OSAT (PTI &ASE) | EPAE | Abhishek | On Track | 99% | Q2 | KR1: Achieve process freeze milestone for ADL PCH pipecleaner across both PTI and ASE in quarter | ww17 for PTI ww21 for ASE
GEMS.2.2 | EPAE.1 | Enable CCG MTL PCH-S Multi-sourcing at OSAT (PTI &ASE) | EPAE | Abhishek |  |  | Q3 | KR2: Achieve GRC qual with passing reliability data for ADL PCH pipecleaner by end of Q2'22
GEMS.2.3 | EPAE.1 | Enable CCG MTL PCH-S Multi-sourcing at OSAT (PTI &ASE) | EPAE | Abhishek |  |  | Q4 | KR3: Enable DFF environment for smooth OSAT to Intel data flow in MTL PCH NPI phase (CP1 and CP2 phases) by end of Q4’22
GEMS.2.3 | EPAE.2 | Execute MrP2 @SPIL according product targets (schedule, quality, cost). | EPAE | Roland | On Track | 98% | Q2 | KR1: Achieve package qual for C0 stepping at SPIL before PRQ (ww23'22) to support Wi-Fi 6 demand (MrP2) | MS on track but critical, package issue solved, final stress test running. So package certification will be available before ww23'22, but PRQ endangered due to low yield (not package related)
GEMS.2.3 | EPAE.3 | Execute 2nd FE source (SEC 14LPU-RF) enablement for FmP2 | EPAE | Roland | On Track | 90% | Q2 | KR2: TC package layout freeze in ww25-35 | on track for TO in ww25
GEMS.2.3 | EPAE.3 | Execute 2nd FE source (SEC 14LPU-RF) enablement for FmP2 | EPAE | Roland |  |  | Q4 | KR3: TC package power on in ww40-50
GEMS.2.4 | EPAE.4 | Execute CNV GaP2 @SPIL - 3 dies MCM - Intel's new standard WiFi7 & BT | EPAE | Aruna |  |  | Q3 | KR1: Complete power-on and prequal on GaP2 A0. Freeze process for B0 stepping at SPIL before PRQ (ww24'23) to support Wi-Fi 7
GEMS.3.2 | FTE.3 | FTE Objective On time delivery of technology readiness, NPI and HVM ramp in external manufacturing | *FTE* | *FTE* |  |  |  | (Yellow ones below)
GEMS.3.1 | EPAE.1 | Execute Monroe Peak2 second source according product targets (schedule, quality, cost) | EPAE | Roland |  |  | Q3 | KR1: Qualify second source (JCET / UMTC) for MrP2 in Q3
GEMS.3.1 | EPAE.2 | Execute Hayden Bridge according product targets (schedule, quality, cost) | EPAE | Roland | On Track | 95% | Q2 | KR1: Complete PDC data collection for Hayden Bridge not delaying PRQ by end of Q2 at SPIL, JCET & Amkor | JCET, Amkor PDC samples SOD in ww21, SPIL samples sent ww19
GEMS.3.1 | EPAE.3 | Execute Filmore Peak2 program according product targets (schedule, quality, cost) | EPAE | Roland | On Track | 90% | Q2 | KR1: Complete bumping & assembly setup for FmP2 by mid of Q2 at SPIL | Live wafers shipped for bumping ww20.4
GEMS.3.1 | EPAE.4 | Execute Barlow Ridge according product targets (schedule, quality, cost) | EPAE | Stephen | Done | 100% | Q1 | KR1: TRA completion and DoE definition complete
GEMS.3.1 | EPAE.4 | Execute Barlow Ridge according product targets (schedule, quality, cost) | EPAE | Stephen |  |  | Q3 | KR2: passed successfully process freeze milestone
GEMS.3.1 | EPAE.5 | Execute PNC 16009 according product targets (schedule, quality, cost) | EPAE | Stephen |  |  | Q3 | KR1: Complete process setup and Power on builds.
GEMS.3.1 | EPAE.6 | Execute Mission Bridge 3 according product targets (schedule, quality, cost) | EPAE | Dale | Behind | 80% | Q1 | KR1: Mission Bridge 3 both Silicon and Package T.O. | Si TO pushed to end Q1 and Package TO to accordingly to Q2
GEMS.3.1 | EPAE.6 | Execute Mission Bridge 3 according product targets (schedule, quality, cost) | EPAE | Dale | On Track | 70% | Q2 | KR2: Complete prototype builds with Full Loop wafers | SLW arrived at Spil, FLW targeted for ww23
GEMS.3.1 | EPAE.6 | Execute Mission Bridge 3 according product targets (schedule, quality, cost) | EPAE | Dale |  |  | Q3 | KR3: A0 power on. Complete Assy GRC package rel testing.
GEMS.3.1 | EPAE.7 | Execute Mills Creek Falls (MCF) according product targets (schedule, quality, cost) | EPAE | Dale | Behind | 30% | Q2 | KR1: Package T.O. with final drawings, (substrate, POD, Assembly, etc.) | BU pushed out schedule due to missing design resources. package TO now targeted for ww34
GEMS.3.1 | EPAE.7 | Execute Mills Creek Falls (MCF) according product targets (schedule, quality, cost) | EPAE | Dale |  |  | Q3 | KR2: Bumping. Assembly, Process set up for first eng. builds
GEMS.3.1 | EPAE.8 | Execute Linkville (LKV) according product targets (schedule, quality, cost) | EPAE | Aruna | DONE | 100% | Q2 | KR1: Complete package TO | Tape out pulled in by 4 weeks to ww17
GEMS.3.2 | EPAE.9 | Execute Linkville (LKV) according product targets (schedule, quality, cost) | EPAE | Aruna | On Track | 70% | Q2 | KR2: Complete TRA and define DOEs. | TRA initiated ECD, DOE definitionfinalized ww24
GEMS.3.3 | EPAE.10 | Execute Linkville (LKV) according product targets (schedule, quality, cost) | EPAE | Aruna |  |  | Q3 | KR3: Complete process setup and A0 power on builds.
GEMS.3.1 | EPAE.9 | Execute Gale Peak2 (GaP2) according product targets (schedule, quality, cost) | EPAE | Aruna | Behind | 90% | Q1 | KR1: Complete Package TO - GaP2 variations (STEP, DPHY, EEPROM) | Bu shifted TO to Q2
GEMS.3.2 | EPAE.9 | Execute Gale Peak2 (GaP2) according product targets (schedule, quality, cost) | EPAE | Aruna | Done | 100% | Q1 | KR1: Complete GaP2 STEP POR - TRA and define DOEs
GEMS.3.3 | EPAE.9 | Execute Gale Peak2 (GaP2) according product targets (schedule, quality, cost) | EPAE | Aruna |  |  | Q3 | KR3: Complete power-on and prequal on GaP2 A0.
GEMS.3.2 | EPAE.9 | Execute Gale Peak2 (GaP2) according product targets (schedule, quality, cost) | EPAE | Aruna | Behind | 10% | Q2 | KR4: Bring up 2nd source substrate supplier. | downgraded in priority Due to learinngs from MrP2, focus was on BOM selection, BU does not have capability to desing 2nd source at the moment. will be pushed out by BU
GEMS.3.1 | EPAE.9 | Execute Hawk River according product targets (schedule, quality, cost) | EPAE | Christoph | DONE | 100% | Q2 | KR1: Complete Pre Qual with SL- Material of new Mold Compound in Q2 | New MC successfully passed pre-qual. BU follows now different strategy with new substrate, which will push all milestones and requires new qualification of the package
GEMS.3.1 | EPAE.9 | Execute Hawk River according product targets (schedule, quality, cost) | EPAE | Christoph | Behind | 40% | Q2 | KR2: Si TO of A1 in Q2 | BU internal discusison if A stepping or B stepping should be taped out. decision planned in ww21
GEMS.3.1 | EPAE.10 | Execute EyeC Radar according product targets (schedule, quality, cost) | EPAE | Christoph | Done | 100% | Q1 | KR1: Complete VDA (Pkg TO) of Rx / Tx /LcP ww09
GEMS.3.1 | EPAE.10 | Execute EyeC Radar according product targets (schedule, quality, cost) | EPAE | Christoph | On Track | 80% | Q2 | KR2: Complete A0 first Full Loop builds of Rx / Tx /LcP ww23 | FLW SOD planned for June 3rd
GEMS.3.1 | EPAE.10 | Execute EyeC Radar according product targets (schedule, quality, cost) | EPAE | Christoph | Behind | 60% | Q2 | KR3: A0 power on (Rx / Tx /LcP) end of Q2 | BU shifted PO to ww30 (Q3)
GEMS.3.1 | EPAE.10 | Execute EyeC Radar according product targets (schedule, quality, cost) | EPAE | Christoph |  |  | Q3 | KR4: Complete A0 process cornering, Process freez Q3
GEMS.3.1 | EPAE.10 | Execute EyeC Radar according product targets (schedule, quality, cost) | EPAE | Christoph |  |  | Q3 | KR5: Complete A0 build #2 and #3 of Rx / Tx /LcP in Q3
GEMS.3.1 | EPAE.11 | Execute Bonanza Mine 2 according product targets (schedule, quality, cost) | EPAE | Abhishek | Behind | 95% | Q2 | KR1: Achieve Bonanza Mine 2 PRQ with passing package reliability qual for BZM2 by WW22’22 | Qual failed in TCB 700x (1/314) - root cause is failing substrate material. Most liekly substrate hanling at subtrate vendor or Tessolve caused fail. TF running
GEMS.3.1 | EPAE.12 | Execute PNC 16007 according product targets (schedule, quality, cost) | EPAE | Stephen |  |  | Q2 | KR1: Complete process setup and Power on builds.
GEMS.3.1 | EPAE.12 | Execute PNC 16007 according product targets (schedule, quality, cost) | EPAE | Stephen |  |  | Q3 | KR2: passed successfully process freeze milestone
GEMS.3.1 | EPAE.12 | Execute PNC 16007 according product targets (schedule, quality, cost) | EPAE | Stephen |  |  | Q4 | KR3: Achieve PNC 16007 PRQ with passing package reliability qual by WW44'22
GEMS.4.1 | FTE.4 | FTE Objective Build a world class team with BIC talent, Culture, Systems & Processes | *FTE* | *FTE* |  |  |  | (Yellow ones below)
GEMS.4.1 | GEMS.4.1 | GEMS Objective Build a world class GEMS team with BIC talent, culture, systems & processes | *GEMS* | *GEMS* |  |  |  | Hire and onboard >90% (225 POR) employees EOY'22 - AP/CD/CS/TY
GEMS.4.2 | GEMS.4.2 | GEMS Objective Build a world class GEMS team with BIC talent, culture, systems & processes | *GEMS* | *GEMS* |  |  |  | Deliver key business processes (consignment, selection policies and procedure, contracting, Meteorlake B2B readiness) - CS/TY/CD/DK
GEMS.4.1 | EPAE.1 | Build an IFS product intake framework to structure the way from idea to project execution | *FTE* | Thomas | Done | 100% | Q1 | KR1: Set up product intake process framework in Q1'22, steer all requests over this path | Framework is set up, IFS informed, requests are now steered via intake forum
GEMS.4.1 | EPAE.2 | Establish best technical expert team for external assembly technologies | EPAE | all EPAE |  |  | every Q | KR1: Issue minimum one IDF per quarter from EPAE
GEMS.4.1 | EPAE.3 | Establish a process framework to influence BU product planning | *FTE* | Jason | Behind | 50% | Q2 | KR1: Define and align framework with strategy team targeting on a regular base an early BU engagment (Roadmap and capability) in Q2 | First meetings held, concept in preparation
GEMS.4.1 | EPAE.4 | Establish a process framework to influence BU product planning | *FTE* | Jason |  |  | Q3 | KR2: Roll out process framework to divisions and bring process alive in Q2
GEMS.4.1 | EPAE.5 | Build world class EPAE team with BIC talent, culture | EPAE | Thomas |  |  | every Q | KR1: Analyze structural gap in the current team set up, propose solution and hire accordingly
GEMS.4.1 | EPAE.6 | Establish a process for continuous improvement of NPI | EPAE | Abhishek | Done | 100% | Q1 | KR1: Correlate VDA time with at least 2 project or design parameters by end of January’22
GEMS.4.2 | EPAE.6 | Establish a process for continuous improvement of NPI | EPAE | Abhishek | Behind | 95% | Q1 | KR2: Present VDA analysis results to stakeholders and define next process staps by end of Q1 2022 | Presentation ready, meeting shifted to Q2 due to availability of stakeholder
GEMS.4.3 | EPAE.6 | Establish a process for continuous improvement of NPI | EPAE | Abhishek | Done | 100% | Q1 | KR3:Influence 80% closure of all NPI Harmonization topics (ref: beginning of 2022) by end Q1 ’22
GEMS.4.4 | EPAE.6 | Establish a process for continuous improvement of NPI | EPAE | Abhishek | Done | 100% | Q1 | KR4: Define the handover process and contents of handover process with EMP team by end of Q1’22
GEMS.4.1 | EPAE.7 | Standardize a process for a succesful NPI | EPAE | Aruna |  |  | Q2 | KR1: Standardize technical risk assessment process, to capture TRA rating update during NPI Process freeze, to ensure successful PRQ.