## Prashant
Objective |  | Critical Path (Interim Milestone or Sub Goal) |  |  |  |  | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | # | As Measured by | ECD | Owners | Tracking | Scoring
1 | Enable exploration of 3DIC technologies for predictable and competitive modular product intercepts | 1 | Framework for 3DIC PF defined |  |  |  | 1 | common metric defined for 2.XD benchmarking and develop insights on scalability based on key metrics | Q1
[7 empty] | 2 | common metric defined for 3D benchmarking and develop insights on scalability based on key metrics | Q1
|  | 2 | Memory/Logic Coupling options identified |  |  |  | 1 | Pathfind capability/cost of SRAM on logic based TCCD/TCM with external vendors (1) paper assessment; (2) design enabling; (3) tape out | Q1-Q4
[7 empty] | 2 | Track/Benchmark emerging memories | Q1
|  | 3 | Explore (to Pathfind) promising scaling options to scale logic technology (area and voltage scaling) |  |  |  | 1 | Downselect best options beyond GAA from switching energy and area scalability | Q1
[7 empty] | 2 | Explore technology options for SRAM as a chiplet (3D stacked to Random Logic) | Q2
2 | Expand engagements with product arhcitects/designers to explore future foundry offerings at modular design concept stage | 1 | BZM logic-logic (process tech meeting #/mm2) |  |  |  | 1 | explore CoW/WoW process option meeting specs
[7 empty] | 2 | Pathfind process flow options for TC
|  | 2 | ANR - WoW DTC (Tighly coupled cap via 3D meeting spec) |  |  |  | 1 | Compare MaxMim, DTC, ISC to meet Cap, ESR spec
[7 empty] | 2 | Pathfind process flow options for TC
|  | 3 | LCH Logic-NVM |  |  |  | 1 | close on MRAM viability
[7 empty] | 2 | close on NVM-logic packaging/stacking option
3 |  | 1 |  |  |  |  | 1
2
|  | 2 |  |  |  |  | 1
2
|  | 3 |  |  |  |  | 1
2

## Angada
Objective |  | Critical Path (Interim Milestone or Sub Goal) |  |  |  |  | Key Results | [5 empty] | Comments
|  | # | Milestone | Customers | Sponsors | Dependency | # | As Measured by | ECD | Owners | Tracking | Scoring
1 | Build Predictive DTCO Flow for CMOS Logic | 1 | Assess small-circuit PPA due to material and process changes in MOL and BEOL materials and processes (L1 PPA) | Internal; Leads to Objective # | Jeff, Derchang | Hire 1 TCAD Engg by Q1.3 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 2 | Assess small-circuit PPA due to circuit-level changes (eg. Standard cell architecture / layout / circuit, fan out, Vdd, interconnect length etc) (L1 PPA) | Internal; Leads to Objective # | Jeff, Derchang | Hire 1 TCAD Engg by Q1.3 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 3 | Capable of generating PDK collateral | Internal; Leads to Objective # | Jeff, Derchang | Hire 1 TCAD Engg and Physical Design Engg by Q1.3 | 1 |  |  | Angada, Wenjie
[7 empty] | 2 |  |  | Angada, Wenjie
|  | 4 | Assess block-level PPA due to material, process, circuit-level changes (L2 PPA) | Internal; Leads to Objective # | Jeff, Derchang | Hire 1 Physical Design Engg by Q1.3; PDK collateral is available | 1 |  | Q3.2 | Angada, Chung-Chin
[7 empty] | 2 |  | Q3.3 | Angada, Chung-Chin
|  | 5 | Assess device-level (transistor) due to material and process changes (L0 PPA) | Internal; Leads to Objective # | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 | NSFET NMOS is available and calibrated to experimental data | Q3.1 | Angada
[7 empty] | 2 | NSFET PMOS is available and calibrated to experimental data | Q3.2 | Angada
|  | 6 | Provide 3 methods to improve PPA 5% | Internal; Leads to Objective # | Jeff, Derchang |  | 1 | 2 methods proposed and PPA determined | Q4.2 | Angada
[7 empty] | 2 | 1 more method proposed and PPA determined | Q4.3 | Angada
2 | Build Predictive DTCO Flow for SRAM | 1 | Assess bit-cell level PPA due to material and process changes in MOL and BEOL materials | Internal; Leads to Objective # | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 2 | Assess array-level PPA due to material and process changes in MOL and BEOL materials | Internal; Leads to Objective # | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 3 | Assess bit-cell and array-level PPA due to material and process changes in FEOL changes | Internal; Leads to Objective # | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 4 | Assess bit-cell and array-level PPA due to layout changes | Internal; Leads to Objective # | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 5 | Provide 3 PPA optimization options considering logic and memory heterogeniety | Internal; Leads to Objective # | Jeff, Derchang |  | 1 | 2 methods proposed and PPA determined |  | Angada
[7 empty] | 2 | 1 more method proposed and PPA determined |  | Angada
3 |  | 1 |  |  |  |  | 1
2
3
|  | 2 |  |  |  |  | 1
2
|  | 3 |  |  |  |  | 1
2
4 | Organizational Development | 1 | Set up compute and license infrastructure |  | Jeff, Derchang |  | 1 | Identify funding source; Coordinate with the EDA team to acquire licenses | Q1.3 | Angada, Derchang, John Mark
[7 empty] | 2 | Set up compute and tool infrastructure for predictive DTCO / STCO activities | Q1.3 | Angada, Derchang, John Mark
|  | 2 | Complete hiring goals |  | Jeff, Derchang |  | 1 | Hire 3 approved reqs | Q2.3 | Angada, Derchang, John Mark
[7 empty] | 2 | Get approval for 2 additional reqs | Q1.3 | Angada, Derchang, John Mark
[7 empty] | 3 | Hire 2 additional reqs (if approved) | Q3.3 | Angada, Derchang, John Mark
|  | 3 |  |  |  |  | 1
2

## Sheet1
Objective |  | Critical Path (Interim Milestone or Sub Goal) |  |  |  |  | Key Results | [5 empty] | Comments
|  | # | Milestone | Customers | Sponsors | Dependency | # | As Measured by | ECD | Owners | Tracking | Scoring
1 | Build Predictive DTCO Flow for CMOS Logic | 1 | Assess small-circuit PPA due to material and process changes in MOL and BEOL materials and processes (L1 PPA) | Internal; Leads to Objective 1.6 | Jeff, Derchang | Hire 1 TCAD Engg by Q1.3 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 2 | Assess small-circuit PPA due to circuit-level changes (eg. Standard cell architecture / layout / circuit, fan out, Vdd, interconnect length etc) (L1 PPA) | Internal; Leads to Objective 1.6 | Jeff, Derchang | Hire 1 TCAD Engg by Q1.3 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 3 | Capable of generating PDK collateral | Internal; Leads to Objective 1.6 | Jeff, Derchang | Hire 1 TCAD Engg and Physical Design Engg by Q1.3 | 1 |  |  | Angada, Wenjie
[7 empty] | 2 |  |  | Angada, Wenjie
|  | 4 | Assess block-level PPA due to material, process, circuit-level changes (L2 PPA) | Internal; Leads to Objective 1.6 | Jeff, Derchang | Hire 1 Physical Design Engg by Q1.3; PDK collateral is available | 1 |  | Q3.2 | Angada, Chung-Chin
[7 empty] | 2 |  | Q3.3 | Angada, Chung-Chin
|  | 5 | Assess device-level (transistor) due to material and process changes (L0 PPA) | Internal; Leads to Objective 1.6 | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 | NSFET NMOS is available and calibrated to experimental data | Q3.1 | Angada
[7 empty] | 2 | NSFET PMOS is available and calibrated to experimental data | Q3.2 | Angada
|  | 6 | Provide 3 methods to improve PPA 5% |  | Jeff, Derchang |  | 1 | 2 methods proposed and PPA determined | Q4.2 | Angada
[7 empty] | 2 | 1 more method proposed and PPA determined | Q4.3 | Angada
2 | Build Predictive DTCO Flow for SRAM | 1 | Assess bit-cell level PPA due to material and process changes in MOL and BEOL materials | Internal; Leads to Objective 2.5 | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 2 | Assess array-level PPA due to material and process changes in MOL and BEOL materials | Internal; Leads to Objective 2.5 | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 3 | Assess bit-cell and array-level PPA due to material and process changes in FEOL changes | Internal; Leads to Objective 2.5 | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 4 | Assess bit-cell and array-level PPA due to layout changes | Internal; Leads to Objective 2.5 | Jeff, Derchang | Hire 2nd TCAD Engg by Q2.1 | 1 |  |  | Angada
[7 empty] | 2 |  |  | Angada
|  | 5 | Provide 3 PPA optimization options considering logic and memory heterogeniety |  | Jeff, Derchang |  | 1 | 2 methods proposed and PPA determined |  | Angada
[7 empty] | 2 | 1 more method proposed and PPA determined |  | Angada
3 |  | 1 |  |  |  |  | 1
2
3
|  | 2 |  |  |  |  | 1
2
|  | 3 |  |  |  |  | 1
2
4 | Organizational Development | 1 | Set up compute and license infrastructure |  | Jeff, Derchang |  | 1 | Identify funding source; Coordinate with the EDA team to acquire licenses | Q1.3 | Angada, Derchang, John Mark
[7 empty] | 2 | Set up compute and tool infrastructure for predictive DTCO / STCO activities | Q1.3 | Angada, Derchang, John Mark
|  | 2 | Complete hiring goals |  | Jeff, Derchang |  | 1 | Hire 3 approved reqs | Q2.3 | Angada, Derchang, John Mark
[7 empty] | 2 | Get approval for 2 additional reqs | Q1.3 | Angada, Derchang, John Mark
[7 empty] | 3 | Hire 2 additional reqs (if approved) | Q3.3 | Angada, Derchang, John Mark
|  | 3 |  |  |  |  | 1
2

## Team DerChang
Mission Statement: Explore Global Advanced Process Technology for Competitive Product Roadmap and Intercept
Objective |  | Critical Path (Interim Milestone or Sub Goal) |  |  |  |  | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | # | As Measured by | ECD | Owners | Tracking | Scoring
1 | 3DIC Pathfinding -- Modular Methodology and Decsion Process | 1 | Establish 3DIC Cookbook | FTE | Changhong | ATTD, OSAT suppliers and foundry packaging | 1 | OSATs and Foundries capability ranking completed based on the common metrics | Q1/2022 | Prashant (Lead), Max, Jason, Alois, David
[7 empty] | 2 | Risk assessed and mitigation plan developed with paper based PPAC quantification for 3D-cache (vs.incumbent) | Q2/2022 | Prashant (Lead), Angada, Stephen (?) Max, Jason
3
4
|  | 2 | Assess 3DIC roadmap and drive action to close gap for Intel Product leadership |  |  |  | 1 | 3DIC capability roadmap as manifest in 3DIC cookbook KPI | Q3/2022
2
2 | Logic/SRAM Disaggregation | 1 | Preditive DTCO for logic | FTE | Changhong | Srini, Kingsley | 1 | DTCO tool suite demostrate L1 PPA for Interconnect DTS and MTS DOE | Q1/2022 | Angada
[7 empty] | 2 | DTCO tool suite demostrate L1 PPA for GAA x'tor DTS and MTS DOE | Q2/2022 | Angada
[7 empty] | 3 | DTCO tool suite demostrate L2 PPA for circuit topo DOE | Q3/2022 | Angada
[7 empty] | 4 | DOE proposal for 5% PPA improvement using predictive DTCO tool suite | Q4/2022 | Angada
|  | 2 | Preditive DTCO for SRAM | FTE | Changhong, Chee How | Srini, Kingsley, | 1 | DTCO tool suite demostrate L1 PPA for GAA SRAM cell DTS and MTS DOE | Q2/2022 | Angada, xxx
[7 empty] | 2 | DTCO tool suite demostrate L1 PPA for GAA SRAM Array dimension design | Q3/2022 | Angada
[7 empty] | 3 | DTCO tool suite demostrate L2 PPA forcircuit topo DOE | Q3/2022 | Angada
[7 empty] | 4 | DOE proposal for 5% PPA improvement using predictive DTCO tool suite | Q4/2022 | Angada
|  | 3 | Optimized GAA for SRAM array | FTE, DEG | Changhong,Chee How, Srini, Kingsley, TY(?) | LTD, Foundry | 1 | Process flow established for GAA technology options | Q1/2022 | Prashant (Andy?)
[7 empty] | 2 | Physical layout density quantify with options selected | Q2/2022 | Prashant (Andy?)
[7 empty] | 3 | Down select with paper based PPAC benchmark | Q4/2022 | Prashant, Angada, (Andy?)
|  | 4 | MRAM LLC optionality | LTD, | Changhong,Al, Chee How, TY (?) | LTD, IMEC | 1 | Optimized MRAM Process Flow | Q1/2022 | Prashant
[7 empty] | 2 | MRAM array construted | Q2/2022 | Prashant (TD-DE)
[7 empty] | 3 | PPAC benchmark | Q4/2022
3 | Exploring foundries' technology offering by connecting product architecture | 1 | BZM logic-logic density optimization |  |  |  | 1 | 3D stack process selection
2
|  | 2 |  |  |  |  | 1
2
|  | 3 |  |  |  |  | 1
2
4 | Organization Development | 1 | Meet Organization HC Plan |  |  |  | 1 | +1 H | Q1/22
[7 empty] | 2 | +2 H | Q2/22
[7 empty] | 3 | +1 H | Q3/22
[7 empty] | 3 | +1 H | Q4/22

## to be intgrated by JM
| GEMS |  |  | FTE/FTiP
| Objective | FTE Kye Results |  | FTiP Objective | # | Milestone | Owner
1 | Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | Deliver 3CRM refresh and align with DEG/BU for Server and Client product roadmap in compliance with the GLADIUS framework (Quarterly cadence) AMB: Capability, Capacity, Cost gap/actions identified - TY/CD | 1 | 3DIC Pathfinding -- Modular Methodology and Decision Process | 1 | 3DIC Cookbook for 2.x/3D Supplier capability Ranking using common metrics Q1/22 -- Module Level (L0) Q2/22 -- Inter Module (L1) Q3/22 -- DTCO methodology Q4/22 -- Paper based L2 metric quantification capability | DerChang, Srini, Thomas
|  |  | 2 | Disaggregation methodology: Memory Subsystem & Chiplets Phy Standardization | 1 | Predictive DTCO for logic and SRAM technology exploration (GAA) and optimization (N3) Q2/22 -- L1 PPA Q3/22 -- L2 PPA Q4/22 -- 5% PPA improvement demonstrated | DerChang
[5 empty] | 2 | Cache memory disaggregation selection Q1/22 GAA based SRAM process flow and cell construct Q2/22 Array design complete and density optimized Q3/22 Down select based on PPA assessment | DerChang, Srini
[5 empty] | 3 | D2D Standardization Q1/22 Complete D2D landscape technical comparison in Q1’22 KR2: Provide engagement support for successful consortium formation KR3: Create Strategy to enable CXi on ext. foundries | Srini
[5 empty] | 4 | 3DIC PoC test vehicle Q1/22 Test chip scope defined, with DTC, PDN requirement quantified Q3/22 Test vehicle Tapeout | Srini
[5 empty] | 5 | MRAM LLC optionality Q2/22 MRAM viability based on Best In Class STTM publication Q3/22 Array design complete and density optimized Q4/22 Down select based on PPA assessment | DerChang
|  |  | 3 | G+2 Foundry Technology Engagement | 1 | Explore Advanced Foundry Technologies Q3/22 4LPP TC Tapeout Q4/22 4LPP TC success criteria assessed (500 dies) | Srini
[5 empty] | 2 | N2 Engagement Q1/22 Initiate regular N2 meeting with TSMC Define product intercept and technology requirements Q2/22 baseline PPA assessment based on PDK V0.1 Q3/22 DTCO optimization (X'tors, interconnect, 2D and 3D IP topology) Q4/22 Test chip design start | Srini

## Q2-2022
| GEMS |  |  | FTE/FTiP
| Objective | FTE Kye Results |  | FTiP Objective | # | Milestone | Owner
1 | Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | Deliver 3CRM refresh and align with DEG/BU for Server and Client product roadmap in compliance with the GLADIUS framework (Quarterly cadence) AMB: Capability, Capacity, Cost gap/actions identified - TY/CD | 1 | 3DIC Pathfinding -- Modular Methodology and Decision Process | 1 | 3DIC Cookbook for 2.x/3D Supplier capability Ranking using common metrics Q1/22 -- A metric covering physical, electrical and thermal specs Q2/22 -- 95% test structures defined for spec validation Q3/22 -- Test strcutures completed for tapeout Q4/22 -- Silicon based metric quantification to assess suppliers' capability | Max Wu,
|  |  | 2 | Disaggregation methodology: Memory Subsystem & Chiplets Phy Standardization | 1 | Predictive DTCO for N2 exploration Q2/22 -- L1 PPA Q3/22 -- L2 PPA Q4/22 -- 5% PPA improvement demonstrated | DerChang
[5 empty] | 2 | Cache memory disaggregation selection Q1/22 GAA based SRAM process flow and cell construct Q2/22 Array design complete and density optimized Q3/22 Down select based on PPA assessment | DerChang, Srini
[5 empty] | 3 | D2D Standardization Q1/22 Complete D2D landscape technical comparison in Q1’22 KR2: Provide engagement support for successful consortium formation KR3: Create Strategy to enable CXi on ext. foundries | Srini
[5 empty] | 4 | 3DIC PoC test vehicle Q1/22 Test chip scope defined, with DTC, PDN requirement quantified Q3/22 Test vehicle Tapeout | Srini
[5 empty] | 5 | MRAM LLC optionality Q2/22 MRAM viability based on Best In Class STTM publication Q3/22 Array design complete and density optimized Q4/22 Down select based on PPA assessment | DerChang
|  |  | 3 | G+2 Foundry Technology Engagement | 1 | Explore Advanced Foundry Technologies Q3/22 4LPP TC Tapeout Q4/22 4LPP TC success criteria assessed (500 dies) | Srini
[5 empty] | 2 | N2 Engagement Q1/22 Initiate regular N2 meeting with TSMC Define product intercept and technology requirements Q2/22 baseline PPA assessment based on PDK V0.1 Q3/22 DTCO optimization (X'tors, interconnect, 2D and 3D IP topology) Q4/22 Test chip design start | Srini
FTE.1
| Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | DTCO for N2
|  | 3DIC |  |  |  | N2 companion chip strategy including interaction with memory
|  | N2? |  | P2 |  | Layer 1 Srini on Design/Product requirement (gopi, brian)
Layer 2 Technology optimization for Intel's design/product
Ashuk murugavil (DE, Gary Patan)
|  | SRAM disagg |  | P1 |  | 1. Replacement of P1222.6
2
| demand |  |  |  |  | 1. Replacement of P1222.6
Interaction between logic and DRAM
execution
| team |  |  |  |  | hiring people

## OKR work sheet
| FTE Objective | FTiP Objective | Q1 | Q2 | Q3 | Q4
FTE.1 | Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business
| FTiP | 4LPP
| FTiP | N2 / 3GAP PPA
| FTiP | A winning N2 companion chip strategy including interaction with memory
|  | HCC | Technology selection based on density and process capability | SRAM process flow and cell construct | Array defined and density meeting requirement (within 10% of N2) | Down select based on PPA assessment
|  | IO and Power Supply |  | Top 3 technology candidates based on … (success critereia needed) | Signal integraity and Power delivery : Interface success criteria (pre UCIe spec) | Test Chip (planning and intelligence harvesting)
| FTiP | N2 "Design collateral" exceeds Supplier's base line capability
|  |  | Methdology inplace | N2 Logic L1 PPA | N2 Logic L2 PPA | 5% PPA improvement demonstrated
| FTiP | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics
|  |  | KR1: Module Level KPI delivered | KR2: Flow Integration (Inter Module) KPI delivered | KR3: DTCO methodology established | KR4: Paper based L2 metric quantification capability validated
FTE.2 | Meet or exceed Intel’s external capacity demand roadmap
| FTiP | P1222.61, P1222.7 Dual-drive
|  |  | Technology selected and landing zone defined for Dual-Drive | Die Size and Process Cost at 95% confidence for NPI decision for 2023 Tapein intercept |  | Die Size and Process Cost at 95% confidence for NPI decision for 2024 Tapein intercept
GF 12LP
FTE.3 | On time delivery of technology readiness, NPI and HVM ramp in external manufacturing
FTE.4 | Build a world class GEMS team with BIC talent, culture, systems & processes
| FTiP | Meeting Plan'22 HC goal
| FTiP | Strength Technical Pipeline Thru University Research

## OKR soundbite
Objective: | Actionable, Significant, Concete, Inspirational | ASCI
Key Results: | Specific, Measurable, Attainable, Relevant, Time-bound | SMART
Andy says | Yes, No, Simple