## Sheet1
Milestone | Due Date | Notes | Owner
Check In with Leads | May 25th | Status Update and Help Needed (5min per group to give a status update on TLP Pipeline assessments and any help needed) *Josh to send current pipeline tracker in email | PM
Pipeline Talent Matrix Assessments Complete | July 1st (end of Q2) | (list of candidates for Pipeline(new/removed) | Leads/HRM
Request to all managers to Declar Intent to Nominate a PE, Sr PE | July 8th, 2022 | Candidate to already be in the program, unless there is an excepetion. Managers need to make sure to check with Staff sponsor and HRM on budget | Leads/HRM
Managers Declare Intent to Nominate a PE or Sr. PE | 2022-07-29 | Request will be emailed to all managers of eligible TLPers by July 8, giving them 3 weeks to respond. | TLP Chair/PM
SMG Staff GMs Approve Their List of Candidates | 2022-08-12 | Budget Availablity determined by Staff GMs with guidnace from Staff Sponsor | BU Staff sponsor/GM
Assign PE Coaches to Candidates | 2022-08-19 | Start date, takes a few days for confirms | TLP Chair/PM
Round 1 Nomination Forms Complete | 2022-09-16 | Gives them 5 weeks after GM approval of candidates, however we recommend they start at intent to nominate if they have not already | Manager/Candidate to send to PM/TLP Chair
Round 1 Committee Review with Coaches | 2022-10-06 | Could shift based on committee availability (days not weeks) | TLP Chair/PM/Committee Members
Final Round Nomination Packages Complete | 2022-11-07 | Gives them 4 weeks from round 1 results notification | TLP Chair/PM/Committee Members
Final Round Manager Presentation to Committee | 2022-11-14 | Could shift based on committee availability (days not weeks) | TLP Chair/PM/Committee Members
Assumed date SMG Staff Needs Promo Recommendations from Committee | 2022-11-21 | Waiting on Rewards calendar from HR | TLP Chair/PM to send reccomendation to Christoph
Remainder of dates pending Rewards calendar from HR