## 2024-Q1 iMBO
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
Actionable, |  | Specific | [5 empty] | Yes
Significant |  | Measurable | [5 empty] | No
Concete |  | Attainable | [5 empty] | Simple
Inspirational |  | Relevant
Time-bound
| OKR 1: Demo FO-EB 3D interposer for cache memory and influence decision for future CCG product roadmap |  | Wafer SORT testing enablement | FTE | FTiP, FTiN | None | Dany, Vijaya |  | Finalize post-silicon preparation for wafer sort by WW05 (test programs, testing logistics) | WW06 | Q1
|  |  |  | FTE | FTiP, FTiN | None | Dany, Vijaya, Vincent, Li Feng |  | Complete single die testing by WW14 | WW14 | Q1
|  |  | Muddy Creek Final Testing Enablement | FTE | FTiP, EPAE | None | Dany, Li, Andreas |  | Finalize inteposer design, including test structures | WW12 | Q1
|  |  |  | FTE | FTiP, FTiN | None | Dany, Vijaya |  | Finalize post-silicon preparation for stacked-die testing by WW20 (test programs, testing logistics) | WW20 | Q2
|  |  |  | FTE | FTiP, FTiN | None | Dany, Vijaya, Vincent, Li Feng |  | Demonstrate stacked die functionality and PPA assessment of 25um ubump in silicon | WW32 | Q3
| OKR 2: Demo 15um ubump for SRAM chiplet integration |  | Enable 15um microbump vehicle | FTE | FTiP, EPAE | SiFO alignment | Dany, CC, Rich |  | Alignment with Samsung to support 15um design rules, deliver updated masks to support work / experiments towards 15um ubump | WW06 | Q1
|  |  |  | FTE | FTiP, EPAE | Pending successful demo on short-loop wafers | Dany, Rich, Eddie |  | Finalize design for MDC/B0 (accounting for trials | TBD | Q1?
|  |  |  | FTE | FTiP, FTiN |  | Dany, Vijaya |  | Update post-silicon prep for MDC/B0 (SORT and stacked-die config) | TBD | Q2
|  |  |  | FTE | FTiP, EPAE | OSAT alignment | Dany, Vijaya, Vincent, Li Feng |  | Demonstrate stacked die functionality and PPA assessment of 15um ubump test vehicle in silicon (need date - align schedule logic with UltraCreek) | TBD | Q2/Q3?
| OKR3: Define cachelet optionality and provide BU with options for eLLC |  | Optimize memory for low-cost | -- | FTiP | None | Dany, Rich |  | Generate PPA assessement for low-cost SRAM cache chiplet options, given floorplan constraints (TSV, ESD, bump pitch, etc) | WW08 | Q1

## 2023-Q4 iMBO
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
Actionable, |  | Specific | [5 empty] | Yes
Significant |  | Measurable | [5 empty] | No
Concete |  | Attainable | [5 empty] | Simple
Inspirational |  | Relevant
Time-bound
1 | OKR 1: Memory die tapeout and single die enablement | 1 | Single-die testing enablement | FTE | FTiP, FTiD | None | Dany, Jiajing, Ping | 1 | Muddy Creek database release | WW33 | Q3 | done |  | Execution towards tapeout
|  |  |  | FTE | FTiP, FTiN | None | Dany, Vijaya | 2 | Post-silicon preparation (test plan, probing logistics) | WW07'24 | Q1'24 | wip |  | WW06: Full loop wafers out A0 Probecard: PO sent, expecting around WW06 Test site: Still in discussion with commercial team
|  |  |  | FTE | FTiP, FTiN | None | Dany, Vijaya | 3 | Single die testing | WW12'24 | Q1'24 | prep |  | Test program in preparation
2 | OKR 2: Demo viability of using FO-EB 3D interposer for cache memory | 2 | Stacked-die FO-EB stencil capability for FTE test chips | FTE | FTiP, EPAE | SiFO | Dany, Max, Li | 1a | Finalize wafer logistics / SOW / quote with SIFO to enable Muddy Creek to proceed | WW18'24 | Q2 | done
|  |  |  | FTE | FTiP, EPAE | OSAT alignment | Dany, Max, Li | 1b | Finalize wafer logistics / SOW / quote with OSAT to enable Muddy Creek to proceed | WW46 | Q4 | wip |  | TRA completed, 1x L2 risk item, 2x L3 risk items. L2 risk item mitigation plan in place. SOW done (?)
|  |  |  | FTE | FTiP, EPAE | 1a & 1b | Dany, Li, Andreas | 2 | Interposer design tapeout | WW52 | Q4 | wip |  | Interposer design is WIP, on-track for delivery.
|  |  |  | FTE | FTiP, EPAE | SIFO timeline OSAT alignment | Dany, Max, Li | 3 | Assembly roto-rooter | WW12 | Q1'24 |  |  | Schedule need alignment with need date from SPIL
3 | OKR 3: Scaling of ubump pitch for embedded memory | 3 | Scaling of MDC to 15um bump pitch | FTE | FTiP, EPAE | None | Dany, CC | 1 | - Top metal layer definition for MDC for 15um pitch - Interposer architecture for testing MDC w/ 15um pitch | WW42 | Q4 | done |  | Definition is completed. Working on implementation (#3)
|  |  |  | FTE | FTiP, EPAE | SiFO | Dany, CC | 2 | Finalize wafer logistics / SOW / quote with SIFO to enable 15um bumping of Muddy Creek to proceed | WW52 | Q4 | wip |  | logistics aligned with Samsung, but waiting for final alignment before committing
|  |  |  | FTE | FTiP, EPAE | #2 | Dany, CC | 3 | MDC spider chip w/ 15um pitch: Database ready of MDC, updated with 15um pitch, only top layer metals changed | WW46 | Q4 | done |  | DB sent to Samsung, pending final alignment
|  |  |  | FTE | FTiP, EPAE | OSAT alignment | Dany, CC | 4 | Terrace memory interposer design w/ 15um Interposer design ready for tapeout Go/no-go decision | WW52 | Q4 |  |  | Need go/no-go decision (ROI / OSAT engagement)
4 | OKR4: Arch tech assessment for memory disaggregation | 4 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. | -- | FTiP | None | Dany, Rich | 1 | Evaluate low-cost SRAM cache chiplet options (process simplification, metal routing optimization, etc.) | WW48 | Q4 | wip, partial review in WW42 |  | Review progress on low-cost SRAM cache chiplet in WW42; need to extend to N4 and revisit metal layer needs
|  |  |  | -- | FTiP | None | Dany | 2 | Scaling roadmap beyond 2nm for SRAM vs cell topology | WW52 | Q4 | wip |  | cell topology study for roadmap scaling array topology study for stacking Cell layout generated on N2 for all topo

## 2023-Q3 iMBO
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
Actionable, |  | Specific | [5 empty] | Yes
Significant |  | Measurable | [5 empty] | No
Concete |  | Attainable | [5 empty] | Simple
Inspirational |  | Relevant
Time-bound
1 | OKR 1: Memory die tapeout and single die enablement | 1 | Single-die testing enablement | FTE | FTiP, FTiD | None | Dany, Jiajing, Ping | 1 | Muddy Creek database release | WW33 | Q3 | on-track |  | Execution towards tapeout
|  |  |  | FTE | FTiP, FTiN | None | Dany, Shibu | 2 | Post-silicon preparation (test plan, probing logistics) | WW45 | Q3
|  |  |  | FTE | FTiP, FTiN | None | Dany, Shibu | 3 | Single die testing | WW04 | Q1'24
2 | OKR 2: Demo viability of using FO-EB 3D interposer for cache memory | 2 | Stacked-die FO-EB stencil capability for FTE test chips | FTE | FTiP, EPAE | SiFO | Dany, Max, Li | 1a | Finalize wafer logistics / SOW / quote with SIFO to enable Muddy Creek to proceed | WW18 | Q2 | done
|  |  |  | FTE | FTiP, EPAE | OSAT alignment | Dany, Max, Li | 1b | Finalize wafer logistics / SOW / quote with OSAT to enable Muddy Creek to proceed | WW40 | Q3
|  |  |  | FTE | FTiP, EPAE | 1a & 1b | Dany, Li, Andreas | 2 | Interposer design tapeout | WW50 | Q4 |  |  | Schedule need alignment
|  |  |  | FTE | FTiP, EPAE | SIFO timeline OSAT alignment | Dany, Max, Li | 3 | Assembly roto-rooter | WW12 | Q1'24 |  |  | Schedule need alignment
3 | OKR 3: Scaling of ubump pitch for embedded memory | 3 | Scaling of MDC to 15um bump pitch | FTE | FTiP, EPAE | None | Dany, CC | 1 | - Top metal layer definition for MDC for 15um pitch - Interposer architecture for testing MDC w/ 15um pitch | WW40 | Q3
|  |  |  | FTE | FTiP, EPAE | SiFO | Dany, CC | 2 | Finalize wafer logistics / SOW / quote with SIFO to enable 15um bumping of Muddy Creek to proceed | WW52 | Q4
|  |  |  | FTE | FTiP, EPAE | #2 | Dany, CC | 3 | MDC spider chip w/ 15um pitch: Database ready of MDC, updated with 15um pitch, only top layer metals changed | WW52 | Q4
|  |  |  | FTE | FTiP, EPAE | #1 / #2 | Dany, CC | 4 | Terrace memory interposer design w/ 15um Interposer design ready for tapeout | WW52 | Q4
4 | OKR4: Arch tech assessment for memory disaggregation | 4 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. | -- | FTiP | None | Dany, Rich | 1 | Scaling roadmap for 2nm and beyond SRAM vs cell topology | WW40 | Q3 |  |  | cell topology study for roadmap scaling array topology study for stacking Cell layout generated on N2 for all topo
|  |  |  | -- | FTiP | None | Dany | 2 | Cache memory strategy vs integration options (cubing, vs non-stacked) | WW40 | Q3

## 2023-Q2 iMBO
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
Actionable, |  | Specific | [5 empty] | Yes
Significant |  | Measurable | [5 empty] | No
Concete |  | Attainable | [5 empty] | Simple
Inspirational |  | Relevant
Time-bound
1 | OKR 1: Disagg cache POC | 1 | Disagg cache POC | CCG | FTiP, FTiD | None | Dany, Jiajing, Ping | 1 | Electric Pond APR 1.0 release | WW17 | Q2 |  |  | Plan post-mortem for strategic planning of Muddy Creek
|  |  |  | CCG | FTiP, FTiD | Resourcing | Dany, Jiajing, Ping | 2 | Muddy Creek APR 1.0 release | WW26 | Q2 |  |  | Scope defined vs. ELP Resource secured
|  |  |  | CCG | FTiP, FTiD | None | Dany, Jiajing, Ping | 3 | Muddy Creek database release | WW33 | Q3 |  |  | WW33 is expected tapeout on SF4 Identify Muddy Creek playbook
| OKR 2: Modular 3DIC strategy for system construct | 2 | Enable FO-EB stencil capability for FTE test chips | FTE | FTiP, EPAE | SiFO | Dany, Max, Li | 1a | Finalize wafer logistics / SOW / quote with SIFO to enable Muddy Creek to proceed | WW18 | Q2 | WW18
|  |  |  | FTE | FTiP, EPAE | OSAT | Dany, Max, Li | 1b | Finalize wafer logistics / SOW / quote with OSAT to enable Muddy Creek to proceed | WW20 | Q2
|  |  |  | FTE | FTiP, EPAE | 1a & 1b | Dany, Li, Andreas | 2 | Interposer design tapeout | WW32 | Q3
|  |  |  | FTE | FTiP, EPAE | SIFO timeline | Dany, Max, Li | 3 | Assembly roto-rooter | WW50 | Q4
2 | OKR3: Arch tech assessment for memory disaggregation | 1 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. | -- | FTiP | None | Dany | 1 | Scaling roadmap for 2nm and beyond SRAM vs cell topology | WW26 | Q2 |  |  | cell topology study for roadmap scaling array topology study for stacking Cell layout generated on N2 for all topo
|  |  |  | -- | FTiP | None | Dany | 2 | Cache memory strategy vs integration options (cubing, vs non-stacked) | WW26 | Q2

## 2023-Q1 iMBO
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
Actionable, |  | Specific | [5 empty] | Yes
Significant |  | Measurable | [5 empty] | No
Concete |  | Attainable | [5 empty] | Simple
Inspirational |  | Relevant
Time-bound
1 | OKR 1: Disagg cache POC | 1 | Disagg cache POC | CCG | FTiP, FTiD | None | Dany, Jiajing, Ping | 1 | Electric Pond database release | WW08 | Q1 | WW17 | 50% | ELP database not ready by end of Q1 At RTL/APR release 0.8 by end of Q1
|  |  |  | CCG | FTiP, FTiD | None | Dany, Jiajing, Ping | 2 | ELP singulated die tests validated & meeting spec, feedback for NVL decision | WW35 | Q3
|  |  |  | CCG | FTiP, FTiD | None | Dany, Jiajing, Ping | 3 | Silicon validation in 2.3D package of ELP | WW45 | Q4
| OKR 2: Modular 3DIC strategy for system construct | 2 | Enable FO-EB stencil capability for FTE test chips | FTE | FTiP, EPAE | OSAT,SiFO | Dany, Max, Jason | 1 | Establish process flow for testchip | WW08 | Q1 | WW13 | 100% | Process flow established. Conclusion: non-feasible with TSMC shuttle Conclusion: feasible with SF4 shuttle
|  |  |  | FTE | FTiP, EPAE | OSAT,SiFO | Dany, Max, Jason | 2 | Interposer design tapeout | WW12 | Q1 |  | 25% | Interposer design started (rough placement & design rules), but gated by shuttle tapeout logistics.
|  |  |  | FTE | FTiP, EPAE | OSAT,SiFO | Dany, Max, Jason | 3 | Assembly POC on testchip | WW32 | Q2
2 | OKR3: Arch tech assessment for memory disaggregation | 1 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. | -- | FTiP | None | Dany | 1 | Matrix of Disagg. architecture design and Interface defined | WW13 | Q1 |  | 0%
|  |  |  | -- | FTiP | None | Dany | 2 | PPAC of In-Package memory options and disagg, architecture decision | WW26 | Q2

## Template
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective |  | Critical Path (Interim Milestone or Sub Goal) | [5 empty] | Key Results
|  | # | Milestone | Customers | Sponsors | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring
Actionable, |  | Specific | [5 empty] | Yes
Significant |  | Measurable | [5 empty] | No
Concete |  | Attainable | [5 empty] | Simple
Inspirational |  | Relevant
Time-bound
1 | FTE.1: Be a competitive advantage for Intel by delivering the best in the foundry/OSAT business | 1 | A winning High Capacity Cache strategy |  | FTiP, FTiD |  | Andy, Dany, Klaus, (team Kingsley) | 1 | Technology selection based on density and process capability | 2022-04-29 | Q2
[8 empty] | 2 | SRAM process flow and cell construct with patterning count on par of better than N6 1P9M | 2022-07-01 | Q2
[8 empty] | 3 | Array defined and density meeting requirement (within 10% of N2) | 2022-09-30 | Q3
[8 empty] | 4 | Down select based on PPA assessment | 2022-12-30 | Q4
|  | 2 | A winning N2 companion chip strategy |  | FTiP, FTiD |  | Klaus, Long, Stephen, Dany | 1 | Identify top 3 external technology candidates and companion chip function for N2 compute tile | 2022-07-01 | Q2
[8 empty] | 2 | Establish Technology capability meeting signal integrity and power delivery success criteria (pre UCIe spec) | 2022-09-30 | Q3
[8 empty] | 3 | Silicon Validation Plan in place | 2022-12-30 | Q4
|  | 3 | N2 "Design collateral" exceeds Supplier's baseline capability |  | FTiP, FTiD |  | Angada, Atul, Wenjie, Hank | 1 | Methodology in place | 2022-04-15 | Q2
[8 empty] | 2 | N2 Logic L1 PPA delivered and meet paper target | 2022-07-01 | Q2
[8 empty] | 3 | N2 Logic L2 PPA delivered and meet paper target | 2022-09-30 | Q3
[8 empty] | 4 | 5% PPA improvement demonstrated | 2022-12-30 | Q4
|  | 4 | 3DIC Cookbook for 2.x/3D Supplier capability and cost Ranking using common metrics |  | FTiP, EPAE |  | Max, Jason, Hank, Angada | 1 | Module Level KPI delivered | 2022-04-15 | Q2
[8 empty] | 2 | Flow Integration (Inter Module) KPI delivered | 2022-07-01 | Q2
[8 empty] | 3 | Common metric based DTCO methodology established | 2022-09-30 | Q3
[8 empty] | 4 | Paper based L2 metric quantification capability validated | 2022-12-30 | Q4
2 | FTE.2: Meet or exceed Intel’s external capacity demand roadmap | 1 | Establish ADM base die dual drive for 2023-2025 NTI intercept | Integrated and Discrete Graphics Owners and Architects | FTE |  | Mike, Max | 1 | Technology selected and landing zone defined for Dual-Drive | 2022-04-28 | Q2
[8 empty] | 2 | Die Size and Process Cost at 95% confidence for NPI decision for 2023 Tapein intercept | 2022-07-01 | Q2
[8 empty] | 3 | Die Size and Process Cost at 95% confidence for NPI decision for 2024 Tape in intercept | 2022-12-30 | Q3
3 | FTE.4 Build a world class GEMS team with BIC talent, culture, systems & processes | 1 | Meeting Plan'22 HC goal (6HC) |  | FTE |  | Angada | 1 | one Physical Design Engineer and one Memory technologies | 2022-04-29 | Q2
[8 empty] | 2 | Prashant and Peihua back fill | 2022-07-01 | Q2
[8 empty] | 3 | Two TCAD/Model Engineer | 2022-09-02 | Q3
[8 empty] | 4 | Jeff back fill | 2022-12-30 | Q4
|  | 2 | Incubate technical pipe line by collaborating with research institutes |  | FTE |  | Max, Per, Angada, Prashant | 1 | Sponsor one University Research Project on 3DIC characterization methodology and benchmark | 2022-07-01 | Q2
[8 empty] | 2 | Establish one captive research in STCO with world leaders in research consortia | 2022-09-02 | Q3