## Mid quarter pulsing
Objective | Owner | ww20 | Status | % | Q | Key Result | Comments | Q2 Owenrs' Comments
Logic Technology roadmap aligned to BU Requirements | Andy & Team | Updated | On Track | 85% | Q3'24 | prePDK L2 methodology delivered as measured by Mock A14 PDK, DK and L2 PPA (revised after Q2/shift to Q3) | Methodology identified using existing APR flows with cell mapping and RC scaling, • Full flow automation for SH demonstrated in WW34. DH automated complete WW38. DTCO cell automation under development. • SLiC to SPICE netlist methdology complete with LDE included. LIB generation methdology complete, APR with RC scalars demonstrated including BEOL My modification capability. | SLiC methdology complete, LDE included .LIB generation methdology complete, APR with RC scalars complete including BEOL stack modification. actual A14 library (w/o LDE)
|  | Updated | Behind | 25% | Q4'24 | prePDK Product-level methodology created to evaluate Mock A14 technology for CCG '28 leadership Product (Shift to Q1 '25 due to memory methodology development) | IDC, Atom, GFx, SRAM, IPG teams engaged, 16 cell L1 .LIB for IDC and working with SRAM team on 2029 Targets. • Post DEG reorg. and Core Strategy shift announcement, focus on pre-PDK technology evaluation with Cores Central Function teams and focus on methodology. From this interaction we expect to be able to produce data that the CCG and DCAI architecture teams can use influence the product roadmap. SRAM team is engaged and we are establishing pre-PDK memory targeting and evaluation methdology. | Met with all design teams, NPU architecture, and UCIe design team. Interest secured only from IDC and UCIe so far, SRAM positive but knowledge gap is too far at this point. Need to update A14 projection before reengaging. | Due to
|  | Updated | Behind | 0% | Q4'24 | BU interest in A14 secured and presented to TSMC as measured by Mock A14 evaluation for '28 Intel products (Shift to Q2 '25 due to methdology development and Core Strategy/DCAI roadmap shifts) | Requires product evaluation methdology finalized and Core Strategy,DCAI roadmap re-alignment by EOY 24 | Healthy connection to CPAD, DCAI need to re-engage following reorg.
|  | Updated | On Track | 75% | Q4'24 | Decadal Logic Technology Roadmap (A14, A10, A7, A5/CFET) as manifest in Design Rule, Compact Model with L1 PPA demonstration | Decadal TSMC roadmap completed in Q1 to A7 with L1-based PPA. Need to update based on new learning from A16 and updated A14 by EOY | Decadal TSMC roadmap completed in Q1 to A7 with L1-based PPA. Need to update based on new learning from A16 and updated A14 by EOY
Modular packaging strategy for holistic system construct | Dany & team | Updated | DONE | 100% | Q2'24 | Disagg Cache: Muddy Creek A0 yield demonstrated | • Day 1 power on 80% test validation • SORT testing completed, final yield 97%, all wafers tested and sent to Assembly for interposer build | SORT testing completed, final yield 97%, all wafers tested and sent to Assembly for interposer build
|  | Updated | DONE | 100% | Q2'24 | Disagg Cache: Muddy Creek B0 tapeout as measured by: Experiment completed, final alignment layer defined | • Tape-in in Q1, • Two DOE SL concluded 4µm Bump Opening sizing • Tapeout for final commit @ WW23.
|  | Updated | DONE | 100% | Q3'24 | Disagg Cache: Muddy Creek B0 yield demonstrated |  | Tracking for wafers back in WW26
|  | Updated | Behind | 25% | Q3'24 | Disagg Cache: Muddy Creek 25µm µB FO-3D module yield Module performance spec demonstrated |  | Tracking for assembly builds back in WW27
[5 empty] | Q4'24 | Disagg Cache: Cool Creek 15µm µB 3D module yield Module performance spec demonstrated
|  | Updated | On Track | 50% | Q4'24 | Disagg Cache: BU cachelet interests secured and presented to SiFO suppliers of choice
| CC, Dany | Updated | On Track | 90% | Q2'24 | IPM: Memory Cubing module flow and costing analyzed including TMC and VWB | Fastfail decision point #1. • VWB concluded not to proceed due to thruput and scalability • TMC Flow, costing done WW24. • TMC LLW6 $2.35/GB vs. $4.39/GB HBM4+ • Sunset decision pending, trending "continue"
|  | Updated | DONE | 100% | Q3'24 | IPM: Phy defintion for FO and 3D package @ vertical interconnect pitch of 1~25µm as manifest in Energy, transfer Rate, signaling method | Fastfail decision point #2 32Gb/die 16 die mockup model build Electrical molde (RLC, HFSS) established 15GT/s (PI/SI) capable. Thermal capability better than HBM3+, detail model based on 16Gb 64DQ die wip;
|  | Updated | On Track | 50% | Q4'24 | IPM: MIO/BU interests secured and presented to Tier-1 DRAM supplier | "Targeting Plan'25 AI-PC for LP-CAMM displacement PrePOR for TTL and Jaguar Shores. Packaing Technology Risk Management under ""One Intel"" team (GEMS, FTD, DCAI), OSAT tbd LPW with Samsung and SK Hynix under discussion"
| Long Wang, Peter Atkinson (CPAD) | Updated | On Track | 50% | Q2'24 | Modular VR: Project definition aligned with CCG/IL VR solution | Fast fail point #1 • Revised MTL DLVR MBPS -- Low risk conversion strategy established (V-Conv+DLVR) instead of DLVR only • Leadership changed. Working thru reorg; • Revised business process yet to be understood
|  | Updated | On Track | 75% | Q3'24 | Modular VR: Supply chain integration and operation model defined, suppliers aligned | Fast fail point #2 • Incorporate SCVR • Low cost suppliers id'd; cost analysis in progress and decision pending • Modular technology and scalaing path under development
[5 empty] | Q4'24 | Modular VR: BU prePOR secured with VR tile ‘test vehicle’ TO decision | Targeting Plan'25 CCG integrated VR options
Status
On Track
Behind
NOT DONE
DONE
ZBB
Updated?
Updated
ZBB

## MAR 2024
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective: Actionable, Significant, Inspirational, Concrete |  |  | Key Results: Specific, Measurable, Attainable, Relevant, Time-bound |  |  |  | Yes, No, Simple
Objective |  | Customer | Critical Path (Interim Milestone or Sub Goal) |  |  |  | Key Results
|  |  | # | Milestone | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring | Comment, Team OKR alignment
1 | Logic Technology roadmap aligned to BU Requirements | Sponsoer: Changhong Dai Customer: BU, GEMS Stakeholder: Chee How Lim Owner: DerChang Kau | 1 | 1.4nm Technology Definition for 2028 Leadership Product Definition |  | Andy Wei & Logic TD | 1 | Mock N1.4 PDK and L1 PPA |  | Q1'24
[7 empty] | 2 | L2 methodology, Mock N1.4 DK and L2 PPA |  | Q2'24 |  |  | FTE OKR
[7 empty] | 3 | Product-level (L3-like) methodology created with CCG to evaluate Mock A14 technology for CCG '28 leadership Product |  | Q3'24 |  |  | FTE OKR
[7 empty] | 4 | Product-level (L3-like) methodology created with DCAI to evaluate Mock A14 technology for DCAI '28 leadership Product |  | Q4'24
[7 empty] | 5 | BU interest secured for beyond N2 technology and presented to TSMC |  | Q4'24 |  |  | FTE OKR
|  |  | 2 | Decadal Logic Technology Roadmap as manifest in Design Rule, Compact Model with L1 PPA demonstration |  | Andy Wei & Logic TD | 1 | Mock N1 PDK and L1 PPA |  | Q2'24
[7 empty] | 2 | Mock A7 PDK and L1 PPA |  | Q3'24
[7 empty] | 3 | Mock CFET PDK and L1 PPA |  | Q4'24 |  |  | FTE OKR
Q4'24
1
2
2 | Modular 3DIC strategy for holistic system construct | Sponsoer: Changhong Dai Customer: CCG, Discrete Graphics DCAI/MIO Stakeholder: Thomas Huber Kingsley Lai, Siri Rajagopalan Chee How Lam Owner: DerChang Kau | 1 | Disaggregated cache in 2.3D and 3D advanced package POC for BU product intercept plan | ELP tapeout on N6 shuttle | Dany Ly-Gagnon & Memory Team | 1.1 | Muddy Creek A0 Yield demonstration |  | Q2'24 |  |  | FTE OKR
[7 empty] | 1.2 | Muddy Creek 25µm µB FO-EB module yield Module performance spec demonstrated |  | Q3'24 |  |  | FTE OKR
[7 empty] | 2.1 | Muddy Creek B0 TO |  | Q2'24 |  |  | FTE OKR
[7 empty] | 2.2 | Muddy Creek B0 Yield demonstration |  | Q3'24 |  |  | FTE OKR
[7 empty] | 2.3 | Cool Creek 15µm µB 3D module yield Module performance spec demonstrated |  | Q4'24 |  |  | FTE OKR
[7 empty] | 3.1 | Optimized SRAM yield "10%" saving |  | Q2'24
[7 empty] | 3.2 | BU's cachelet interest secured and presented to TSMC and SF |  | Q3'24 |  |  | FTE OKR
|  |  | 2 | Modular embeded VR Tile (above and beyond iMBO commitment) |  | Long Wang & Srini Rajagopalan | 1 | Project defintion aligned with CCG/IL VR solution |  | Q2'24 |  |  | FTE OKR candidate. Fastfail decision point #1
[7 empty] | 2 | Supply chain integration and operation model defined, suppliers aligned |  | Q3'24 |  |  | FTE OKR candidate. Fastfail decision point #2
[7 empty] | 3 | BU prePOR secured with VR tile ‘test vehicle’ TO decision |  | Q4'24 |  |  | FTE OKR candidate. Targeting Plan'25 CCG integrated VR options
|  |  | 3 | Terracd Memory Cubing for augmented High bandwidth memory (wip, funding pending) |  | CC Kuo, Klaus Goebel & Ping-Chen Liu | 1 | Memory Cubing module flow and costing analyzed including TMC and VWB |  | Q2'24 |  |  | FTE OKR candidate. Fastfail decision point #1
[7 empty] | 2 | Phy defintion for FO and 3D package @ vertical interconnect pitch of 1~25µm as manifest in Energy, transfer Rate, signaling method |  | Q2'24 |  |  | FTE OKR candidate. Fastfail decision point #2
[7 empty] | 3 | MIO/BU interests secured and presented to Tier-1 DRAM supplier |  | Q4'24 |  |  | FTE OKR candidate. Targeting Plan'25 AI-PC for LP-CAMM displacement
3 | Build Vital Pathfinding Organization for to prepare for global external Manufacturing tomorrow |  | 1 | Complete Logic Technology Pathfinding Backend and system coverage |  | Andy Wei | 1 | PDK Engineer: responsible for design flow enablement for future technology features. |  | Q1'24
[7 empty] | 2 | SoC Architect: lead system-level PPAC analysis to develop strategies and options/trade-off for monolithic and disaggregated technologies. |  | Q2'24
Under Development
oC/oP Active Cooling
CXL persistent memory

## Andy's 24 iMBO
Departmental Objective | Time-Bound Objective | Key Results | Owners | Quarter | Tracking | Scoring
Technology Roadmap for Product Architecture/Tech. Selection Decisions | 1. Logic roadmap L1 update by node | 1. Mock N1.4 update based on N2 PDK calibration | Eddie, Hank, Hanchi | Q1
1. Mock Technology Definition |  | 1. Mock N1 definition and L1 to final variant | Eddie, Hank, Hanchi | Q2
2. PPAC Assessment L1/L2 |  | 2. Mock A7 definition and L1 to final variant | Eddie, Hank, Hanchi | Q3
3. System-level implication L3 |  | 3. Mock A5 (CFET) definition and L1 to final variant | Eddie, Hank, Hanchi | Q4
4. Product architecture implication
5. Foundry interface/technology influence | 2. Build L2 methodology and capability | 1. Mock library build and characterization (SLiC and path to .lib generation) | Eddie, Hank | Q2
|  | 2. Pipeclean with existing flow (no techfile modification -- min. hack) | (Anil), Hank | Q2
|  | 3. New hire with APR and research EDA capability | (Odie, Stephen, Nij) | Q2
| 3. Build L3 system-level methodology and capability | 1. Logic block PPA technology mapping/scalars | (Vincent), Hank | Q1
|  | 2. SRAM cache macro technology mapping/scalars | (Ping), Dany, Hank | Q2
|  | 3. Overall assessment methodology, block, cache, I/O dissag. PKG, and EDA | (Chung-Ching, Max) | Q2
| 4. Product technology selection influence | 1. Identify lead products with CCG and DCAI and start WGs/demo mapping/scalars | (Chee How) | Q1
|  | 2. Apply L3 methodology to lead CCG product and assess product-level changes based on technology choices |  | Q2
|  | 3. Apply L3 methodology to lead DCAI product and assess product-level changes based on technology choices |  | Q3
|  | 4. BU interest secured and presented to TSMC BD, get meetings with RD |  | Q3
Technology Operations -- Process Technology Expertise in GEMS/DEG | 1. PDK calibration | 1. N3B PDK physical calibration including SPX deck | Hank, Hanchi, Eddie, (Jeff) | Q1
1. Calibrate models to PDK |  | 2. N2 PDK mock calibration including SPX deck | Hank, Hanchi, Eddie, (Atul) | Q1
2. Process flow and costing |  | 3. SF4 PDK physical calibration | Hank, Hanchi, Eddie | Q2
3. Monitor conferences, IMEC, equipment/EDA vendor data |  | 4. SF2 PDK mock calibration | Hank, Hanchi, Eddie, (Atul) | Q2
4. Review technology and research innovation and innovate beyond
| 2. Proces flow builds and costing | 1. N3B, N3E, N2 process flow | Hanchi (training) | Q1
|  | 2. Mock N2-SPR, A14, A10, A7 process flow | Hanchi (training) | Q1
|  | 3. Samsung SF4 and SF2 process flows | Hanchi (training) | Q2
| 3. CFET evaluation and assessment | 1. review CFET literature and IMEC assumptions and layouts | Eddie | Q2
|  | 2. CFET architectures and parasitics evaluation | Hanchi, Eddie | Q3
|  | 3. CFET process flows finalized with SPX | Hanchi | Q4

## 2023 PF iMBO Oct
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective: Actionable, Significant, Inspirational, Concrete |  |  | Key Results: Specific, Measurable, Attainable, Relevant, Time-bound |  |  |  | Yes, No, Simple
Objective |  | Customer | Critical Path (Interim Milestone or Sub Goal) |  |  |  | Key Results
|  |  | # | Milestone | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring | Comment
1 | Logic Technology roadmap aligned to BU Requirements | Sponsoer: Changhong Dai Customer: BU, GEMS Stakeholder: Chee How Lim Owner: DerChang Kau | 1 | Logic Technology Roadmap aligned to BU | DEG, MSO Partnership | Logic Team and Andy Wei | 1 | 3 year roadmap formal presentation to and feedback from BU |  | Q2 | 25% |  | FTE FTiP.1.KR1: 3 year roadmap formal presentation to and feedback from BU N2P pending N2 calibration; N2P shrink modeled N1.4 L0/L1 on 2 versions of Mockup generated; BU engagement to be started
[7 empty] | 2 | Pathfinding L0/L1 test structures implemented with N2 Test Vehicle |  | Q3 |  |  | Added
[7 empty] | 3 | Si technology high-level roadmap to year 2030 with PPAC trend |  | Q4
[7 empty] | 1 | Establish Ad hoc Technical Forum for Internal Alignment with Client Definition |  | Q3-->Q4 |  |  | 1. Draft the format from ETPP (mainly gap stopping today) 2. Development scalable trajectory instead of point solution 3. CCG and DEG teechnologists to be named
[7 empty] | 2 | Expand to next Product Segment (DC, AI or NES) |  | Q4
[7 empty] | 3 | Formalize System/External Technology Co-Pathfnding MRC |  | Q1'24
|  |  | 2 | Foundry capability Projection |  | Logic Team and Andy Wei | 1 | SF3, SF2 initial projection for 3C calibration |  | Q2 |  |  | Streched goal; move to Q2
[7 empty] | 2 | TSMC N1.4 Mockup and L1 PPAC demonstrating full node scale from N2 |  | Q3 | done |  | FTE FTiP.1 KR2: TSMC A14 Mockup and L1 PPAC demonstrating full node scale from N2 N1.4 L0/L1 on 2 versions of Mockup generated
[7 empty] | 3 | Si technology high-level roadmap to year 2030 with PPAC trend |  | Q4 |  |  | FTE FTiP.1 KR2: TSMC A14 Mockup and L1 PPAC demonstrating full node scale from N2 N1.4 L0/L1 on 2 versions of Mockup generated
|  |  | 3 | Building Core Competency for Technology assessment and predictability of competitive landscape for roadmap planning | N2 PDK assessment | Logic Team and Andy Wei | 1 | Self-consistent pathfinding methodology established |  | Q1 | done |  | FTE FTiP.1 KR3: Si technology high-level roadmap to year 2030 with PPAC trend
[7 empty] | 2 | Methodology validated With TCAD using L0, L1, L2 metric |  | Q2 | done |  | TCAD cannot be validated. Q2 focus on L0/L1 Mock vs. PDK learning
2 | Standardize Disaggregated Cache Memory | Sponsoer: Changhong Dai Customer: Bob Royer Stakeholder: Kingsley Lai, Siri Rajagopalan Owner: DerChang Kau | 1 | Disagg cache POC | ELP tapeout on N6 shuttle | Memory Team, Dany Ly-Gagnon, Ping Lu and Jiajing Wang | 1 | Electric Pond Database Release, spec validated; preliminary NVL decision made | WW08 | Q1 | no done |  | DBR not done due to resoruces Preliminary NVL decision not done; NVL Px mockup PPAC presented to CPAD; PX processor with 256MB SLC on FO-3D is cost netrual to P processor
[7 empty] | 2 | ELP sigulated die tests validated; NVL risk decision made | WW35 | Q3 |  |  | Need to replanned; POR decision pending; TSMC public MPW withdrawn due to laser ablation prohibitive to bumping process at SPIL
[7 empty] | 1 | Muddy Creek(MDC) / SF4X Tapeout |  | Q3 | Done
[7 empty] | 1 | MDC B-stepping for 15µm µB (3DIC shrink) |  | Q4
[7 empty] | 2 | MDC FO-EB package validated, meeting spec |  | Q4 |  |  | FTE FTiP.2 KR1: ELP FO-EB package validated, meeting spec; NVL POR change decision made
[7 empty] | 3 | MDC SDS functional |  | Q1'24
|  |  | 2 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. |  | Dany Ly-Gagnon, Eddie Flores | 1 | Matrix of Disagg. architecture design and Interface defined |  | Q1
[7 empty] | 2 | PPAC of In-Package memory options and disagg, architecture decision |  | Q2 | 50% |  | FTE FTiP.2 KR2: PPAC of In-Package memory options and disagg, architecture decision 4~7nm from Intel. TSMC, SF PPAC of 64,128/256MB SRAM in 2.3D-3D for NVL-PX muckup done Tasking on 10 to 28nm with memory cubing in Q2
| Modular 3DIC strategy for holistic system construct | Sponsoer: Changhong Dai Customer: Kuljit Bains GEMS & DEG Stakeholder: Thomas Huber. Srini Rajagopalan Kingsley Lai Owner: DerChang Kau | 2 | 3DIC Strategic Roadmap | ~$600K | CC Kuo and Hank Wang | 1 | TMC: Paper flow for scalable memory cube at cost lower than HBM established |  | Q1 | done |  | FTE FTiP.3 KR1: Terraced Memory Cube: Paper flow for scalable memory cube at cost lower than HBM established IP disclised (CC Kuo), High level cost assessed; detail costing pending;
[7 empty] | 2 | Preliminary Roadmap on FO and Cubing |  | Q3 |  |  | 1. Scalable Disaggregation Model Development; Disaggregation Classification and Connectivity 2. With MIO and division endorsemet
[7 empty] | 3 | 3DIC Roadmap’24 and JDP proposal ratified |  | Q4
4 | Build Vital Pathfinding Organization for to prepare for global external Manufacturing tomorrow |  | 1
2
3
4

## 2023 PF iMBO July
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective: Actionable, Significant, Inspirational, Concrete |  |  | Key Results: Specific, Measurable, Attainable, Relevant, Time-bound |  |  |  | Yes, No, Simple
Objective |  | Customer | Critical Path (Interim Milestone or Sub Goal) |  |  |  | Key Results
|  |  | # | Milestone | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring | Comment
1 | Logic Technology roadmap aligned to BU Requirements | Sponsoer: Changhong Dai Customer: BU, GEMS Stakeholder: Chee How Lim Owner: DerChang Kau | 1 | Logic Technology Roadmap aligned to BU | DEG, MSO Partnership | Logic Team and Andy Wei | 1 | 3 year roadmap formal presentation to and feedback from BU |  | Q2 | 25% |  | FTE FTiP.1.KR1: 3 year roadmap formal presentation to and feedback from BU N2P pending N2 calibration; N2P shrink modeled N1.4 L0/L1 on 2 versions of Mockup generated; BU engagement to be started
[7 empty] | 2 | Pathfinding L0/L1 test structures implemented with N2 Test Vehicle |  | Q3 |  |  | Added
[7 empty] | 3 | Si technology high-level roadmap to year 2030 with PPAC trend |  | Q4
[7 empty] | 1 | Establish Ad hoc Technical Forum for Internal Alignment with Client Definition |  | Q3 |  |  | 1. Draft the format from ETPP (mainly gap stopping today) 2. Development scalable trajectory instead of point solution 3. CCG and DEG teechnologists to be named
[7 empty] | 2 | Expand to next Product Segment (DC, AI or NES) |  | Q4
[7 empty] | 3 | Formalize System/External Technology Co-Pathfnding MRC |  | Q1'24
|  |  | 2 | Foundry capability Projection |  | Logic Team and Andy Wei | 1 | SF3, SF2 initial projection for 3C calibration |  | Q2 |  |  | Streched goal; move to Q2
[7 empty] | 2 | TSMC N1.4 Mockup and L1 PPAC demonstrating full node scale from N2 |  | Q3 | 33% |  | FTE FTiP.1 KR2: TSMC A14 Mockup and L1 PPAC demonstrating full node scale from N2 N1.4 L0/L1 on 2 versions of Mockup generated
[7 empty] | 3 | Si technology high-level roadmap to year 2030 with PPAC trend |  | Q4 |  |  | FTE FTiP.1 KR2: TSMC A14 Mockup and L1 PPAC demonstrating full node scale from N2 N1.4 L0/L1 on 2 versions of Mockup generated
|  |  | 3 | Building Core Competency for Technology assessment and predictability of competitive landscape for roadmap planning | N2 PDK assessment | Logic Team and Andy Wei | 1 | Self-consistent pathfinding methodology established |  | Q1 | done |  | FTE FTiP.1 KR3: Si technology high-level roadmap to year 2030 with PPAC trend
[7 empty] | 2 | Methodology validated With TCAD using L0, L1, L2 metric |  | Q2 |  |  | TCAD cannot be validated. Q2 focus on L0/L1 Mock vs. PDK learning
2 | Standardize Disaggregated Cache Memory | Sponsoer: Changhong Dai Customer: Bob Royer Stakeholder: Kingsley Lai, Siri Rajagopalan Owner: DerChang Kau | 1 | Disagg cache POC | ELP tapeout on N6 shuttle | Memory Team, Dany Ly-Gagnon, Ping Lu and Jiajing Wang | 1 | Electric Pond Database Release, spec validated; preliminary NVL decision made | WW08 | Q1 | no done |  | DBR not done due to resoruces Preliminary NVL decision not done; NVL Px mockup PPAC presented to CPAD; PX processor with 256MB SLC on FO-3D is cost netrual to P processor
[7 empty] | 2 | ELP sigulated die tests validated; NVL risk decision made | WW35 | Q3 |  |  | Need to replanned; POR decision pending; TSMC public MPW withdrawn due to laser ablation prohibitive to bumping process at SPIL
[7 empty] | 1 | Muddy Creek(MDC) / SF4X Tapeout |  | Q3
[7 empty] | 2 | MDC FO-EB package validated, meeting spec |  | Q4 |  |  | FTE FTiP.2 KR1: ELP FO-EB package validated, meeting spec; NVL POR change decision made
[7 empty] | 3 | MDC SDS functional |  | Q1'24
|  |  | 2 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. |  | Dany Ly-Gagnon, Eddie Flores | 1 | Matrix of Disagg. architecture design and Interface defined |  | Q1
[7 empty] | 2 | PPAC of In-Package memory options and disagg, architecture decision |  | Q2 | 50% |  | FTE FTiP.2 KR2: PPAC of In-Package memory options and disagg, architecture decision 4~7nm from Intel. TSMC, SF PPAC of 64,128/256MB SRAM in 2.3D-3D for NVL-PX muckup done Tasking on 10 to 28nm with memory cubing in Q2
| Modular 3DIC strategy for holistic system construct | Sponsoer: Changhong Dai Customer: Kuljit Bains GEMS & DEG Stakeholder: Thomas Huber. Srini Rajagopalan Kingsley Lai Owner: DerChang Kau | 2 | 3DIC Strategic Roadmap | ~$600K | CC Kuo and Hank Wang | 1 | TMC: Paper flow for scalable memory cube at cost lower than HBM established |  | Q1 | done |  | FTE FTiP.3 KR1: Terraced Memory Cube: Paper flow for scalable memory cube at cost lower than HBM established IP disclised (CC Kuo), High level cost assessed; detail costing pending;
[7 empty] | 2 | Preliminary Roadmap on FO and Cubing |  | Q3 |  |  | 1. Scalable Disaggregation Model Development; Disaggregation Classification and Connectivity 2. With MIO and division endorsemet
[7 empty] | 3 | 3DIC Roadmap’24 and JDP proposal ratified |  | Q4
4 | Build Vital Pathfinding Organization for to prepare for global external Manufacturing tomorrow |  | 1
2
3
4

## 2023 PF iMBO Rev Apr.
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective: Actionable, Significant, Inspirational, Concrete |  |  | Key Results: Specific, Measurable, Attainable, Relevant, Time-bound |  |  |  | Yes, No, Simple
Objective |  | Customer | Critical Path (Interim Milestone or Sub Goal) |  |  |  | Key Results
|  |  | # | Milestone | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring | Comment
1 | Logic Technology roadmap aligned to BU Requirements | Sponsoer: Changhong Dai Customer: BU, GEMS Stakeholder: Chee How Lim Owner: DerChang Kau | 1 | Logic Technology Roadmap aligned to BU | DEG, MSO Partnership | Logic Team and Andy Wei | 1 | 3 year roadmap formal presentation to and feedback from BU |  | Q2 | 25% |  | FTE FTiP.1.KR1: 3 year roadmap formal presentation to and feedback from BU N2P pending N2 calibration; N2P shrink modeled N1.4 L0/L1 on 2 versions of Mockup generated; BU engagement to be started
[7 empty] | 2 | Pathfinding L0/L1 test structures implemented with N2 Test Vehicle |  | Q3 |  |  | Added
[7 empty] | 3 | Si technology high-level roadmap to year 2030 with PPAC trend |  | Q4 |  |  | FTE FTiP.1 KR3: Si technology high-level roadmap to year 2030 with PPAC trend
|  |  | 2 | Foundry capability Projection |  | Logic Team and Andy Wei | 1 | SF3, SF2 initial projection for 3C calibration |  | Q2 |  |  | Streched goal; move to Q2
[7 empty] | 2 | TSMC N1.4 Mockup and L1 PPAC demonstrating full node scale from N2 |  | Q3 | 25% |  | FTE FTiP.1 KR2: TSMC A14 Mockup and L1 PPAC demonstrating full node scale from N2 N1.4 L0/L1 on 2 versions of Mockup generated
|  |  | 3 | Building Core Competency for Technology assessment and predictability of competitive landscape for roadmap planning | N2 PDK assessment | Logic Team and Andy Wei | 1 | Self-consistent pathfinding methodology established |  | Q1 | done
[7 empty] | 2 | Methodology validated With TCAD using L0, L1, L2 metric |  | Q2 |  |  | TCAD cannot be validated. Q2 focus on L0/L1 Mock vs. PDK learning
2 | Standardize Disaggregated Cache Memory | Sponsoer: Changhong Dai Customer: Bob Royer Stakeholder: Kingsley Lai, Siri Rajagopalan Owner: DerChang Kau | 1 | Disagg cache POC | ELP tapeout on N6 shuttle | Memory Team, Dany Ly-Gagnon, Ping Lu and Jiajing Wang | 1 | Electric Pond Database Release, spec validated; preliminary NVL decision made | WW08 | Q1 | no done |  | DBR not done due to resoruces Preliminary NVL decision not done; NVL Px mockup PPAC presented to CPAD; PX processor with 256MB SLC on FO-3D is cost netrual to P processor
[7 empty] | 2 | ELP sigulated die tests validated; NVL risk decision made | WW35 | Q3 |  |  | Need to replanned; POR decision pending; TSMC public MPW withdrawn due to laser ablation prohibitive to bumping process at SPIL
[7 empty] | 3 | ELP FO-EB package validated, meeting spec; NVL POR change decision made | WW45 | Q4 |  |  | FTE FTiP.2 KR1: ELP FO-EB package validated, meeting spec; NVL POR change decision made
|  |  | 2 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. |  | Dany Ly-Gagnon, Eddie Flores | 1 | Matrix of Disagg. architecture design and Interface defined |  | Q1
[7 empty] | 2 | PPAC of In-Package memory options and disagg, architecture decision |  | Q2 | 50% |  | FTE FTiP.2 KR2: PPAC of In-Package memory options and disagg, architecture decision 4~7nm from Intel. TSMC, SF PPAC of 64,128/256MB SRAM in 2.3D-3D for NVL-PX muckup done Tasking on 10 to 28nm with memory cubing in Q2
3 | Modular 3DIC strategy for holistic system construct | Sponsoer: Changhong Dai Customer: Kuljit Bains GEMS & DEG Stakeholder: Thomas Huber. Srini Rajagopalan Kingsley Lai Owner: DerChang Kau | 1 | Scalable Disaggregation Model Development |  | Dany Ly-Gagnon, Max Wu, Jason Zhang | 1 | Disaggregation Classification and Connectivity |  | Q3
|  |  | 2 | OSAT/SiFO Technology Capability Projection | ~$600K | CC Kuo and Hank Wang | 1 | TMC: Paper flow for scalable memory cube at cost lower than HBM established |  | Q1 | done |  | FTE FTiP.3 KR1: Terraced Memory Cube: Paper flow for scalable memory cube at cost lower than HBM established IP disclised (CC Kuo), High level cost assessed; detail costing pending;
[7 empty] | 2 | Preliminary Roadmap on FO and Cubing |  | Q3
|  |  | 3 | 3DIC Strategic Roadmap |  |  | 1 | 3DIC Roadmap’24 and JDP proposal ratified |  | Q4
4 | Build Vital Pathfinding Organization for to prepare for global external Manufacturing tomorrow |  | 1
2
3
4

## 2023 PF iMBO Rev Jan
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective: Actionable, Significant, Inspirational, Concrete |  |  | Key Results: Specific, Measurable, Attainable, Relevant, Time-bound |  |  |  | Yes, No, Simple
Objective |  | Customer | Critical Path (Interim Milestone or Sub Goal) |  |  |  | Key Results
|  |  | # | Milestone | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring | Comment
1 | Logic Technology roadmap aligned to BU Requirements | Sponsoer: Changhong Dai Customer: BU, GEMS Stakeholder: Chee How Lim Owner: DerChang Kau | 1 | Logic Technology Roadmap aligned to BU | DEG, MSO Partnership | Logic Team and Andy Wei | 1 | 3 year roadmap formal presentation to and feedback from BU |  | Q2 |  |  | FTE FTiP.1.KR1: 3 year roadmap formal presentation to and feedback from BU
[7 empty] | 2 | Si technology high-level roadmap to year 2030 with PPAC trend |  | Q4 |  |  | FTE FTiP.1 KR3: Si technology high-level roadmap to year 2030 with PPAC trend
|  |  | 2 | Foundry capability Projection |  | Logic Team and Andy Wei | 1 | SF3, SF2 initial projection for 3C calibration |  | Q1
[7 empty] | 2 | TSMC A14 Mockup and L1 PPAC demonstrating full node scale from N2 |  | Q3 |  |  | FTE FTiP.1 KR2: TSMC A14 Mockup and L1 PPAC demonstrating full node scale from N2
|  |  | 3 | Building Core Competency for Technology assessment and predictability of competitive landscape for roadmap planning | N2 PDK assessment | Logic Team and Andy Wei | 1 | Self-consistent pathfinding methodology established |  | Q1
[7 empty] | 2 | Methodology validated With TCAD using L0, L1, L2 metric |  | Q2
2 | Standardize Disaggregated Cache Memory | Sponsoer: Changhong Dai Customer: Bob Royer Stakeholder: Kingsley Lai, Siri Rajagopalan Owner: DerChang Kau | 1 | Disagg cache POC | ELP tapeout on N6 shuttle | Memory Team, Dany Ly-Gagnon, Ping Lu and Jiajing Wang | 1 | Electric Pond Database Release, spec validated; preliminary NVL decision made | WW08 | Q1
[7 empty] | 2 | ELP sigulated die tests validated; NVL risk decision made | WW35 | Q3
[7 empty] | 3 | ELP FO-EB package validated, meeting spec; NVL POR change decision made | WW45 | Q4 |  |  | FTE FTiP.2 KR1: ELP FO-EB package validated, meeting spec; NVL POR change decision made
|  |  | 2 | In-Package Memory Cookbook -- Optimized memory processes, packaging technology and DFT/DFM features. |  | Dany Ly-Gagnon, Eddie Flores | 1 | Matrix of Disagg. architecture design and Interface defined |  | Q1
[7 empty] | 2 | PPAC of In-Package memory options and disagg, architecture decision |  | Q2 |  |  | FTE FTiP.2 KR2: PPAC of In-Package memory options and disagg, architecture decision
3 | Modular 3DIC strategy for holistic system construct | Sponsoer: Changhong Dai Customer: Kuljit Bains GEMS & DEG Stakeholder: Thomas Huber. Srini Rajagopalan Owner: DerChang Kau | 1 | FO-EB stencil for FTE test chips |  | Dany Ly-Gagnon, Max Wu, Jason Zhang | 1 | FO-EB Stencil Database Release/TO | WW12 | Q1
[7 empty] | 2 | FO-EB Stencil package validated L1D (physical) /L1E (electrical) spec met | WW32 | Q3 |  |  | FTE FTiP.3 KR3: FO-EB Stencil package validated (L1D/L1E spec met)
|  |  | 2 | Terraced Memory Cube (TMC) -- A modular 3DIC integration with a remix of mainstream logic, memory and 3DIC technologies | ~$600K | CC Kuo and Hank Wang | 1 | TMC: Paper flow for scalable memory cube at cost lower than HBM established |  | Q1 |  |  | FTE FTiP.3 KR1: Terraced Memory Cube: Paper flow for scalable memory cube at cost lower than HBM established
[7 empty] | 2 | 2 die stacking L1D/L1E demonstrated |  | Q3
[7 empty] | 3 | 4 die stacking L1D/L1E demonstrated if needed |  | Q4 |  |  | FTE FTiP.3 KR2: Terraced Memory Cube: die stacking L1D (Physical) /L1E(Electrical) demonstrated
4 | Build Vital Pathfinding Organization for to prepare for global external Manufacturing tomorrow |  | 1
2
3
4

## Template
Mission Statement: Explore advanced technologies and modular integration for predictable and competitive product roadmap
Objective: Actionable, Significant, Inspirational, Concete |  | Key Results: Specific, Measurable, Attainable, Relevant, Time-bound |  |  |  | Yes, No, Simple
Objective | Eco System | Critical Path (Interim Milestone or Sub Goal) |  |  |  | Key Results
|  | # | Milestone | Dependency | Owners | # | As Measured by | ECD | Quarter | Tracking | Scoring | Comment
1 | – Chartering Group: team accountable for results – Sponsor: Typically the leader of chartering team – Customer: Recipients of the project outcome – Stakeholders: affect or affected by the projects. – Other dependency/support for execution | 1 |  |  |  | 1
2
|  | 2 |  |  |  | 1
|  | 3 |  |  |  | 2
2 |  | 1 |  |  |  | 1