## Slide 1: Series 30 3DXP IM JDP SOW
Version 1.3
Jan 12th, 2018

## Slide 2: Signature Page
This SxP Joint Development Program Statement of Work Rev 1.3 (“30s SxP Memory SOW”), having been approved by the JDP Committee is hereby approved by Intel and Micron respectively effective as of XX YY, 2018, as signified by the signature of each company’s authorized representative below. It is understood and agreed that this JDP SOW may be amended in due course in accordance with the procedures set forth in the Joint Development Program Agreement.
MICRON TECHNOLOGY, INC. INTEL CORPORATION
By: By:
Name: Name:
Date: Date:

## Slide 3: Revision Page
Approval Date | REV | Pages Affected | Was | Is | Comments
06-23-2016 | 0.5 | ALL |  | 30s 3DXP Pathfinding SOW | 
10-14-2016 | 0.6 | Signature Page & Revision page |  | Moves effective date to 10/14 and adds termination language | 
01-27-2017 | 0.7 | Signature & Revision page, Dates in Sections 0.0, 3.0 and 4.0 (deliverables for Final SOW) |  | Extends SOW to 8/31/17 and changes dates in section 0.0, 3.0 and 4.0 accordingly to align with current program status | Both partners extended the pathfinding SOW on a month-to-month basis till Feb 2nd, 2018.
 | 1.3 | ALL |  | 30s 3DXP SOW | 
Notes: 3

## Slide 4: SOW Contacts
Al Fazio Intel JDP co-manager
Russ Meyer Micron JDP co-manager
Greg Atwood Micron Design
Naga Chandrasekaran Micron TD
Matt Goldman Intel Design
Stephen Keeney Intel Product
Fabio Pellizzer Micron TD
Shafqat Ahmed Intel TD

## Slide 5: SOW Contents
0.0 SOW purpose
1.0 Strategy Overview
  1.1 Scaling/Product Strategy
  1.2 Scaling Roadmap
2.0 Project Milestones
3.0 30s Cost/GB Scaling
  3.1 S37A die size and Risks
  3.2 30s Cost/GB projection
4.0 Proc. Dev. Challenges
  Array/Cell scaling
  CMOS/BEOL enablers
  Process Arch summary
  Development vehicles
  Risk Areas & mitigation path
  Periphery Development Model
5.0 Design SOW
  Key design features
  30s Product Envelope
  Strategy
  Arch/ Chop Strategy
  Milestones
6.0 Product Development SOW
  Alpha product strategy
  Reliability and Assembly scope
7.0 Development Budget

## Slide 6: 0.0 SOW Purpose
To define and communicate the 3DXP scaling roadmap and development strategy to enable the 3rd generation, 30s product (S37A).
To define project deliverables
To define milestones and performance metrics to track the progress towards the deliverables
To define the resource allocation and budget to achieve the targeted deliverables

## Slide 7: 1.0 Strategy Overview

## Slide 8: 1.1: Scaling / Product Strategy
WL/BL pitch scaling (41nm 28nm) to enable 2x density with similar or smaller die size (< 200 mm2)
  Stay with 4-decks and take advantage of the die (Quilt) and process architecture (stacked via for strapped WL) from 20-series
Enable DDR5 like performance (1600MT/s   3200 MT/s)
  Need to achieve >50% reduction in read energy per bit to maintain the operating power window (2x read bandwidth  50% read energy)
  Target 50% reduction in write energy per bit to also maintain power parity when saturating the bus with write operations (3200MT/s for a given multi-die package)
Increase concurrency (24 partitions  32 partitions) to support maximum write bandwidth per die (800MB/s  1100MB/s). Higher write bandwidth will also be evaluated.
The Array, CMOS and Cu/Low-k (MOL) process development needs will be accommodated by S36X (2-deck spider chip based on S26A) and XP03-Rev2 (CMOS & BEOL test chip) vehicles, respectively

## Slide 9: 1:2 3DXP Scaling Roadmap
10s 3DXP / S15C
Pitch: 41nm pitch
Decks: 2
Tile Arch: Staggered WL
Density: 128Gb
20s 3DXP / S26
Pitch: 41nm pitch
Decks: 4
Tile Arch: Staggered WL & BL w/ Quilt
Density: 256Gb
30s 3DXP / S37
Pitch: 28nm pitch
Decks: 4
Tile Arch: Staggered WL & BL w/ Quilt
Density: 512Gb
20s Goals:
1. Minimize array/cell/periphery dev 2. Faster time to market
3. ~35% lower cost/GB
4. ~30% lower energy (pJ/bit)
4 Deck, Quilt Arch Learning
S15X (emulates 4x WL Cap)
XS26A (patterning vehicle)
XP01 (mini-array, CMOS)
S15A, S15B
Dev Vehicles
Alpha Product
30s Goals:
1. Focus on WL/BL pitch scaling
2. Stay with 20s array and quilt arch
3. > 35% lower cost/GB
4. ≥ 50% or more energy reduction(pJ/bit)
5. 3200-4800 MT/Sec IO
4128nm Pitch Learning
XP03-Rev2 (CMOS / Interconnect dev, design IP)
S36X (Spider chip based on S26A w/ Quilt Arch)

## Slide 10
2.0 High Level Milestones
# | Milestone | Date
1 | S36X TO (Aug, 17) & Si start | Jan, ‘18
2 | XP03 TO (May, ’17 - Done) XP03-Rev21 TO (F11X/F2 version) | March, ’18
3 | 30s Final Collateral (DR/Model) release | June, ‘18
4 | S37A data base release | Dec., ’18
5 | S37A Storage Qual | March, ‘20
6 | S37A Memory Qual | June, ‘20
1XP03-Rev2 is the F11X/F2 version of XP03. XP03-Rev2 will have updated LV CMOS structures and scribe features compatible with both F11X and F2 patterning/ metrology.

## Slide 11: 3.0 30s Cost/GB Reduction

## Slide 12: S37A Die Size and Risks
S37A Arch Risk/Status:
Fit all the necessary CMOS under the much smaller Tiles
  Aggressive HV CMOS scaling not yet fully vetted
  WL/BL driver current requirement based on speculative cell DTS
Metal Routability analysis not complete
  Additional scaling of BEOL design rules may be required
S37A Die size projected to match S26A: ~195-199mm2
  12.7mm x 15.6mm
  4Kx4K Tile, 4-deck, 32-partitions, Quilt Arch

## Slide 13: 30s Cost/GB (Unconstrained Floor Space)
Green Field Cost Comparison Table
Product | Decks | Density (GB) | Die Size (mm2) | DPW | Yield | Wafer Cost* | Cost/GB | Cost Reduction
S26A | 4 | 32 | 199.1 | 306 | 80% | $2,443 | $0.31 | N/A
S37A* | 4 | 64 | 199.1 | 306 | 80% | $3, 047 | 0.19 | 37.6%
Note:
Assumptions of the preliminary 30s MOR flow
Triple-Gox, dual-spacer, 3 extra implants, & stressor films for CMOS
$100/wf cost adder for SiGe epi and low-K (place holder)
Additional complexity of the 14nm array process is simulated by adding one more de-integrated etch step per WL/BL level (~$200/wf total cost adder - a placeholder for additional films/CMP/etch needs for array).
* Includes $400 fixed OH

## Slide 14: 4.0 Process Arch Challenges

## Slide 15: 4.1: Array/Cell Scaling
Item | Working Assumption / Status | Strategy / Key Enabling Factors
WL / BL Patterning | Pitch-quad (PQ) for 14nm line and space. | 1. Start with PQ BKMs from other technologies in HVM 2. Maintaining virgin/undamaged PM/SD properties will require optimization of liner, seal, clean and dry etch development: Dry etch needs to enable higher aspect ratio stack etch, maintain profile and minimize PM undercut Partial liner and seal conformality, quality, etch robustness, interaction with PM/SD need to be optimized. May need cluster tool w/o vacuum break, as cell volume to surface area ratio decreases. Potential voiding, shrinkage issues with CSOD 3. Higher aspect ratio stack increases risk for toppling/ structural integrity and needs to be managed through film thickness, adhesion, stress optimization.
WL / BL /Via Resistance | Tile with Quilt Architecture: R per cell (vs. 20s) < 1.67x increase req for 4kx4k | Change in CD is offset by identical reduction in WL/ BL length (for 4kx4k). Key issue is the thin film effect: Explore techniques to reduce W resistivity or new material with Low R Need to quantify 30s WL/BL R before committing to a tile arch Explore via resistance reduction (e.g. WSiN removal from OPV)
On Pitch Via (OPV) | OPV scaling from 28nm20nm (top) | Increase post-litho CD reduction and tighter reg budget (5nm, stacked)
Vt Window / Disturb | Same Vt, thermal and read disturb window as 20s | Smaller cell area and reduced space expected to degrade RWB and may be more prone to disturb. Set-ability / set-speed vs. thermal disturb trade-offs need to be managed. Need to explore new SD, PM composition to buy back window and maintain Set/Reset algo timing.
Cell Current | All currents (SET, RESET, SSR, iHOLD, leakage) scale down by 40% | Set / Reset currents are expected to scale with area or volume. However, iHold and leakage assumptions are riskier. All current assumptions require validation before Rev1 design freeze
Von | Same Von as 20s at 40% lower current | 
Set-Reset | Same set-reset pulse times as 20s | 
Cell Capacitance | Same as 20s. | WL to WL and BL to BL space are scaled. However, WL and BL length (for 4kx4k) tile size is scaled by the same factor to offset the increase.

## Slide 16
Item | Working Assumption/Status | Strategy | Key Enabling Factors (to be evaluated)
Tile Size / Array Arch | 4kx4k tile with Quilt Architecture. | To fit HV CMOS under tile, perf enhancement (drive current/um) and tighter DRs are needed. Scaled metal pitch and/or more metal layers will be required for socket hook-up, local/global signal routing. Re-architect/redesign the select logic to optimize the layout and interconnect required Re-architect/re-optimize under tile circuits (current mirror, sense amp, tile logic, VDM generation & control logic, level shifters) to reduce device count and make use of MVTs (90A CMOS) | Isolation scaling (STI/Well DRs) Triple Gate Oxide Stressor liner Contact DR scaling Dual-damascene, pitch doubled, W M5
Energy | Set a goal of 50% pJ/bit energy reduction over S26A | Define pad and internal voltages based on Read, pump-in Write voltages as needed Lower Vcc Lower HV Cgate (or load) by transistor W scaling Routing cap reduction | Lower Vpp/Hpvpp Lower Vnn/Hnvnn Lower Vcc (1.2  1.1V) Lower Cgate (or device width) through HV & LV perf improvements Low-k dielectric (~3.0) for key signal paths and/or metal thickness scaling
IO Perf. | ≥3200 MT/s (DDR5) level IO performance | Delivering ≥3200 MT/sec requires significant LV CMOS perf improvement while Vcc is scaled: Lower Cgate / Cmiller and higher drive current Redesign/re-optimize the pad to array speed critical paths to reduce logic and clock latency Re-optimize high speed circuits to manage reduced timing margins while balancing active and idle power costs Benchmark 30s CMOS specs against comparable technologies and evaluate design BKMs | Tox (2312A), Lgate (8040-50nm) scaling Junction scaling/ optimization Low-temperature Dual Spacer SiGe Epi for PMOS S/D Stressor liner Stress Memorization Technique (SMT) NiSi
4.2: CMOS/BEOL Enablers of Product Spec

## Slide 17
4.3: Process Architecture Summary
Area | 10s / 41nm pitch / 2-deck S15C 2Kx4K Tile | 20s / 41nm pitch / 4-deck S26A 4Kx4K Tile | 30s / 28nm Pitch / 4-deck S37A 4Kx4K Tile
CMOS | 19 mask levels Dual gate CMOS (23A/110A) | No change from 10s HV CMOS width scaling | ~23-27 mask levels (TBD) STI / Isolation scaling Tri-Gate CMOS (12A/90A/110A) Poly CD scaling (80 40nm) Dual spacer Stressor liner / SMT SiGe Epi/ NiSi Borderless Contact
M1-M4 (Cu) | M1 single-damascene Cu M2-M4 dual-damascene Cu All 193-dry levels | M1, M4 single damascene Cu M2-M3 dual damascene Cu V3 and M4 goes 193i (+2) | M1 single damascene Cu M2-M4 dual damascene Cu, w/ low-k ILD (e~~3.0) V3 / M4 goes back to 193-dry M5 is added: dual-damascene, PD, V4/M5 193i
Array levels | 2 decks  4 PD levels 3 OPV levels 7 193i levels for array | 4 decks  8 PD levels 5 OPV levels 13 193i levels for array | 4 decks  8 PQ levels 5 OPV levels 13 193i levels for array
Top Metal / Passivation | Thick Al, SiO2+SiON Passivation, Polyimide | No Change | No Change
Summary / Comments | Total of 7 193i level OPV levels require CD shrink | Total of 15 193i level. 41nm L/S Cu M4 in X-&Y-dir. requires process dev (Photo/PVD/Plating) New chop schemes and stacked OPV are key process development areas for array. | Total of 15 to 16 193i level 8 layers goes from PD to PQ Added 1 more interconnect (M5) under array M2-M4 Cu layers may require low-k ILD Array development will need to look into new PM/SD composition, seal, liner, etch processes Increased scope for periphery development for under tile fitting, energy and IO perf

## Slide 18: 4.4: Development Vehicles
Name | Why | Description | Projected DBR Date
S36X | Array process and 14nm cell learning 14nm WL/BL R | Based on S26A FEOL design up to M4 Additional V4/M5 “glue layers” 2 decks of 14nm array over S26A WL/BL drivers | Aug, ’17 (done)
XP03-Rev2 | CMOS scaling and Low-K BEOL development | Full suite of CMOS and BEOL test structures | March,’18 (F11X/F2 compatible)
S37A | Alpha product | 4k x 4k Tile, Quilt architecture | Dec, ‘18

## Slide 19: 4.5: Identified Risk Areas & mitigation paths from Pathfinding
Area | Issue | Current Focus
Current Delivery | Ireset delivery to far cells a concern based on voltage and CuA assumptions | Reduce path resistance – focus array via R reduction, chzn of WL/BL resistance (1st/cut, 2nd cut)., HV improvement opportunities, viability of lower current req. for cell
CuA Fit for 1x128 partition (S36A) | 4% gap to fitting all CMOS under tile. | Design rule / scaling opportunities for isolation / contact placement, etc.
LV improvement Path | Gap in leakage and/or perf | Adopt LV logic transistors from Intel logic
Array scaling enablers | Mitigation path for thermal / read disturb. How to achieve reduction in cell current reqs Read voltage reduction with E2 drift/shift/evo reduction Capability for full-stack PQ capability at 14nm | Several pathfinding/x-functional teams (process/ design) working to resolve key issues - including – (1) material/doping changes for Electrode/PM/SD (2) WSiN removal from array via (3) CMOS enhancements (4) Improvements in seal/fill, etc.

## Slide 20: 4.6: Periphery Development Model
To alleviate risk to schedule and reduce # of process transfers, the 30s SXP CMOS and Low-K/Cu modules will be developed at F11X (Intel-NM).
A new version of XP03 (Rev2) will be taped out for F11X (Intel-NM fab) to perform the following development and integration work –
  Integration of MV/ HV transistors into 65nm logic process flow
  Adopt 30s SXP design rules and ILD heights required for metal/via processing into 45nm logic low-k based Cu flow
After the development work is completed, the process modules/ flow will be directly transferred to IMFT (F2). For some modules, where similar tool-sets already exist, this may require further matching/re-development work by the JDP partners in IMFT.
High-level deliverables and transfer scheme is outlined in the following slides

## Slide 21: CMOS & Interconnect: Development Scope
Module | Logic base process | 30s SXP Development Need
STI | 1.2V isolation req | 5V isolation w/ 90nm AA-to-AA: achieved with 3.2K trench depth and well implant optimization. Optimize gap-fill with HARP oxide.
Gate / Poly | 12A Gate with RTN Poly etch angle > 88 40-50nm poly CD | Assess HV Ox rel with RTN and optimize if needed. Move poly patterning to 193i for ease of patterning.
Spacer | Low-temp BTBAS Spacer | LV and HV will require diff. spacer thicknesses Need to develop integration scheme that works for both transistors (manage GIDL)
SiGe | Dry/Wet chemistry for Si etch Low-temp SiGe Epi | Decide on whether this is also helpful for HV PMOS (vs. GIDL concern). Change mask scheme if needed.
NiSi | Rext reduction | Adopt or develop new fuse collateral
Stressor Nitride Film | High stress film for NLV | Need to make sure film thickness is compatible with contact module integration and optimize if necessary.
Low-k / Cu | 160nm pitch | 135nm pitch with taller via for inter-metal cap reduction

## Slide 22: Periphery Dev Schedule
* XP03-Rev2: existing development vehicle (XP03) needs to be re-taped out with Intel/F2 scribe. In addition, logic transistors based on new design rules have to be added.
During XP03-Rev2 based process development at F11X, Intel will provide necessary development resources for process engineering, integration, and device
optimization and transfer to IMFT.
Existing periphery JDP team will provide support in testchip layout/tapeout, parametric tests, HV integration, reliability assessment, and matching/post-transfer development activities at F2.
S37A DBR

## Slide 23: 5.0 Design SOW

## Slide 24
Features | S26 POR | S37**
Density | 32GB | 64GB
Array Architecture | Quilt | Quilt
Number of Partitions | 32 | 32
I/O Performance (Interface) | 1600MT/s/pin (DDR4) | 3200MT/s/pin (DDR4)
Read Latency | 95ns | 80ns
Write Completion Time | 475ns | 475ns
Sustained Read Throughput | 1600MB/s 10 partition concurrency | 3200MB/s 16 partition concurrency
Sustained Write Throughput | 800MB/s 24 partition concurrency | 1100MB/s 32 partition concurrency
Read Power / Read Energy (FF/85C) | 666mW / 52pJ/b | 666mW / 26pJ/b
Write Power / Write Energy (FF/85C) | 755mW / 118pJ/b | 520mW / 59pJ/b
Power Supplies | Vdd=Vddq=1.2V Vhh=3.3 Vpp=5.3 Vnn=-4.7 | Vdd=Vddq=1.1V Vhh=TBD Vpp=TBD Vnn=TBD
5.1: Key Product Spec Targets
50% energy reduction (critical enabler for higher read bandwidth within the same power window)
Increase IO speed to DDR4 equivalence
~18% Improvement in random read performance
2x Read Bandwidth
37.5% Improvement in Write Bandwidth
SXP JDP – Confidential
Double the density / maintain the same die size
** Design and TD teams will continue to perform pathfinding in Q1, ’18 timeframe to evaluate whether better product specs
for S37A can be achieved – as defined in the 30s Perf Envelope (see slide 25). LV CMOS is pre-enabled to support higher
IO / logic performance and further design/array/process optimization may be necessary in follow-up products to
take advantage of the capability.

## Slide 25: 5.2: 30s Product Perf Envelope
It is possible to envision 14nm, 4-deck array with lower Read and Write energy
(pJ/b) than S37A POR, thus enabling higher Read/Write bandwidth.
Higher performance CMOS has been adopted as part of POR periphery architecture to support higher Rd/Wr BW
For the same thermal envelope as 20s,
  Rd energy reduction to < 26 pJ/b is required to enable > 3200 MT/sec.
  Increased # of partitions (> 32) is needed to enable write BW > 1100 MT/sec. Write BW of up to 2200 MT/sec can be enabled by further reduction in write energy ( ≤ 43pJ/b), in addition to 64 partition architecture.
Items | S37A POR | Technology Scope | Comments
# of Partitions | 32 | 64 | CuA HV scaling required for 64 partitions (POR), but expect 5-10% die size penalty due to increase in PCU and other supporting circuitry.
Rd BW (MT/sec) | 3200 | 3200-4800 | CMOS enables IO speed up to 4800 MT/sec. ≥ 3200 MT/sec requires Rd energy scaling below 26 pJ/b
Rd Energy (pJ/b) | 26 | 26-17 | ≤ 26 pJ/b require further pathfinding (design/array arch/algo)
Wr BW (MT/sec) | 1100 | 1100-2200 | 1100 < Wr BW ≤ 1600 MT/sec limited by # of partitions (32) Wr BW up to 2200 MT/sec possible with energy down to 43 pJ/b & 64 partitions
Wr Energy (pJ/b) | 59 | 59-43 | ≤ 59 pJ/b require further pathfinding (design/array arch/algo)

## Slide 26: 5.3: Design Strategy Overview
Maintain the quilt architecture while optimizing the area utilization under the tile and the global placement of elements within the partition
  S26A equivalent tile area reduced by 50%
  Extensive use of MVT (TOX=90A) devices. Reliability concerns addressed through algo specific voltage controls
Re-architect the IO to array interface & speed critical paths to enable higher read & write bandwidth
Optimize the supply voltage requirements to minimize active energy for read & write
Maximize algo and trim capability for 30s-specific array/cell needs (to be decided)

## Slide 27
Item | Strategy | Details
Die Size / Floor-planning | Maintain Quilt Architecture. Optimize under tile circuit area utilization Optimize partition level circuit placement | Aggressive scaling of select devices / identification and reevaluation of critical design rules Reorientation of select devices / sharing of select device drivers to minimize routing and local diffusion Re-architect & re-optimize the local current mirror, sense amp, tile logic, and local level shifters to reduce device count, share well connections, and make use of MVTs wherever possible Evaluate partition level circuit placement and global driver positioning to minimize routing and energy and support desired performance
Performance | Re-architect IO to array interface Re-optimize high speed critical path circuits | Redesign high speed input/output path circuitry with new LVT collateral to balance performance needs versus active and idle power costs Redesign command & data path architecture to minimize critical path latency Redesign periphery logic engine to streamline critical paths Highest risk circuits placed on XP03 test vehicle to accelerate performance path design learning
Energy | Voltage Scaling Lower static currents (lower cell currents) Interconnect energy reduction | Define pad and internal voltages based on read More extensive use of VHH (instead of VPP) Internally pump to support write voltages Lower Vcc / regulate to even lower Vcc for array logic Evaluate tradeoffs of thinner interconnect (lower C / higher R) Conversion to MVTs wherever possible
Algo Capability | Maintain S2x flexibility & trimmability | Add support for post S26A1+/S15C14+ features Review feature classes & trimmability to maximize flexibility (deck to deck offsets, ED controls, algo shutdown)
New Capabilities | Flexible Power Sequencing Matrix ODT | Complete conceptual design and cost analysis to support new features
5.3: Design Strategy in Depth

## Slide 28
Strategy: Ensure that each chop provides equal or better performance at reduced overall cost relative to S26/S25
S37A architecture has 32 partitions with 2x128 bit slices per partition:
Chop to S36 involves removing 1 slice from each partition, matching S37A performance
Chop to S35 involved removing ½ the decks (4  2), also matching S37A performance
5.4: Derivative Products: S36/S35 Support
SXP JDP – Confidential
S37A
32 partitions
2 slices / partition
Rd/Wr BW: 3200/1100 MT/sec
S36A
32 partitions
1 slice/ partition
Rd/Wr BW: 3200/1100 MT/sec
Chop strategy enabled by fitting all non-decoder CuA under 1-tile.

## Slide 29
5.5: Design Gates to Execution
R0
R1
R2
R3
R3
DBR - 2months
DBR - 5months
DBR - 8months
DBR - 11months
Path to meet key prod goals
XP03 Feed-back
Med- Conf. Periphery Collateral
Test mode/DFM/Features
High-Conf. Cell Parameters
High-Conf. Collateral (DR/Model)
Final list of
Cell Algorithm / Features
Milestone | Pathfinding Related Gates
Rev0 (Transition from pathfinding to execution) | Path to meet die size, performance, and energy goals Resolution of customer performance requirements Initial data from XP03 test circuits available Medium confidence collateral ready for use (transistor models & design rules) Prelim device reliability requirements defined (aging/SOA/TDDB) New testmode, DFM, and external feature requests compiled / prioritized
Rev1 (Start of sheet level perf validation) ~3months after Rev0 | High confidence collateral ready for use High confidence cell characteristics defined (current & voltage requirements) Final aging/SOA tools ready for use
Rev2 (Start of path & full chip perf validation) ~3months after Rev1 | Final list of cell/algo feature requests
Determine Tile Arch & Chop
Strategy

## Slide 30: 6.0 30s SXP Product SOW

## Slide 31: Content
Product Schedule
Product Goals
  Qualification Criteria
  Ship Release Criteria
Development & Manufacturing Strategy
  Wafer Test
  Package Test
  CMOS & Array Reliability
  Packaging and Assembly
  Product Validation & Optimization
  Qualification

## Slide 32: SXP 30s Project Schedule
Milestone | Current Projection (V2.0)
S36X Si Start | Jan, 18
S36X 1D Probe | April, ‘18
30s Final Collateral Release | June, ‘18
S36X 2D Probe | Oct. ‘18
S37A DBR | Dec, ‘18
S37A SVC | Sep. ‘19
S37A MSC | Dec. ‘19
S37A Storage Qual | March, ‘20
S37A Memory Qual | June. ‘20

## Slide 33: Product Goals – Memory Spec
Key Specifications | Values
Operating Temperature | -40°C to 85°C (Tj)
Read Power / Energy | 666mW / 26pJ/b
Write Power / Energy | 520mW / 59pJ/b
tCK | 625ps / 1.6GHz
Read Latency | 80ns1
Sustained Read Throughput | 3200MB/s1
Sustained Write Throughput | 1100MB/s1
Maximum Write Cycles | 4.0E6
Selected Cell Read Disturb | 1.3E5
Write disturb cycles per aggressor | 2048
Retention | 85°C 2 Days + 40°C 7 Years
RBER | 5.0E-5
Quality | 500 DPM
Timings referenced to 625ps tCK
This table reflects preliminary #s based on 10s

## Slide 34: Product Goals – Storage Spec
Key Specifications | Values
Operating Temperature | -40°C to 85°C (Tj)
Read Power / Energy | 576mW / 30pJ/b
Write Power / Energy | 377mW / 95pJ/b
tCK | 833ps / 1.2GHz
Read Latency | 133ns1
Sustained Read Throughput | 2400MB/s1
Sustained Write Throughput | 496MB/s1
Maximum Write Cycles | 1.3E5
Selected Cell Read Disturb | 6E3
Write disturb cycles per aggressor | 400
Retention | 85°C 2 Days + 40°C 5 Years
RBER | 6.0E-4
Quality | 3000 DPM (qual timeframe 500 DPM (final)
Timings referenced to 833ps tCK
This table reflects preliminary #s based on 10s

## Slide 35: Development & Manufacturing Strategy
Si-start through M4 process development will occur at F11X and will be transferred to IMFT (F2). S37A Skip-array NPI and EPF will run at IMFT.
S36X front end processing (Si-start through M4) will take place in IMFT (S26A die), while M5 and array development work will be at Boise F4
Initial tape-out for M5 and Array layers will be to Boise F4. No Product Qualification or Ship Release from F4. Process will be transferred to IMFT, based on certain product health criteria.
IMFT (F2) will be the alpha-fab to qualify the entire process.
Preliminary wafer start plans for 2018-19 (work in progress)

## Slide 36: Wafer Test Strategy
JDP Probe teams will jointly develop all wafer test capability required to support the technology development and the full product specification. The required test flows are defined by the Product Engineering team. Flows may include:
  Wafer Test Flow
  Wafer Speed Binning Flow
  WLR / ICF / ECF Flows
JDP and IMFT Probe teams will jointly develop all H/W and S/W required to support the wafer test flows.

## Slide 37: Package Test Strategy
JDP Test teams will jointly develop all package test capability required to support the technology development and the full product specification. Required test flows are defined by the Product Engineering team. Flows may include:
  PGSRT
  Hot Sort
  Cold Final
  Burn-in
JDP teams will jointly identify package test platforms which meet the technology development and product requirements.
JDP Test teams will jointly develop all H/W and S/W required to support the package test flows.

## Slide 38: CMOS & Array Reliability
JDP Reliability teams will jointly support development of volume and bench level reliability data collection to enable technology and Product development.
JDP Reliability teams will jointly develop wafer and package test reliability flows and development line sampling plans for both intrinsic and extrinsic CMOS and array reliability issues.

## Slide 39: Product Development Strategy
JDP PE teams will jointly support product design validation, characterization, and debug.
JDP PE teams will jointly support definition and implementation of all wafer and package test flows.
JDP PE teams will jointly develop all H/W and S/W capabilities needed to support:
  µProbe / Wafer debug and EFA
  Interface Validation/Characterization
  Array Characterization
  Package EFA
JDP PE teams will jointly support product and test flow optimization to enable technology development, product qualification, and HVM.

## Slide 40: Qualification Strategy
JDP QA teams will jointly define the test flows needed for qualification. Qualification flow definition will be based on JEDEC standards adapted as needed for SXP.
JDP QA teams will support look-ahead qualification runs to enable technology development.
JDP will support silicon and package qualification which represents the envelope of the product requirements.

## Slide 41: 7.0 Development Budget

## Slide 42: Budget Planning
This SOW project scope and activities for 2018 are to be consistent with the 2018 SXP JDP budget.
Budgets for subsequent years of this SOW will be adopted on a yearly basis, as part of the overall SXP JDP budget.

## Slide 43: BACKUP

## Slide 44: From Pathfinding SOW: Deliverables for 30s Final SOW
Item Date Status
Timeline for (a) development vehicles: def’n and content, strategy 2/15/2017 Done
(b) overall collateral readiness
2. Intermediate product specs defined and high-level assessment of 3/31/2017 Done
product architectural choices to meet product spec
3. Selection of process architectural elements for the periphery 4/30/2017 Done1
4. Detailed timeline for S37A design, Proc Dev and Qualification 5/30/2017 Done
5. Preliminary data for WL/BL resistance and 14x14nm cell assumptions 9/30/2017 WIP2
6. Med-High confidence CPW, CoT and Cost/GB estimates 9/30/2017 WIP3
Final SOW for JDP approval TBD
Notes:
1 1st pass process elements selected. Will work through next level of optimization based on data.
2 A simple 2-mask vehicle defined for WL/BL resistance (1st and 2nd cut). Expect data in Q1, ’18. Cell assumption validation was an aggressive goal and will be available in mid-’18.
3 Need cost estimate for low-k tool/ flow. Array reqs (beyond PQ) is WIP, as we identify risk areas and develop mitigation plans.

## Slide 45: 30S WL/BL Resistivity Prognosis
New
Material
1.6~1.7x seems to be the right
assumption for ~6-7nm scaling
of the WL, based on the data
at hand
Explore new material and further
optimization of deposition conditions,
etc.