## Slide 1: Self-Select Memory IM JDP SOW
Version 2.0
January 31, 2018

## Slide 2: Signature Page
This 3DXP Joint Development Program Statement of Work Rev 2.0 (“Self-Select Memory SOW”), having been approved by the JDP Committee is hereby approved by Intel and Micron respectively effective as of mmm dd, 2018, as signified by the signature of each company’s authorized representative below. It is understood and agreed that this JDP SOW may be amended in due course in accordance with the procedures set forth in the Joint Development Program Agreement.
MICRON TECHNOLOGY, INC |  |  | INTEL CORPORATION | 
By: |  |  | By: | 
Name: |  |  | Name: | 
Date: |  |  | Date: | 

## Slide 3: Revision Page
Approval Date | REV | Pages Affected | Was | Is | Comments
Jan-20-2016 | 1.0 | ALL |  | Initial Self-Select Memory SOW | 
Jan-31-2018 | 2.0 | ALL |  | SSM technology and product SOW | 
Notes: 3

## Slide 4: SOW Contacts
Name | Function | Company
Russ Meyer | JDP co-manager | Micron
Al Fazio | JDP co-manager | Intel
Mark Helm | Design | Micron
Matt Goldman | Design | Intel
Geetha Jayaraman | Product/Test Development | Intel
Kiran Pangal | Array Development | Intel
Fabio Pellizzer | Technology Development | Micron
DerChang Kau | Technology Development | Intel

## Slide 5: SOW Contents
0.0 Purpose
1.0 Introduction
1.1 Background
1.2 Mission and Scope
2.0 Strategy
2.1 Overview
2.2 Development Vehicles
2.3 Scaling Roadmap
2.4 Lead Product
2.5 Gen+1 Product
3.0 Milestones
3.1 Fail Check
3.2 Decision Process for Execution
3.3 POR Critical Path
3.4 PrePOR Critical Path
4.0 Cost analysis
5.0 Process Development
5.1 Risks
5.2 Cell Stack Definition
5.3 Process Architecture
6.0 Design SOW 6.1 Key Product Specs & Constraints 6.2 Design Strategy Overview 6.3 Decoder Design and Design Rule 6.4 Design Milestones & Gates to Execution
7.0 Product/Test Development SOW
7.1 Array Development Strategy
7.2 Product Development Strategy
7.3 Wafer Test Strategy
7.4 Package Test Strategy
8.0 Budget & Assumptions
8.1 Silicon Startup Plan

## Slide 6: 0.0 Purpose
The goal of the work is to validate Self-Select Memory, SSM, fundamentals for a Go/No-Go decision fast.
The intent and purpose of the document are –
To introduce SSM and alpha product for technology demonstration
To illustrate the strategy for “fast fail or succeed” with an alpha product
To establish milestones and incremental fail check based on the strategy
To define key activities and deliverables through the milestones
To define the resources and the budget to achieve the targeted deliverables

## Slide 7: 1.0 Introduction
Background, Mission and Scope

## Slide 8: 1.1 Background
VT,High
VT,Low
S15B SD-only, lot 8792062, 18nm SDd ver 4
Positive
Write
Negative
read
Negative
Write
Negative
read
Pulse Polarity
TE
BE
SD
Fundamentally, it is a 3DXP technology.
  Physical construction of SSM array is BEOL 3D stackable X-Y cross point compatible with mainstream CMOS.
  Read/write is to threshold a cell in a tile while the rest of cells are inhibited in subthreshold bias.
A VT window (∆VT) has been observed by applying programming pulses with opposite polarity. The best known ∆VT physics is an electrochemical potential modulation by polarity.
  Write – Band offset switching subject to mass transport (memory effects)
  Read – Space Charge modulation resulting in voltage shift (memory window)
−/−
+/−
Write/Read
Polarity
900mV
+/+
−/+
VTH [mV]
σ of bit distribution

## Slide 9: 1.2 Mission & Scope
Mission
  Scalability and Roadmap Development of 3D XPoint™ Technology
Scope
  Seek for fundamental understandings of non-volatility of bipolar operation of SSM by demonstrating reliable Read Window Budget.
  Validate bipolar decoder and power supply scheme with a multi-deck product by benchmarking density, energy and latency against the incumbent.
  Develop world leading 3D XPoint product roadmap based on SSM physics, low cost process enablers and high efficiency decoding scheme.

## Slide 10: 2.0 Strategy
Overview, Development Vehicles, Scaling Roadmap, Alpha Product and Gen+1

## Slide 11: 2.1 Strategy Overview
“Fast fail or succeed” by building a 3DXP product for SSM
  Test complete array in high volume and validate product worthiness by building prototypes
  To minimize additional cell development beyond SSM pathfinding, the SSM process flow developed on S26A mask set will be exploited for alpha product demonstration.
Leverage 20’s infrastructure and synergy for high velocity development.
Bipolar Decoder Design
Fast implementation: based on S26A floor plan, inc. Pad
Low risk execution: S26A based CMOS technology & collateral @ minimum augmentation required
Algo development leverage by reusing S26 test infrastructure
Enable probe synergy with S26 PG1 specs at shorter write completion time
SSM Switching Physics w/ 20nm Cell
Cell development (DTS/MTS) based on S26A scribe mini array and single cell structures (SR71, QTT, 2XCMOS)
Develop fundamental understanding of switching mechanism for tuning window and reducing distribution
20nm SSM Structure Yield
Establish S26A SSM-flow baseline and change control
Leverage with S26A yield improvement
20nm Startup Flow Defined
Structure and RWB demonstrated yield
DTS/MTS/RWB are consistent
S26S Tapeout
Product vehicle: 256Gb in 197mm2 @S26A Spec, plus
Power delivery for @ 240ns write completion testable
Fail or Succeed
Scaling Roadmap
Process architecture Stack (S26A like) vs. Tier (3DNAND-like)

## Slide 12: 2.2 Development Vehicle Expectations
S26A – Live die and the scribe structures of S26A (20nm node) Plate-set
  Dual deck process: product die structure yield learning for SSM baseline process flow
  Single Cell: Basic bipolar characterization capability is established with the 2xCMOS test structure.
  QTT (quarter-tile size mini array): A electrically bi-directional operable mini array test structure.
  SR71 (one full tile array) – A bi-directional decoded, operable 512K addressable array:
S26S – A 20nm node bipolar 3DXP product in compliance with S26A spec
Features | S26A | S26S
Density | 256Gb | 256Gb
Die Size | 197mm2 | 197mm2
Array Architecture | Quilt | Quilt
Number of Partitions | 32 | 32
I/O Performance (Interface) | 1600MT/s/pin (DDR4) | 1600MT/s/pin (DDR4)
Read Latency | 95ns | 95ns
Write Completion Time | 475ns | 240ns
Read/Write Throughput | 1600 / 800 MB/s | 1600 / 800 MB/s
Read / Write Energy | 52 / 118 pJ/b | 52 / 118 pJ/b
Power Supplies | Vdd=Vddq=1.2V Vhh=3.3, Vpp=5.3, Vnn=-4.7V | Vdd=Vddq=1.2V Vhh=3.3, Vpp=5.3, Vnn=-4.7V

## Slide 13: 2.3 Scaling Roadmap Development
Architecture
  SSM memory switching physics is the foundation
  Scalable cell architecture will be established based on RWB tuning enablers.
  Low cost process architecture will be developed in accordance to cell architecture.
  Scalable memory core architecture will be developed based on cell architecture and scaling requirement for density and performance.
Scaling rule of thumb
  Density: doubling every generation
  Latency: equal or reduce
  Bandwidth/GB: Equal or improve
Reference architecture: SXP stack vs. 3D-NAND tier
  Scalable architecture development starts when 1. Switching mechanism is manageable and 2. 20nm Product Vehicle is DBR’d
3D-tier
3D-stack

## Slide 14: 2.4 Lead Product for “Fast Fail or Succeed” and Risk Mitigation Strategy
To build with S26S in compliance with S26A spec @ ½ set time.
  Test complete array in high volume and validate product worthiness by building prototypes
  High level of synergy and reuse with 20series in design, tests and collateral
  Additional Thick Gate nMOS Transistor (TGnMOST) is required in order to meet S26A energy spec
S24S Design Start
100% S26A collateral
CMOS Bipolar Decoder (no HV Stress) 50% high switching energy
S26A3 footprint/50% Dummy WL/BL
Wafer level testable for SSM functionality @ ½ of set time
Power/thermal envelope prohibitive for full throttle component test (system level validation)
TGnMOST & DR Assessment
Decoder fitted, TGnMOST meet I-V requirement for 20nm
Change CMOS decoder scheme to TGnMOST decoder scheme [+2Q]
Design to S26A full spec, compatible to S26A full spec
EoQ1 RA for Q3 TO
Risk in DR
S24S DBR @Q3/18
w/o TGnMOST
Validation at lower BW
Spec-compliant S26S DBR @Q1/19
w/ TGnMOST
High Risk
Low Risk
Risk in TGnMOST
Low Risk
High Risk
S26S’ DBR @Q3/18
w/o TGnMOST
Validation at lower BW

## Slide 15: 2.5 Gen+1 Product outlook
High-level strategy definition to be reexamined and better defined (e.g. with execution plan) under scaling roadmap analysis in Q4’18.
Development Vehicle Strategy
  14nm SSM Spider Chip:
  Base silicon uses S26S, Array spider similar or identical to S36X layout High level of synergy and reuse with S26S for jump start 14nm cell scaling and structure yield
  14nm SSM Alpha Product: Fast time of transition to 14nm half-pitch product in compliance with S37A spec High level of synergy and reuse with 30series in design, tests and collateral
 | S26A | S36X | S26S | S37A | 14nm SSM Spider | 14nm SSM Alpha
Density/Die Size | 256Gb / 197mm2 | 128 Gb / 197mm2 | 256Gb / 197mm2 | 512Gb / 195mm2 | 128Gb / 197mm2 | 512Gb / 195mm2
half pitch | 20.5nm | 14nm | 20.5nm | 14nm | 14nm | 14nm
Cell Architecture | SXP | SXP | SSM | SXP | SSM | SSM
Decoder | Unipolar | Unipolar | Bipolar | Unipolar | Bipolar | Bipolar
Read/Write Latency | 95/475 ns | 95/475 ns | 95/240 ns | 80/475 ns | 95/240 ns | 80/240 ns
Read/Write Energy | 52/118 pJ/b | 52/118 pJ/b | 52/118 pJ/b | 26/59 pJ/b | 52/118 pJ/b | 26/59 pJ/b
Read/Write Thruput | 1600/800 MB/s | 1600/800 MB/s | 1600/800 MB/s | 3200/1100 MB/s | 1600/800 MB/s | 3200/1100 MB/s
I/O and Transfer Rate | DDR4 1600MT/s | DDR4 1600MT/s | DDR4 1600MT/s | DDR5 3200MT/s | DDR4 1600MT/s | DDR5 3200MT/s
S26A based
S37A based
S26S unique
G+1 SSM unique
Color coding:

## Slide 16: 3.0 Milestone
Fail Check and Critical Path

## Slide 17: 3.1 Fail Check
# | Objectives as measured by | On or before (Calendar year)
1 | SSM switch mechanism validated with Dual Deck silicon (SR71) 20nm Product D0 vs. D1 Read/Write polarity defined; No RWB showstopper on paper | Q2/2018
2 | 20nm Vehicle DBR S26A3 die size @ ½ set speed 20nm SSM Process Startup flow defined | Q3/2018
3 | 20nm Vehicle yielding @ PG1 spec Silicon demonstrated, no show stopper on bipolar ops. | Q2/2019
4 | 20nm Vehicle Memory Qual As measured by qual success criteria @ ½ set speed | Q4/2019
S24S is POR for 20nm Vehicle.
Energy Spec compliant S26S is prePOR pending on TGnMOST and DR readiness.
Should fast-fail decision be favorable to S26S, POR change decision will be ratified by JDP Committee by the end of Q1/2018.

## Slide 18: 3.2 Product POR and Decision Process for POR Change
In order to meet die size and energy of SXP counter part, SSM has high design collateral scope & risk
  More aggressive DR is needed to fit more transistors for bipolar decoder
  TGnMOST development is required in compliant to energy spec
TGnMOST & Collateral Assessment
Decoder fitted, TGnMOST meet I-V requirement for 20nm
EoQ1 RA for Q3 TO
Risk in DR & TGnMOST
Low Risk
High
Risk
S26S
TGnMOST
low risk 20nm DR
S26A spec
S24S Design Start
100% S26A collateral
CMOS Bipolar Decoder (no HV Stress)
20~50% high switching energy
S26A3 footprint @ ¼ of density
Wafer level testable for SSM cross tile functionality @ ½ of set time, 64Gb
Continue S24S Design
S24S
No TGnMOST
100% 20nm DR
S26A spec @ Lower BW
S37S
TGnMOST
S37S DR
S37A spec
Collateral Development
TGnMOST
14nm SSM Design Collateral
To fit in S37A density/die size
POR
PrePOR
Evaluation/Decision

## Slide 19: 3.3 POR Critical Path: Fast Fail and Fast Succeed and Beyond POR as of Q1/2018, S24S is 20nm Product Vehicle
 |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
20nm SSM | SSM RWB demonstrated on Dual Deck SR71 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S24S DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S24S Probe Yield @ PG4 RWB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S24S Probe Yield @ PG1 RWB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S24S Qual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14nm SSM | S36X Spider Chip DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | SSM Collateral Release (TGnMOST, DR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | RWB demonstrated, S/U Flow Defined |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S37S DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S37S Qual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Scaling Roadmap Pathfinding Starts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
S26A PG1 PRQ
S37A PG1 PRQ
Based on high confidence
collateral for fast fail
Passing PG4 criteria triggers 14nm SSM Alpha Product Design Start for fast succeed

## Slide 20: 3.4 PrePOR Critical Path for 20nm then 14nm Products with high confidence of energy spec compliant S26S DBR by Q1/19
 |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
20nm SSM | SSM RWB demonstrated on Dual Deck SR71 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S26S DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S26S Probe Yield @ PG4 Spec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S26S Probe Yield @ PG1 Spec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S26S Qual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14nm SSM | S36X Spider Chip DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | SSM Collateral Release (TGnMOST, DR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | RWB demonstrated, S/U Flow Defined |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S37S DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S37S Qual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Scaling Roadmap Pathfinding Starts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
S26A PG1 PRQ
S37A PG1 PRQ
Based on TGnMOST / DR for energy spec compliant S26S
Passing PG4 criteria triggers 14nm SSM Alpha Product Design Start for fast succeed

## Slide 21: 4.0 Cost Analysis
S26S Die size is the same as S26A
  Bipolar decoders size should be equal or better than SXP counterpart.
Lower cost due to process simplification from partial etch architecture to single etch scheme.
Preliminary green-field analysis has been performed for cost-of-transition and cost-per-wafer
  Based assumptions for the etch simplification of 20 series SXP technology
Higher yield expected due to SSM potentially overcoming several SXP issues, including
  No cross-contamination between PM and SD
  Lower cell aspect-ratio for etch and fill
  Lower programming current  Additional relaxation to metal (WL/BL) requirements for scaling
 | CoT ($M/1k) | Delta ($M/1k) | CPW | Delta
10s -> 20s MOR | 144.9 |  | $2,274.00 | 
10s -> 4 Deck SSM | 114.8 | -30.1 | $2,040.00 | ($234.00)
10s -> 20s 2 Deck MOR | 26.1 |  | $1,559.29 | 
10s -> 2 Deck SSM | 25 | -1.1 | $1,438.25 | ($121.04)

## Slide 22: 5.0 Process Development
Challenge, Cell definition and Process Architecture

## Slide 23: 5.1 Known Risks and Mitigation Strategy
Area | Issue | Mitigation Strategy
Memory Switching Mechanism | The best known mechanism is mass transport due to polarity. There are three risks associate with the mechanism What elements accountable for memory switching and process control/tuning of memory window Unable to quantify memory window subject to read polarity VT vs. PA/PW results not matching expectation (window expansion/saturation) | Composition skew and contamination control (including ambient). Cell morphology segmenation, including building two-deck SSM
Vt drift | Set drift is similar to SXP; however, reset drift is ½ of Set’s . No window expansion post drift. | Wider time-0 window to support single VDM strategy True spec reset drift for alternative dual VDM strategy
Reset Read Disturb | 300mV of Reset VT reduction is observed after 20K Read cycles | Segment Reset VT shift mechanism

## Slide 24: 5.2 Cell Definition
Initial cell development will be done on SR71B in S26A mask set, for both first and second deck.
  The result will be S26S startup MTS
  Write performance (write current and pulse width) and Read Window Budget must enable S26S qual
Product validation
  S26S array experiment and characterization enables SSM optimization for S26A qual.
Item | Working Assumption / Status | Strategy / Key Enabling Factors
SD exploration | POR is SD2V16 | Explore composition skew on the class of SD1 and SD2 Deploy 3DXP material exploration BKM, including L0 thin film characterization L1 Cantilever process and characterization L1D on pitch process development and inline characterization L2 full loop process with physical and electrical assessment
Laminas | POR is 5Å Al2O3 sandwich SD | L1D and L2 for assessment
Electrodes | POR is the same as S26A’s TE and BE | Synergize with SXP counterpart Further optimization with L1D and L2 if needed
WL/BL metals | POR is the same as S26A’s | Synergize with SXP counterpart Further optimization with L1D and L2 if needed
Etch Profile | POR is same as S26A’s (≥89°) | L1D and L2 with etch experiment
Seal/fill | POR is same as S26A’s (no liner) | L1D and L2 including partial liner for profile engineering and transfer function tuning and contamination control

## Slide 25: 5.3 Process Architecture
CMOS and BEOL
  High level of synergy to S26A
  Adding Thick Gate nMOS Transistor for decoder, process and collateral development required.
Array Process
  Structural yield on wafer will be evaluated and improved on S26A main array, 1-and 2-deck structural yield (now), may be extended to 4 decks before S26S TO (if needed)
 | S15C 41nm pitch / 2-deck 2Kx4K Tile | S26A 41nm pitch / 4-deck 4Kx4K Tile | S26S 41nm pitch / 4-deck 4Kx4K Tile
CMOS | 19 mask levels Dual gate CMOS (23A/110A) | No change from 10s HV CMOS width scaling | Copy from S26A Adding Thick gate nMOS Transistor for S26S
M1-M4 (Cu) | M1 single-damascene Cu M2-M4 dual-damascene Cu All 193-dry levels | M1, M4 single damascene Cu M2-M3 dual damascene Cu V3 and M4 goes 193i (+2) | Same as S26A
Array levels | 2 decks  4 PD levels 3 OPV levels 7 193i levels for array | 4 decks  8 PD levels 5 OPV levels 13 193i levels for array | Copy from S26A simplified cell stack and BL/WL patterning scheme
Top Metal / Passivation | Thick Al, SiO2+SiON Passivation, Polyimide | No Change | No Change

## Slide 26: 6.0 Design SOW

## Slide 27: 6.1 Product Spec and Boundary Conditions
Key specs that will change or that will be a challenge to maintain vs S26A
Broad class of specs that will be unchanged vs S26A
Other spec or product constraints that design must meet
  Die size / pad positions / available voltages

## Slide 28: 6.2 Design Strategy Overview
Decoders to be updated and fit in same space
Termination/drivers to be updated accordingly
  Polarity control logic to be added
Read algo essentially unchanged from S26A
Write algo to be updated/simplified version of SET/RST from S26A
Validation focused on decode path and algo changes

## Slide 29: 6.x2 20nm Alpha Product Spec
S26S – A 20nm node bipolar 3DXP product in compliance with S26A spec
S24S – A contingency to eliminate the design collateral risk
  Favorable to “Fast-Fail” with 100% S26A collateral (low risk, fast execution)  DBR Q3/2018
  S26A die size, ¼density, higher energy, lower bandwidth validation
Features | S26A | S26S | Contingency: S24S
Density | 256Gb | 256Gb | <64Gb
Die Size | 197mm2 | 197mm2 | 197mm2
# of Deck | 4 | 4 | 4
Array Architecture | Quilt | Quilt | Quilt
Number of Partitions | 32 | 32 | 32
I/O Performance (Interface) | 1600MT/s/pin (DDR4) | 1600MT/s/pin (DDR4) | 1600MT/s/pin (DDR4)
Read Latency | 95ns | 95ns | 95ns
Write Completion Time | 475ns | 240ns | 240ns
Read/Write Throughput | 1600 / 800 MB/s | 1600 / 800 MB/s | 930 / 527 MB/s
Read / Write Energy | 52 / 118 pJ/b | 52 / 118 pJ/b | 89 / 179 pJ/b
Power Supplies | Vdd=Vddq=1.2V Vhh=3.3, Vpp=5.3, Vnn=-4.7V | Vdd=Vddq=1.2V Vhh=3.3, Vpp=5.3, Vnn=-4.7V | Vdd=Vddq=1.2V Vhh=3.3, Vpp=5.3, Vnn=-4.7V

## Slide 30: 6.x3 14nm Alpha Product Spec
“S37S” – A 14nm node bipolar 3DXP product in compliance with S37A spec
  TGnMOST and Pitched-Cell Design Rule to fit bipolar decoder in S37A patch
Features | S37A | S37S
Density | 512Gb | 512Gb
Die Size | 195mm2 | 195mm2
# of Deck | 4 | 4
Array Architecture | Quilt | Quilt
Number of Partitions | 32 | 32
I/O Performance (Interface) | 3200MT/s/pin (DDR5) | 3200MT/s/pin (DDR5)
Read Latency | 80ns | 80ns
Write Completion Time | 475ns | 240ns
Read/Write Throughput | 3200 / 1100 MB/s | 3200 / 1100 MB/s
Read / Write Energy | 26 / 86pJ/b | 26 / 86 pJ/b
Power Supplies | Vdd=Vddq=1.1V Vhh=tbd, Vpp=tbd, Vnn=tbd | Vdd=Vddq=1.1V Vhh=tbd, Vpp=tbd, Vnn=tbd

## Slide 31: 6.3 Design Strategy Details

## Slide 32: 6.4 Design Milestones & Gates to Execution

## Slide 33: 7.0 Product/Test Development
Array, Product and Wafer/Package Tests development

## Slide 34: 7.1 Array Development Strategy
Array development through both SR71 and S26S including algorithms and trims for bipolar operation for technical risk assessment meeting product requirements and support the technology go or no go decision.
JDP Reliability teams will jointly support development of volume and bench level reliability data collection to enable technology and Product development.

## Slide 35: 7.2 Product Development Strategy
JDP PE teams will jointly support product design validation, characterization, and debug.
JDP PE teams will jointly support definition and implementation of all wafer and package test flows.
JDP PE teams will jointly develop all H/W and S/W capabilities needed to support:
  µProbe / Wafer debug and EFA
  Interface Validation/Characterization
  Array Characterization
  Package EFA
JDP PE teams will jointly support product and test flow optimization to enable technology development, product qualification, and HVM.
JDP Reliability teams will jointly develop wafer and package test reliability flows and development line sampling plans for both intrinsic and extrinsic CMOS and array reliability issues.

## Slide 36: 7.3 Wafer Test Strategy
JDP Probe teams will jointly develop all wafer test capability required to support the technology development and the full product specification. The required test flows are defined by the Product Engineering team. Flows may include:
  Wafer Test Flow
  Wafer Speed Binning Flow
  WLR / ICF / ECF Flows
  Wafer Level SR71 volume testing
JDP and IMFT Probe teams will jointly develop all H/W and S/W required to support the wafer test flows.

## Slide 37: 7.4 Package Test Strategy
JDP Test teams will jointly develop all package test capability required to support the technology development and the full product specification (S26S). Required test flows are defined by the Product Engineering team. Flows may include:
  PGSRT
  Hot Sort
  Cold Final
  Burn-in
JDP teams will jointly identify package test platforms which meet the technology development and product requirements.
JDP Test teams will jointly develop all H/W and S/W required to support the package test flows.

## Slide 38: 8.0 Budget
This SOW project scope and activities for 2018 are to be consistent with the 2018 SXP JDP budget.
Budgets for subsequent years of this SOW will be adopted on a yearly basis, as part of the overall SXP JDP budget.