## Slide 1: Self-Select Memory Path-Finding IM JDP SOW
Version 3.4
April 19, 2018

## Slide 2: Signature Page
This 3DXP Joint Development Program Statement of Work Rev 3.4 (“Self-Select Memory Pathfinding SOW”), having been approved by the JDP Committee is hereby approved by Intel and Micron respectively, as signified by the signature of each company’s authorized representative below. This Self-Select Memory Pathfinding SOW, automatically and without further action by either party, will be effective on May 8, 2018, if by May 7, 2018 Intel is ready to engage with Micron in development work hereunder at Intel’s Fab 11X to modify its 65nm logic process and low-K/Cu process for use in the periphery process of 30-series technology. This Self-Select Memory Pathfinding SOW shall terminate upon the earliest to occur of (i) completion of the purpose, objectives and/or milestones defined herein, or (ii) July 17, 2018, unless extended by mutual agreement of the Parties. It is understood and agreed that this JDP SOW may be amended in due course in accordance with the procedures set forth in the Joint Development Program Agreement.
MICRON TECHNOLOGY, INC |  |  | INTEL CORPORATION | 
By: |  |  | By: | 
Name: |  |  | Name: | 
Date: |  |  | Date: | 

## Slide 3: Revision Page
Approval Date | REV | Pages Affected | Was | Is | Comments
Jan-20-2016 | 1.0 | ALL |  | Initial Self-Select Memory Research SOW | 
April-19-2018 | 3.4 | ALL |  | SSM Path-Finding SOW | 
Notes: 3

## Slide 4: SOW Contacts
Name | Function | Company
Russ Meyer | JDP co-manager | Micron
Al Fazio | JDP co-manager | Intel
Mark Helm | Design | Micron
Matt Goldman | Design | Intel
Geetha Jayaraman | Product/Test Development | Intel
Steve Casper | Product/Test Development | Micron
Kiran Pangal | Array Development | Intel
Fabio Pellizzer | Technology Development | Micron
DerChang Kau | Technology Development | Intel

## Slide 5: SOW Contents
0.0 Purpose
1.0 Introduction
1.1 Background
1.2 Mission and Scope
2.0 Strategy
3.0 Milestones
4.0 Cost analysis
5.0 Process Development
5.1 Risks
5.2 Cell Stack Definition
5.3 Process Architecture
6.0 Design SOW 6.1 Design Strategy 6.2 Key Specifications & Features 6.3 Design Milestones & Gates to Execution
7.0 Product/Test Development SOW
7.1 Array Development Strategy
7.2 Product Development Strategy
7.3 Wafer Test Strategy
7.4 Package Test Strategy
8.0 Budget

## Slide 6: 0.0 Purpose
The goal of the work is to explore and evaluate Self-Select Memory, SSM, technology ahead of a product roadmap decisions.
The intent and purpose of the document are –
To introduce SSM and alpha product for technology demonstration
To characterize the technology to define an alpha product proposal
To establish milestones and incremental fail check based on the strategy
To define key activities and deliverables through the milestones
To define the resources and the budget to achieve the targeted deliverables

## Slide 7: 1.0 Introduction
Background, Mission and Scope

## Slide 8: 1.1 Background
VT,High
VT,Low
S15B SD-only, lot 8792062, 18nm SDd ver 4
Positive
Write
Negative
read
Negative
Write
Negative
read
Pulse Polarity
TE
BE
SD
The technology will be explored in a cross point architecture
  Physical construction of SSM array is BEOL 3D stackable X-Y cross point compatible with mainstream CMOS.
  Read/write is to threshold a cell in a tile while the rest of cells are inhibited in subthreshold bias.
A VT window (∆VT) has been observed by applying programming pulses with opposite polarity. The best known ∆VT physics is an electrochemical potential modulation by polarity.
  Write – Band offset switching subject to mass transport (memory effects)
  Read – Space Charge modulation resulting in voltage shift (memory window)
−/−
+/−
Write/Read
Polarity
900mV
+/+
−/+
VTH [mV]
σ of bit distribution

## Slide 9: 1.2 Mission & Scope
Mission
  Scalability and Roadmap Development of SSM Technology
Scope
  Seek for fundamental understandings of non-volatility of bipolar operation of SSM by demonstrating reliable Read Window Budget.
  Validate bipolar decoder and power supply scheme with a multi-deck product by benchmarking density, energy and latency against the incumbent.
  Develop world leading memory product roadmap based on SSM physics, low cost process enablers and high efficiency decoding scheme.

## Slide 10: 2.0 Strategy
The strategy for ‘fast fail or succeed’ is built on ‘stepping-up’
SR71 – SSM basics, including scaling, symmetry with solid empiricals to support switching mechanism
S24S – Array feature development with high volume statistical validation with Probe, WLR, Burn and ULR metric.
Build alpha product – Design and process development in order to pick an array node, assess and develop required CMOS and Design Rules and BEOL, such that all work coherently for die size and performance matching or better than SXP counterpart.
Develop Scaling roadmap – Follow the general scaling expectation for cost and energy reduction
  Density: doubling every generation
  Latency: equal or reduce
  Bandwidth/GB: Equal or improve

## Slide 11: 3.0 Milestones
Deliverables for “step up” or not
*Lead Product Path-Finding are the development in design and process in order to pick an array node. The key activities are assessing and developing required CMOS and Design Rules and BEOL. The success criteria are die size, cost and performance (energy, power, latency and intrinsic reliability) matching or better than SXP counterpart.

## Slide 12: 4.0 Cost Analysis
Using S26S as a proxy SSM alpha product, the die size is the same as S26A
  Bipolar decoders size should be equal or better than SXP counterpart.
Lower cost due to process simplification from partial etch architecture to single etch scheme.
Preliminary green-field analysis has been performed for cost-of-transition and cost-per-wafer
  Based assumptions for the etch simplification of 20 series SXP technology
Higher yield expected due to SSM potentially overcoming several SXP issues, including
  No cross-contamination between PM and SD
  Lower cell aspect-ratio for etch and fill
  Lower programming current  Additional relaxation to metal (WL/BL) requirements for scaling
 | CoT ($M/1k) | Delta ($M/1k) | CPW | Delta
10s -> 20s MOR | 144.9 |  | $2,274.00 | 
10s -> 4 Deck SSM | 114.8 | -30.1 | $2,040.00 | ($234.00)
10s -> 20s 2 Deck MOR | 26.1 |  | $1,559.29 | 
10s -> 2 Deck SSM | 25 | -1.1 | $1,438.25 | ($121.04)

## Slide 13: 5.0 Process Development
Challenge, Cell definition and Process Architecture

## Slide 14: 5.1 Known Risks and Mitigation Strategy
Area | Issue | Mitigation Strategy
Memory Switching Mechanism | The best known mechanism is mass transport due to polarity. There are three risks associate with the mechanism What elements accountable for memory switching and process control/tuning of memory window Unable to quantify memory window subject to read polarity VT vs. PA/PW results not matching expectation (window expansion/saturation) | Composition skew and contamination control (including ambient). Cell morphology segmentation, including building two-deck SSM
Vt drift | Set drift is similar to SXP; however, reset drift is ½ of Set’s . No window expansion post drift. | Wider time-0 window to support single VDM strategy True spec reset drift for alternative dual VDM strategy
Reset Read Disturb | 300mV of Reset VT reduction is observed after 20K Read cycles | Segment Reset VT shift mechanism

## Slide 15: 5.2 Cell Definition
Initial cell development will be done on SR71B in S26A mask set, for both first and second deck.
  The result will be S24S startup MTS
  Write performance (write current and pulse width) and Read Window Budget must enable S24S qual
S24S validation
  S24S array experiment and characterization enables SSM optimization for qual.
Item | Strategy / Key Enabling Factors
SD exploration | Explore composition skew on the class of SD1, SD2 and alternative chalcogenide alloy Deploy 3DXP material exploration BKM, including L0 thin film characterization L1 Cantilever process and characterization L1D on pitch process development and inline characterization L3 full loop process with physical and electrical assessment
Laminas | L1D and L3 for assessment
Electrodes | Synergize with SXP counterpart Further optimization with L1D and L3 if needed
WL/BL metals | Synergize with SXP counterpart Further optimization with L1D and L3 if needed
Etch Profile | L1D and L3 with etch experiment
Seal/fill | L1D and L3 including partial liner for profile engineering and transfer function tuning and contamination control

## Slide 16: 5.3 Process Architecture
CMOS and BEOL
  High level of synergy to S26A
Array Process
  Structural yield on wafer will be evaluated and improved on S26A main array, 1-and 2-deck structural yield (now), may be extended to 4 decks before S24S TO (if needed)
  CD scaling will be evaluated using 14nm SR71 (S36X).
 | S15C 41nm pitch / 2-deck 2Kx4K Tile | S26A 41nm pitch / 4-deck 4Kx4K Tile | S24S 41nm pitch / 4-deck 2Kx2K Tile in the footprint of S26A Tile
CMOS | 19 mask levels Dual gate CMOS (23A/110A) | No change from 10s HV CMOS width scaling | Same as S26A
M1-M4 (Cu) | M1 single-damascene Cu M2-M4 dual-damascene Cu All 193-dry levels | M1, M4 single damascene Cu M2-M3 dual damascene Cu V3 and M4 goes 193i (+2) | Same as S26A
Array levels | 2 decks  4 PD levels 3 OPV levels 7 193i levels for array | 4 decks  8 PD levels 5 OPV levels 13 193i levels for array | Copy from S26A simplified cell stack and BL/WL patterning scheme
Top Metal / Passivation | Thick Al, SiO2+SiON Passivation, Polyimide | No Change | No Change

## Slide 17: 6.0 Design SOW

## Slide 18: 6.1 Design Strategy
Enable path to fast fail or success (S24S) by minimizing non-cell related design risks
  Fork S26A3 database and disposition each post silicon issue’s impact on S24S ability to enable SSM learning
  No changes to periphery or high speed IO circuits
  No changes in die size, pad positions, or externally supplied voltage rails
  Focused changes in address path and partition control logic to enable bidirectional operation
S24S (Design POR):
  Inhibit 50% of the array drivers to provide area for new bipolar predrivers
  Add tile level polarity control and update partition control logic to enable bipolar operation with SSM read/write algorithms

## Slide 19: 6.2 Key Specifications & Features
S24S density reduced by 75% to provide area to support bipolar decoders without any design rule changes
Write completion time reduction based on proposed SSM write functionality
Bipolar decoder functionality projected to increase read/write energy by 71%/51%
Read/write bandwidth aligned to match S26A equivalent power envelope
Features | S26A | S24S (Design POR)
Density | 256Gb | 64Gb
Die Size | 197mm2 | 197mm2
I/O Performance (Interface) | 1600MT/s/pin (DDR4) | 1600MT/s/pin (DDR4)
Read Latency | 95ns | 95ns
Write Completion Time | 475ns | 240ns
Read/Write Throughput | 1600 / 800 MB/s | 930 / 527 MB/s
Read / Write Energy | 52 / 118 pJ/b | 89 / 179 pJ/b
Power Supplies | Vdd=Vddq=1.2V Vhh=3.3, Vpp=5.3, Vnn=-4.7V | Vdd=Vddq=1.2V Vhh=3.3, Vpp=5.3, Vnn=-4.7V

## Slide 20: 6.3 Design Milestones & Gates to Execution
Limited scope of change enables a direct path to Rev2 without requiring Rev1 alignment
Very little design overlap between S24S and S26S / replan required
Milestone | Criteria
Rev 2 | Sheet level performance validation complete / circuits ready for layout
Rev 3 | Full chip functional and performance validation of features, specifications and test modes
DBR | Database Ready for Manufacturing

## Slide 21: 7.0 Product/Test Development
Array, Product and Wafer/Package Tests development

## Slide 22: 7.1 Array Development Strategy
Array development through both SR71 and S24S including algorithms and trims for bipolar operation for technical risk assessment meeting product requirements and support the technology go or no go decision.
JDP Reliability teams will jointly support development of volume and bench level reliability data collection to enable technology and Product development.

## Slide 23: 7.2 Product Development Strategy
JDP PE teams will jointly support product design validation, characterization, and debug.
JDP PE teams will jointly support definition and implementation of all wafer and package test flows.
JDP PE teams will jointly develop all H/W and S/W capabilities needed to support:
  µProbe / Wafer debug and EFA
  Interface Validation/Characterization
  Array Characterization
  Package EFA
JDP PE teams will jointly support product and test flow optimization to enable technology development, product qualification, and HVM.
JDP Reliability teams will jointly develop wafer and package test reliability flows and development line sampling plans for both intrinsic and extrinsic CMOS and array reliability issues.

## Slide 24: 7.3 Wafer Test Strategy
JDP Probe teams will jointly develop all wafer test capability required to support the technology development and the full product specification. The required test flows are defined by the Product Engineering team. Flows may include:
  Wafer Test Flow
  Wafer Speed Binning Flow
  WLR / ICF / ECF Flows
  Wafer Level SR71 volume testing
JDP and IMFT Probe teams will jointly develop all H/W and S/W required to support the wafer test flows.

## Slide 25: 7.4 Package Test Strategy
JDP Test teams will jointly develop all single die package test capability required to support the technology development and the full product specification (S24S). Required test flows are defined by the Product Engineering team. Flows may include:
  PGSRT
  Hot Sort
  Cold Final
  Burn-in
JDP teams will jointly identify package test platforms which meet the technology development and product requirements.
JDP Test teams will jointly develop all H/W and S/W required to support the package test flows.

## Slide 26: 8.0 Budget
This SOW project scope and activities for 2018 are to be consistent with the 2018 SXP JDP budget.
Budgets for subsequent years of this SOW will be adopted on a yearly basis, as part of the overall SXP JDP budget.

## Slide 27: 8.0 Budget
Preliminary 20nm SSM Starts Plan
  This SOW project scope and activities for 2018 are to be consistent with the 2018 SXP JDP budget.
    Budgets for subsequent years of this SOW will be adopted on a yearly basis, as part of the overall SXP JDP budget.
Note that JDP managers will adjust starts plans within agreed budget constraints as required for the program