## Slide 1: SOW Contents
0.0 Purpose
1.0 Introduction
1.1 Background
1.2 Mission and Scope
2.0 Strategy
2.1 Overview
2.2 Development Vehicles
2.3 Scaling Roadmap
2.4 Alpha Product
2.5 Gen+1 Product
3.0 Milestones
3.1 Fail Check
3.2 Critical Path
4.0 Cost analysis
5.0 Process Development
5.1 Risks
5.2 Cell Stack Definition
5.3 Process Architecture
6.0 Design SOW 6.1 Key Product Specs & Constraints 6.2 Design Strategy Overview 6.3 Decoder Design and Design Rule 6.4 Design Milestones & Gates to Execution
7.0 Product/Test Development SOW
7.1 Array Development Strategy
7.2 Product Development Strategy
7.3 Wafer Test Strategy
7.4 Package Test Strategy
8.0 Budget & Assumptions

## Slide 2: 2.5 Gen+1 Product
High-level strategy definition to be reexamined and better defined (e.g. with execution plan) under scaling roadmap analysis in Q4’18.
Development Vehicle Strategy
  14nm SSM Spider Chip:
  Base silicon uses S26S, Array spider uses S36X layout High level of synergy and reuse with S26S for jump start 14nm cell scaling and structure yield
  14nm SSM Alpha Product: Fast time of transition to 14nm half-pitch product in compliance with S37A spec High level of synergy and reuse with 30series in design, tests and collateral
 | S26A | S36X | S26S | S37A | 14nm SSM Spider | 14nm SSM Alpha
Density/Die Size | 256Gb/197mm2 | 256Gb/197mm2 | 256Gb/197mm2 | 512Gb/195mm2 | 256Gb/197mm2 | 512Gb/195mm2
half pitch | 20.5nm | 14nm | 20.5nm | 14nm | 14nm | 14nm
Cell Architecture | SXP | SXP | SSM | SXP | SSM | SSM
Decoder | Unipolar | Unipolar | Bipolar | Unipolar | Bipolar | Bipolar
Read/Write Latency | 95/475 ns | 95/475 ns | 95/240 ns | 80/475 ns | 95/240 ns | 80/240 ns
Read/Write Energy | 52/118 pJ | 52/118 pJ | 52/118 pJ | 26/59 pJ | 52/118 pJ | 26/59 pJ
Read/Write Thruput | 1600/800 MB/s | 1600/800 MB/s | 1600/800 MB/s | 3200/1100 MB/s | 1600/800 MB/s | 3200/1100 MB/s
I/O and Transfer Rate | DDR4 1600MT/s | DDR4 1600MT/s | DDR4 1600MT/s | DDR5 3200MT/s | DDR4 1600MT/s | DDR5 3200MT/s
S26A based
S37A based
S26S unique
Gen+1 SSM unique
Color coding:

## Slide 3: 3.0 Milestone
Fail Check and Critical Path

## Slide 4: 3.1 Fail Check – “Fast Fail or Succeed”
# | Objectives as measured by | On or before (Calendar year)
1 | SSM switch mechanism validated with Dual Deck silicon (SR71) S26S D0 vs. D1 Read/Write polarity defined; No RWB showstopper on paper | Q2/2018
2 | S26S DBR S26S matching S26A3 die size, spec @ ½ set speed S26S Startup flow defined | Q3/2018
3 | S26S Probe yielding @ PG1 spec Silicon demonstrated, no show stopper on bipolar ops. | Q2/2019
4 | S26S Memory Qual As measured by qual success criteria @ ½ set speed | Q4/2019

## Slide 5: 3.2 Critical Path for 20nm, 14nm SSM Products and Beyond
 |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
20nm SSM | SSM RWB demonstrated on Dual Deck SR71 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S26S DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S26S Probe Yield @ PG1 Spec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | S26S Qual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14nm SSM | Spider Chip DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | RWB demonstrated, S/U Flow Defined |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 14nm SSM alpha product DBR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 14nm alpha product Qual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Scaling Roadmap Pathfinding Starts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: 4.0 Cost Analysis
S26S Die size is the same as S26A
  Bipolar decoders size should be equal or better than SXP counterpart.
Lower cost due to process simplification from partial etch architecture to single etch scheme.
Preliminary green-field analysis has been performed for cost-of-transition and cost-per-wafer
  Based assumptions for the etch simplification of 20 series SXP technology
Higher yield expected due to SSM potentially overcoming several SXP issues, including
  No cross-contamination between PM and SD
  Lower cell aspect-ratio for etch and fill
  Lower programming current  Additional relaxation to metal (WL/BL) requirements for scaling
 | CoT ($M/1k) | Delta ($M/1k) | CPW | Delta
10s -> 20s MOR | 144.9 |  | $2,274.00 | 
10s -> 4 Deck SSM | 114.8 | -30.1 | $2,040.00 | ($234.00)
10s -> 20s 2 Deck MOR | 26.1 |  | $1,559.29 | 
10s -> 2 Deck SSM | 25 | -1.1 | $1,438.25 | ($121.04)