## Slide 1
# | Objectives | Status | Issues | Resolutions

## Slide 2
Objectives:
Status:
Issues:
Recommendations:
1.
Problem Statement:
Start Date: End Date: Owners :
OSIR Template

## Slide 3: SxP Package Work Group OSIR
Accountable: | Micron-Intel co-dev
Date Updated: | Date 12/19/2014
Status
Status: – Technical
Issues – Resolution
Issue: Co-planarity out of Spec on QDP With 100um spec CpK is less than 1.0 Resolution: DOE plan in place to improve warpage which will also impact co-planarity (ECD 3/2/15)
Objectives: (Problem statement) | SXP SDP/DDP/QDP Package Development to MFG | 
Qual Readiness: |  | MFG Readiness:
Target: no High risk Status: One High risk (no rel data on functional Si) |  | Target: Mfg capability validated Status: Characterization achieved in WW47 '14 Mfg capability validation targeting SDP/DDP/QDP 7/3/15
Status: - Program
Area | Target | Status | Comments or links
Electrical | no high risk | Med | functional wafer availability
Thermal | no high risk | Low | 
Mechanical | no high risk | Med | QDP specific. Co-plan above spec. DOE WIP on solution to improve.
Board Lev Rel | no high risk | Low | 
Package Reliability | no high risk | High | Lack of array functional data No pkg related issues on peripheral functional si If needed consider BOM change
CPI | no high risk | Med | No CUP directly under Al Pad for S15B
Die Attach | no high risk | Low | 
Wirebond | no high risk | Low | bond pad DOE result clean
Encap | no high risk | Low | up to QDP
 | Target | Status | Comments or Link
MTI Ramp forecast | 100% alignment | completed | 
Risk scale:
Low risk: Have data and volume experience
Medium risk: limited data but need volume experience
High risk: no data