## plan Rev -1
|  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
20nm Test Chip | SSM RWB demonstrated on Dual Deck SR71 | bar: 2018 Q2
S24S DBR | bar: 2018 Q3
PG4 RWB Demonstrated | bar: 2019 Q1
PG1 RWB Demonstrated | bar: 2019 Q2
20nm Alpha | SSM Collateral Release (TGnMOST, DR) | bar: 2018 Q3
S26S DBR | bar: 2019 Q2
Qual | bar: 2019 Q4
Scaling Roadmap Pathfinding Starts | bar: 2018 Q4
RWB | SSM RWB demonstrated on Dual Deck SR71 | bar: 2018 Q3
14nm PF | 14nm Spider (S34X) DBR | [16 empty] | 1. based on S36X array, 2 based on option-1 bipolar decoder ==> reduce addressoible density of S36X by near 1/2 | bar: 2018 Q3
14nm Bipolar Decoder Architecture Defined | bar: 2018 Q3
14nm SSM Collateral Release | bar: 2018 Q4 to 2019 Q1
14nm Alpha | S37S DBR | bar: 2019 Q3 to 2019 Q4
S37S Storage Qual | bar: 2020 Q4
S37S Memory Qual | bar: 2021 Q1 to 2021 Q2
Scaling Roadmap Pathfinding Starts | bar: 2018 Q4
S26A PG1 PRQ
S37A PG1 PRQ

## Al's feedback
|  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
SR71 | Dual Deck RWB Demonstrated
Geometric Scaling Warrant Scaling Path
S24S | S24S DBR; Lead Product Pathfinding Start | bar: 2018 Q1 to 2019 Q4
Scaling Roadmap Development Start | bar: 2018 Q1 to 2019 Q4
Lead Product Pathfinding Success Criteria met* | bar: 2018 Q1 to 2019 Q4
S24S PG4 Qual; Lead Product Design Triggered | bar: 2018 Q1 to 2018 Q4; 2019 Q2 to 2019 Q4
S24S PG1 Qual | bar: 2018 Q1 to 2019 Q3
4
|  | 4 | 16
|  | 2 | 32
|  | 128 | 4
|  | 1 | 4
|  | 32 | 128

## scratch pad
|  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
20nm Test Chip | SSM RWB demonstrated on Dual Deck SR71 | bar: 2018 Q2
S24S DBR | bar: 2018 Q3
PG4 RWB Demonstrated | bar: 2019 Q1
PG1 RWB Demonstrated | bar: 2019 Q2
20nm Alpha | SSM Collateral Release (TGnMOST, DR) | bar: 2018 Q3
S26S DBR | bar: 2019 Q2
Qual | bar: 2020 Q1
Scaling Roadmap Pathfinding Starts | bar: 2018 Q4
RWB | SSM RWB demonstrated on Dual Deck SR71 | [16 empty] | 1. DD on 20.5nm, 2 14nm PQ SD for RWB | bar: 2018 Q3
14nm PF | 14nm Spider (S34X) DBR | [16 empty] | 1. based on S36X array, 2 based on option-1 bipolar decoder ==> reduce addressoible density of S36X by near 1/2 | bar: 2018 Q3
14nm Bipolar Decoder Architecture Defined | bar: 2018 Q3
14nm SSM Collateral Release | bar: 2018 Q4 to 2019 Q1
14nm Alpha | S37S DBR | bar: 2019 Q3 to 2019 Q4
S37S Storage Qual | bar: 2020 Q4
S37S Memory Qual | bar: 2021 Q2
Scaling Roadmap Pathfinding Starts | bar: 2018 Q4
S26A PG1 PRQ
S37A PG1 PRQ