## Slide 1: Series 20 SxP IM JDP SOW
Version 4.0
July 20th, 2015

## Slide 2: Signature Page
This SxP Joint Development Program Statement of Work Rev 4.0 (“20s SxP Memory SOW”), having been approved by the JDP Committee is hereby approved by Intel and Micron respectively effective as of July 20th, 2015, as signified by the signature of each company’s authorized representative below. It is understood and agreed that this JDP SOW may be amended in due course in accordance with the procedures set forth in the Joint Development Program Agreement.
MICRON TECHNOLOGY, INC. INTEL CORPORATION
By: By:
Name: Name:
Date: Date:

## Slide 3: Revision Page
Approval Date | REV | Pages Affected | Was | Is | Comments
05-20-2014 | 0.0 | ALL |  | 20s SxP Pathfinding SOW | 
09-15-2014 | 1.0 | ALL |  | 20s SXP Pathfinding SOW Update | 
10-23-2014 | 2.0 | ALL |  | 20s SXP Interim SOW | 
02-19-2015 | 3.0 | ALL |  | 20s SXP SOW | 
07-16-2015 | 4.0 | Cost, Schedule related slides |  | 20s SXP SOW Update | 
Notes: 3

## Slide 4: SOW Contacts
Al Fazio Intel JDP co-manager
Russ Meyer Micron JDP co-manager
Greg Atwood Micron Design
Naga Chandrasekaran Micron TD
Daniel Elmhurst Intel Design
Doyle Rivers Intel Product
Shafqat Ahmed Intel TD

## Slide 5: SOW Contents
0.0 SOW purpose
1.0 Strategy Overview
  1.1 20s Strategy
  1.2 Scaling Roadmap
2.0 Project Milestones
3.0 20s Cost/GB Scaling
  3.1 S26A die size and Risks
  3.2 20s Cost/GB projection
4.0 Proc. Dev. Challenges
  4-deck strategy
  Stacked on-pitch-via
  10s vs. 20s Process Arch diff.
  Development vehicles
5.0 Design SOW
  Strategy
  Key design features
  Arch/ Chop Strategy
  Milestones
6.0 Product Development SOW
  Alpha product strategy
  Reliability and Assembly scope
7.0 Development Budget

## Slide 6: 0.0 SOW Purpose
To finalize the development strategy, as presented to the JDP committee in the interim SOW (Oct., 2014).
To enable the initial product (S26A) utilizing the 20s SxP technology
To define project deliverables thru calendar year 2016.
To define milestones and performance metrics to track the progress towards the deliverables
To define the resource allocation and budget to achieve the targeted deliverables

## Slide 7: 1.0 Strategy

## Slide 8: Strategy Overview
The goal is to minimize the need for any cell development work beyond 10s by adhering to same cell and deck configuration whenever possible. Cell integration has been the biggest challenge in 10s and it is imperative that minimal re-optimization is needed as we move to 4-deck.
  20s SXP will be based on the same WL and BL pitch (41nm) as 10s and same cell material (PM and SD), and process architecture for the array (WL 1st)
The 4-deck architecture will require a change in how different decks are connected and/or strapped using on-pitch-via (OPV) or metal layers under the array.
HV CMOS scaling will be required to accommodate additional set of driver circuitry. To minimize CMOS process development, scaling will focus on device width reduction (no change in device L).
BEOL metal pitch may require some shrinks. Final decision will depend on S26A layout analysis.
Array and BEOL process development needs will be accommodated by S15X (single-deck electrical vehicle based on S15C) and XS26A (multi-deck, array structural vehicle) that will be based on S26A core layout

## Slide 9: SXP Scaling Roadmap
10s SXP / S15B
Pitch: 41nm pitch
Decks: 2
Tile Arch: Staggered WL
Density: 128Gb
20s SXP / S26
Pitch: 41nm pitch
Decks: 4
Tile Arch: Staggered WL & BL w/ Quilt
Density: 256Gb
30s SXP / S37
Pitch: 28nm pitch
Decks: 4
Tile Arch: Staggered WL & BL w/ Quilt
Density: 512Gb
20s Goals:
1. Minimize array / cell development scope
2. Faster time to market
3. Focus on 4 decks with at least 30% cost/GB scaling at ~30% lower energy (pJ/bit)
4. Incremental HV CMOS scaling to fit drivers under array
30s Pitch Scaling req:
Cell scaling
Low resistance WL / BL material
Cost-effective 28nm pitch patterning
HV CMOS scaling to fit drivers under array
Better LV CMOS for higher speed IO
4128nm
Pitch Learning
30s SXP / S35X
Pitch: 28nm pitch
Decks: 2
Tile Arch: Staggered WL
Density: 128Gb
4 Deck
Learning
10s SXP / S15X
Pitch: 41nm pitch
Decks: 4 (phys), 2 (elec)
Tile Arch: Staggered WL
Density: 128Gb
Not focusing on 30s
In this presentation.

## Slide 10
2.0 High Level Milestones
# | Milestone | Date
1 | 20s Final Collateral (DR/Model) release | June 30th, ‘15
2 | S15X and XS26A – dev. Vehicle TO | April-July, ‘15
3 | S26A data base release | October 23 ’15
4 | S26A Ship Release * | November 15 ’16
5 | S26A Qual Release * | January 18, ‘17
* Ship Release and Qual schedule are placeholders (based on Mid-July, ‘15 projections) and will be finalized in 2H, ’15 as TD resources become available (based on 10s health)

## Slide 11: 3.0 20s Cost/GB Reduction

## Slide 12: S26A Die Size and Risks
S26A Arch / Risk / Status:
20s POR: WL 1st for 10s compatibility and 4Kx4K tile for best cost/GB
Read Disturb is the key risk with 2x WL length (4Kx4K tile size) and strapping of top and bottom WL
  Much higher current spike during read compared to S15B ( may require longer SET back pulse )
Set-ability
  Much higher spike during selection compared to S15B ( may degrade set-ability )
  Higher ihold due to increased WL Cap ( may degrade set-ability )
On track to meet goal of reducing read and write energy by 30% (pJ/bit)
SSR transients
being studied in
S15B with added
cap to LWL
S26A Die size projected to be ~197.1mm2
  12.70mm x 15.52mm, based on single scribe on x- and y-dimension
  4Kx4K Tile, 4-deck, 32-partitions, Quilt Arch

## Slide 13: 20s Cost/GB (Unconstrained Floor Space)
34.7% Cost/GB reduction shows the intrinsic value of the 20s SXP technology in an unconstrained floor space scenario:
- Successful collaboration between TD/Design has resulted in ~5% smaller die size
        delivering 2x density w/o changing cell size or cell collateral
        New process arch allowing strapping of top and bottom-deck WL
Used June, ‘15 MOR (from F4 for all analysis:
http://edm.micron.com/cgi-bin/mtgetdoc.exe?itemID=09005aef86575062

## Slide 14
Space constrained (15K  10.7K)
Change in Total Bit Output (10s 15K  20s 10.7K)
20s Cost/GB (Unconstrained Floor Space)
Even in a constrained floor space scenario, 33% Cost/GB reduction with > 50% Bit output can be achieved

## Slide 15: 4.0 Process Arch Challenges

## Slide 16: 4-Deck Strategy
Two key enabling process features
  Strapping top and bottom WLs in a cost-effective maner
    Requires stacked on-pitch-via OR
    Additional tight pitch metal / Via for strapping
  Able to fit in 1 extra set of drivers under the tile
    Requires HV CMOS scaling (width scaling only)
    May need tighter interconnect layers depending on the chosen tile size
WL
BL
2 BL Sockets
2 WL Sockets
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
S26 WL First, 4-Decks 2 sets of WL drivers, 2 sets of BL drivers
Isolation
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
PM
SD
1 BL Sockets
2 WL Sockets
S15B WL First, 2-Decks
2 sets of WL drivers, 1 set of BL drivers
Isolation

## Slide 17: 10s vs 20s Socket Connections using Stacked OPVs
Key 20s OPV difference is the need to drop a via on top of a 20nm line
Managing CMP topography with 4 decks expected to be a key challenge
Please view in
slide show mode
10s = Dashed line box
WL1 Socket Y
WL1 Socket X
BL0 Socket Y
BL0 Socket X
WL0 Socket Y
WL0 Socket X

## Slide 18: 10s vs 20s Process Arch
Area | 10s S15B 2Kx4K 2-deck | 20s S26A 4Kx4K 4-deck
CMOS | 17-18 mask levels Dual gate CMOS (23A/110A) | No change from 10s HV CMOS width scaling (comprehended in Si based model)
M1-M4 (Cu) | All 193-dry levels M1 single-damascene Cu M2-M4 dual-damascene Cu | V3 and M4 goes 193i (+2) M1 and M4 single damascene Cu M2-M3 remains dual-damascene Cu
Array levels | 2 decks  4 PD levels 3 OPV levels 7 193i levels for array | 4 decks  8 PD levels 5 OPV levels 13 193i levels for array
Top Metal / Passivation | Thick Al SiO2+SiON Passivation Polyimide | No Change
Comments | Total of 7 193i level OPV levels require CD shrink | Total of 15 193i level 1st- and 4th-deck WL strapping requires OPV landing on bottom-most WL Read disturb and Set-ability are key risks due to 4x higher WL Cap.

## Slide 19: Key Risks and Development Vehicles
Notes:
S15X takes priority over XS26A as it generates key data for better quantification of Set-ability and RD risk levels
Both projects will require engineering resources and Si allocation. Start of Si will be based on 10s health assessment.

## Slide 20: 5.0 Design SOW

## Slide 21: Strategy
Improve utility of CMOS under array to achieve double the density (S26 vs S15) while reducing the overall die size
  Switch from hybrid internal/external driver solution used on 10 series to full internal driver solution via quilt architecture
Achieve 30% improved write throughput by reducing write energy and enabling higher write concurrency
  Fuller use of LV signaling within the partition
  Switch from 128 tile wide partition to 16x8 grid of tiles
  Double the number of available partitions
Coherent design of low power states – power reduction, transition energy, and exit time
Continued support for capabilities necessary to support cell functionality

## Slide 22
Key Specifications / Features
Features | S15C Commit | S26
Density | 128Gbits | 256Gbits
Number of Partitions | 16 | 32
I/O Performance (Interface) | 1600MT/s/pin (DDR4) | 2000MT/s/pin (DDR4)
Read Latency | 101.25ns | 80-95ns
Write Completion Time | 475ns | 475ns
Sustained Read Throughput | 1600MB/s | 2000MB/s
Sustained Write Throughput | 550MB/s | 800MB/s
Read Power / Read Energy | 942mW / 74pJ/b | 829mW / 51.8pJ/b
Write Power / Write Energy | 739mW / 168pJ/b | 753mW / 117.6pJ/b
Idle Power | 39mW | 41mW
FSB Power (DLL off) / Exit Time | 2.3mW / 30ns | 3.5mW / 30ns
SSB Power (DLL off) /Exit Time | 500uW / 10us | 1200uW / 5us
FSB Transition Energy | 188-282nJ | 65nJ
SSB Transition Energy | 5050nJ | 1600nJ
30% improved write throughput by reducing write energy and enabling higher write concurrency
  Fuller use of LV signaling within the partition
  Switch from 128 tile wide partition to 16x8 grid of tiles
  Double the number of available partitions
Coherent design of low power states – power reduction, transition energy, and exit time

## Slide 23
Architecture
Feature/Spec | S15C | S26
Density | 128Gbits | 256Gbits
Die Size | 208.38mm2 | <200mm2
Number of Decks | 2 | 4
Partition Structure | 128 sticks in parallel 4 tiles per stick | 16 x 8 tile grid
Number of Tiles / Partition | 512 | 128
Number of Partitions | 16 | 32
Columns / Tile / Deck | 2Kbit | 4Kbit
Rows / Tile / Deck | 4Kbit | 4Kbit
Redundant Repairs | 32 row repair solns / partition 2 column repair solns / partition | 32 row repair solns / partition 32 column repair solns / partition
Cell Stack | WL – BL - WL | WL – BL – WL – BL - WL
WL Driver Placement | Center Driven / Under Tile | Center Driven / Under Tile Quilt
BL Driver Placement | Center Driven / Outside Tile | Center Driven / Under Tile Quilt
Periphery | Adjacent to Pads | Adjacent to Pads
Pads | Single Sided | Single Sided
Improve utility of CMOS under array to achieve double the density (S26 vs S15) while reducing the overall die size
  Switch from hybrid internal/external driver solution used on 10 series to full internal driver solution via quilt architecture
30% improved write throughput by reducing write energy and enabling higher write concurrency
  Fuller use of LV signaling within the partition
  Switch from 128 tile wide partition to 16x8 grid of tiles
  Double the number of available partitions

## Slide 24
Minimize the costs:
  Remove partitions 16-31
  Minimal resources and schedule
  Reduces number of partitions available for concurrent operations
    No change to read throughput: 10-12 partitions supports full throughput / limited by IO
    Write throughput reduced to 550MB/s with all 16 partitions operating concurrently (matches S15)
S25 (Chop) Strategy
REMOVE

## Slide 25: S26 Milestones
Milestone | Criteria
Rev 1 | Basic core architecture frozen / sheet level implementation of all DDS features (design and test mode)
Rev 2 | Sheet level performance validation complete / circuits ready for layout
Rev 3 | Full chip functional and performance validation of features, specifications and test modes
DBR | Database Ready for Manufacturing
Notes:
1. Rev 2 duration is longer due to accommodation of technology driven design request (+5 wks)
2. Added 3 weeks from Rev 2 to Rev3 to accommodate complexities of core layout and termination issues with quilt layout
Old POR
New POR

## Slide 26: 6.0 20s SXP Product SOW

## Slide 27: Content
Product Schedule
Product Goals
  Qualification Criteria
  Ship Release Criteria
Development & Manufacturing Strategy
  Wafer Test
  Package Test
  CMOS & Array Reliability
  Packaging and Assembly
  Product Validation & Optimization
  Qualification

## Slide 28: SXP 20s Project Schedule
Milestone | Current Projection (V4.0) | V3.0 SOW Timeline
DBR | October 23, 2015 | August 28th, 2015
F2 A0 Skip Array Probe | December 7, 2015 | 
F4 A0 1D Probe | January 11, 2016 | 
F2 Extend to EPF+ (1D) | January 18, 2016 | 
F4 A1 4D Probe 1st wafers to assembly | March 27, 2016 | December 4, 2015
F2 4D Probe | June 12, 2016 | 
F2 QS Samples Probe | August 16, 2016 | 
S26A MSC | September 9, 2016 | July 15, 2016
F2 Ship Release | November 15, 2016 | September 2, 2016
F2 Qual Release (VME) | January 18, 2017 | November 23, 2016
Notes:
Current projection is a tentative schedule – showing qual timeline, if module/PI resources at F4 become available now.
We will close on final schedule in 2H, ‘15 as 10s vs. 20s resource constraints are resolved.

## Slide 29: Product Goals – Qualification
Key Specifications | Values
Operating Temperature | 0 – 85°C (Tj)
Read Power / Energy | 909mW / 47.3pJ/b
Write Power / Energy | 704mW / 110pJ/b
tCK | 1.0ns / 1GHz
Read Latency | 95ns1
Sustained Read Throughput | 2000MB/s1
Sustained Write Throughput | 800MB/s1
Maximum Write Cycles | 1.0E7
Selected Cell Read Disturb | 1.0E9
Retention | 12 Decades @ 85°C (1us -> 1.6 wks)
RBER | 5.0E-5
Quality | 500 DPM
1. Timings referenced to 1.0ns tCK

## Slide 30: Product Goals – Ship Release
Key Specifications | Values
Operating Temperature | 0 – 85°C (Tj)
Read Power / Energy | 985mW / 71pJ/b
Write Power / Energy | 760mW / 157pJ/b
tCK | 1.25ns
Read Latency | 110ns1
Sustained Read Throughput | 1600MB/s1
Sustained Write Throughput | 550MB/s1
Maximum Write Cycles | 1.3E5
Selected Cell Read Disturb | 2.0E4
Retention | 12 Decades @ 70°C (1us -> 1.6 wks)
RBER | 6.0E-4
Quality | 5000 DPM
1. Timings referenced to 1.25ns tCK

## Slide 31: Development & Manufacturing Strategy
Initial tape-out and technology development will occur in Boise Fab 4.
No Product Qualification or Ship Release from F4.
Technology development support for F4 will include package builds, backend test development, and look-ahead qualification runs.

## Slide 32: Wafer Test Strategy
JDP Probe teams will jointly develop all wafer test capability required to support the technology development and the full product specification. The required test flows are defined by the Product Engineering team. Flows may include:
  Wafer Test Flow
  Wafer Speed Binning Flow
  WLR / ICF / ECF Flows
JDP and IMFT Probe teams will jointly develop all H/W and S/W required to support the wafer test flows.

## Slide 33: Package Test Strategy
JDP Test teams will jointly develop all package test capability required to support the technology development and the full product specification. Required test flows are defined by the Product Engineering team. Flows may include:
  Hot Sort
  Cold Final
  Burn-in
JDP teams will jointly identify package test platforms which meet the technology development and product requirements.
JDP Test teams will jointly develop all H/W and S/W required to support the package test flows.

## Slide 34: CMOS & Array Reliability
JDP Reliability teams will jointly support development of volume and bench level reliability data collection to enable technology and Product development.
JDP Reliability teams will jointly develop wafer and package test reliability flows and development line sampling plans for both intrinsic and extrinsic CMOS and array reliability issues.

## Slide 35: Packaging & Assembly Strategy
JDP Packaging teams will jointly design and development of packaging solutions which meet the product requirements.
JDP Reliability teams will jointly support simulation, characterization, electrical and physical failure analysis, and qualification of the SXP package.

## Slide 36: Product Development Strategy
JDP PE teams will jointly support product design validation, characterization, and debug.
JDP PE teams will jointly support definition and implementation of all wafer and package test flows.
JDP PE teams will jointly develop all H/W and S/W capabilities needed to support:
  µProbe / Wafer debug and EFA
  Interface Validation/Characterization
  Array Characterization
  Package EFA
JDP PE teams will jointly support product and test flow optimization to enable technology development, product qualification, and HVM.

## Slide 37: Qualification Strategy
JDP QA teams will jointly define the test flows needed for qualification. Qualification flow definition will be based on JEDEC standards adapted as needed for SXP.
JDP QA teams will support look-ahead qualification runs to enable technology development.
JDP will support silicon and package qualification which represents the envelope of the product requirements.

## Slide 38: 7.0 Development Budget

## Slide 39: Budget Planning
This SOW project scope activities for 2015 are consistent with the 2015 SXP JDP budget.
Budgets for subsequent years of this SOW will be adopted on a yearly basis, as part of the overall SXP JDP budget.

## Slide 40: BACKUP