## Sheet1
TODAY
L3 lot activity in F4 | Priority TAG | week32 | week33 | week34 | week35 | week36 | week37 | week38 | week39 | week40 | week41 | week42 | week43 | week44 | week45
S15C-Al doped PM (9904732.003) | HOT | TODAY week32: 53; TODAY week34: EOL
S15C-In doped SD Ver 12 (2% In )-rev 8.02 (9912522.003) | HOT | TODAY week32: 57; TODAY week36: EOL
S15C-In doped SD Ver 12 (2% In )-rev 7.66 (9912532.003) | Screamer | TODAY week32: 52; TODAY week34: 57; TODAY week37: EOL
S15C- WC as top lamina (9912592.003) | Normal | TODAY week32: 51; TODAY week37: 57; TODAY week41: EOL
S15C-AlOx follow up SWR (9912602.003) | Normal | TODAY week32: 51; TODAY week37: 57; TODAY week41: EOL
S15C-SiN doped SD SWR (9912512.003) | Normal | TODAY week32: 51; TODAY week37: 57; TODAY week41: EOL
S15C-Al doped PM backup lot (9904822.003) | Normal | TODAY week32: 55; TODAY week33: expect delay to wait K* completion for SSM; TODAY week41: EOL
S15C-Te skew backup lot (9904742.003) | Normal | TODAY week32: 55; TODAY week33: expect delay to wait K* completion for SSM; TODAY week41: EOL