## 30s gantt 2017
| JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
ACTIVITY | iWW22 | iWW23 | iWW24 | iWW25 | iWW26 | iWW27 | iWW28 | iWW29 | iWW30 | iWW31 | iWW32 | iWW33 | iWW34 | iWW35 | iWW36 | iWW37 | iWW38 | iWW39 | iWW40 | iWW41 | iWW42 | iWW43 | iWW44 | iWW45 | iWW46 | iWW47 | iWW48 | iWW49 | iWW50 | iWW51 | iWW52
Stack structure (aim at thin W)
1st cut FP etch/cleans
1st PL
1st cut LP etch/cleans
1st cut seal | [13 empty] | Lead S36X reaches 1st cut | [16 empty] | Electrical milestone
Electrical lot
W resistivity assessment
35nm W (1st-cut like) L1D
55nm W (2nd-cut like) L1D | [16 empty] | Electrical milestone
S36X electrical assessment
PVD W improvements
Alternate materials
L0/L1 (CLV) assessment
L1 (10s geometry)

## 30s risk items
Item | Target vs 10s | Expectations | Model | Risk vs 10s | Planned Activity | Technical risk rank | Schedule risk rank | Overall rank | Net color | Work gated by | Work begins | Work ends | Milestone @ end
IRST | 0.7X | ~0.6X | Isotropic scaling gives IRST ~ 0.6X | low | Stack optimization (e.g. 2nd cut WSiN in TE) | 6 | 5 | 30 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
Idel | 0.7X | ~0.6X | Metal r will increase at tighter pitch | high | W r @14nm h.p. evaluation/optimization Array via resistance reduction | 6 | 1 | 6 |  | On-pitch reticle (structure) S36X (electrical) | 2017-06-01 | 2017-09-30 | Initial assessment
VT s | same | worse | Volume decreasing and Area/Volume increasing will worsen variability | medium | Etch-Clean-Seal improvement SD material exploration (e.g. In-doped SD) | 4 | 5 | 20 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
tset | same | worse | CD effect / PM contam. / PM segregation | very high | PM material exploration Etch-Clean-Seal improvement WC lamina for segregation containment | 1 | 2 | 2 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
ΔVt | same | same | no PM thickness scaling | low | Design mitigation (e.g. boosted) | 6 | 5 | 30 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
WD | same | 2-4x worse | Smaller distance between cells | medium | Fill optimization Usage model mitigation | 3 | 3 | 9 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
RDG | same | same | Alternative seal/fill could worsen parasitics | low | 1st cut AlxOy WSiN/AlxOy in BE Design mitigation | 4 | 4 | 16 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
E3 shift | same | equal to worse | SD contam. / E/I evolution | low | Etch-Clean-Seal improvement E/I stabilization (e.g. AlxOy SD lamina) | 5 | 5 | 25 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
Ihold | 0.7X | > 0.7x | Ihold depends on parasitics and can limit set-ability (nucleation) | high | Simulation S36X evaluation | 2 | 2 | 4 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
Drift | same | equal to worse | Stronger segregation | medium | SD material exploration (e.g. In-doped SD) Usage model mitigation | 4 | 2 | 8 |  | S36X (electrical) | 2017-10-01 | 2017-12-31 | Initial assessment
[6 empty] | 1=definite risk/no known solution | 1= strong design impact |  |  |  |  | Dates above reflect current SOW
|  | Version is as of 6/26 - swrussell/aredaelli/fpellizz |  |  |  | 2=likely risk/unproven solution | 2 = chal materials exploration
[6 empty] | 3=likely risk/inconvenient solution | 3 = other materials exploration
[6 empty] | 4=probable risk/unproven solution | 4 = process development required
[6 empty] | 5=probable risk/design solution expected | 5 = not time critical
6=low risk/expect to near tgt