## Activity table
Item | Target vs 10s | Expectations | Model | Risk vs 10s | Planned Activity | Technical risk rank | Schedule risk rank | Overall rank | Net color
IRST | 0.6X | ~0.6X | Isotropic scaling gives IRST ~ 0.6X | low | Stack optimization (e.g. 2nd cut WSiN in TE) | 6 | 5 | 30
Idel | 0.6X | ~0.6X | Metal r will increase at tighter pitch | low | W r @14nm h.p. evaluation/optimization | 6 | 1 | 6
VT s | same | worse | Volume decreasing and Area/Volume increasing will worsen variability | medium | Etch-Clean-Seal improvement / SD material exploration (e.g. In-doped SD) | 4 | 5 | 20
tset | same | worse | CD effect / PM contam. / PM segregation | high | PM material exploration / Etch-Clean-Seal improvement / WC lamina for segregation containment | 1 | 2 | 2
WD | same | 2-4x worse | Smaller distance between cells | high | Fill optimization; usage model | 3 | 3 | 9
RDG | same | same | Alternative seal/fill could worsen parasitics | low | 1st cut AlxOy; WSiN/AlO in BE; design | 4 | 4 | 16
E3 shift | same | equal to worse | SD contam. / E/I evolution | low | Etch-Clean-Seal improvement / E/I stabilization (e.g. AlxOy SD lamina) | 5 | 5 | 25
Ihold | 0.5X | lower | Ihold depends on parasitics and can limit set-ability (nucleation) | medium | Simulation / S36X evaluation | 2 | 2 | 4
Drift | same | equal to worse | Stronger segregation | medium | SD material exploration (e.g. In-doped SD); usage model | 4 | 2 | 8
[6 empty] | 1=definite risk/no known solution | 1= strong design impact
[6 empty] | 2=likely risk/unproven solution | 2 = chal materials exploration
[6 empty] | 3=likely risk/inconvenient solution | 3 = other materials exploration
[6 empty] | 4=probable risk/unproven solution | 4 = process development required
[6 empty] | 5=probable risk/design solution expected | 5 = not time critical
6=low risk/expect to near tgt