## Risk Management
Category | problem description | quantification | Risk | model | strategy | Comment
Read Energy (VHH – VNN) vs. Set Vt DTS (VDM and Vinh) | Design self-consistent read configuration between cell Vt and +/-3.3V voltage supply favorable for read energy | Vhh-Vnn = 6.6V VDM 85C: 6.29V[2sigma vdm + vdm2 drift + circuit overhead - cascode drop] vhh->vpp transition temperature: 25C | 3.0 | N/A | - evaluate the viability and DTS change to 7.76 including -350mV vdm change, and 5x inhibit leakage reduction.
Read Latency: 10ns Tsense reduction | 10ns tsense reduction, in order to delivery 80ns read latency, results in potential RWB loss. | 10s data with 25ns tsense comared to 35ns POR: ZoneA: Time 0 RWB: -100mV E2 vdm1 margin: -200mV E3 vdm1 margin: +100mV Post cycle RWB: -60mV, less risk ZoneDE: Vt shift due to tsense reduction of 10ns is <=10mV | 2.0 | -Vdm ramp time and actual voltage delivery -threshold delay statistics interacting with SD composition, thickness, CD, etc… | - volume data collection [WLR] in 10s to explore variation of tsense and cell scaling impact. - assess 30s vs 10s in simulation. Ensure transient time is no worse in 30s. - assess drift of 48 hours
Read Functionality: E2 RBER – Ihold impact to ISSR | Cell read current delivery is lower than Ihold at near region causing potential read functionality issue. | 30s NN: tt: Ihold 21, ISSR [mirror set @25uA] delivery 17uA, 2.5uA gap ss: Ihold 21, ISSR [mirror set @25uA] delivery 11.8A, 9.2uA gap 10s data shows no read functionality issue with ISSR 10uA lower than cell Ihold. BER does not change. | 2.5 | -30s pheriphery circuit path R increases compared to 20s due to die size reduction. - Ihold is expected to stay unscaled for 30s compared to 20s. | - uprobe trace data collection for low ISSR
Read Reliability: RD – eSSR current delivery | Ensure eSSR grow current delivery and read disturb | N/A | 2.5 | N/A | - eSSR
Write Energy: IReset | Write energy is higher than spec | 91.57pJ/bit DTS 0.5 with 60% Ireset scaling assumption, 82.74pJ/bit with 50% Ireset scaling assumption, ~1pJ/uA Spec 64pJ/bit | 1.5
Write Completion time | Projected nucleation time of 30s cell makes write completion time exceed spec | grow time does not increase. nucleation time: 10s/20s PG1 EOL 3.54s: 95ns theoretical calculaiton for 30s: 190ns 10s CD skew projection for 30s: 600ns | 1.5 | - skinning effect along PM sidewall due to oxidization is more signficant for smaller CD - process transfer function is different with smaller CD | - assessment of better ambient control - evaluate the impact of transfer function [more Ge% loss and x-contam] - new PM material exploration
RWB: PM thickness vs. Thermal disturb
RWB: memory effect exploitation vs. elimination | quantify memory effect and its reliability through product lifetime. | N/A | 2.5 | - SD phase segregation due to electrical pulse - electrode - threshold point modulated by electrical pulse beyond phase segregation | - elimination or deploy memory effect for 30s: ** define memory effect metrics **pick key silicons for assessment - define success criteria for 30s memory effect ** validate the scalability of memory effect
set drift management | 3.54sigma 10s to 48 hour drift [UD+BD] is higher than vdm2-vmd1, resulting in high read retry | QW4: RWB 2E-4 ~390mV [7.74, QW4 WIP] VDM2-VDM1: 350mV Read retry rate: ~1E-2 | 2.0
PM material: RWB vs. Set latency | With PM2A3, 31ns is not able to deliver DTS DVT, and tnuc needs 95ns in PG1. |  | 1.5 |  | Explore new PM material options for DVT and set speed
|  |  | 1 | show stopper; no technical path
|  |  | 1.5 | potential show stopper w/ some technical path (e.g., PM scaling)
|  |  | 2 | high risk to resolve issue
|  |  | 2.5 | high risk; data needed to vet strategy (e.g., WSiNless via)
|  |  | 3 | manageable risk